|  | IQVIATM Work Instruction Feasibility |
| --- | --- |
|  | Document Number and Revision: CS_WI_TSS0005 Revision 4 |
| Document Owner: Irene Neilson | Author(s): John Hillier |

- PURPOSE

The Feasibility Analytics team is responsible for leading and facilitating the assessment of whether a study is operationally possible and, if so, where (which countries), including the risks and necessary mitigation strategies. This work instruction (WI) describes the process the Feasibility team follows to make these assessments.

- SCOPE

  - This WI applies to IQVIA staff involved with a Feasibility request for pre-award opportunities and post-award projects, excluding IQVIA Biotech. Feasibility can be a part of many different situations (i.e., different client or internal project team requests), for example:

    - A Request for Proposal (RFP)/Proposal Process

    - Strategic partnerships that may include the RFP/Proposal process or may include other agreed-upon ways of working

    - Stand-alone awarded (paid) Feasibility work

    - Non-compete awarded work

    - A rescue effort to support ongoing projects

    - Early Engagement

- ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

Note: For projects originating in Real World (RW) or Early Clinical Development (ECD), the responsibilities and processes described in this WI will depend on the individual project Scope of Work (SoW). When this occurs, appropriately trained RW or ECD staff will perform these responsibilities unless otherwise agreed upon or if alternative SOPs or Project Instructions (PI) are in place.

| Role | Sections |
| --- | --- |
| Analytics Strategy Lead (ASL) | 6.2, 6.3 |
| Business Development (BD) Representative (Rep) | 6.1, 6.2, 6.3 |
| Country Site Activation Representative (CSA Rep) Representative – formerly known as Local Feasibility Lead | 6.2, 6.3 |
| Feasibility Analytics Lead (FAL) | 6.1, 6.2, 6.3 |
| Feasibility Management Team (FMT) | 6.3 |
| Medical Strategy Lead (MSL) | 6.2, 6.3 |
| Resource Management Team (RMT) | 6.1, 6.3 |
| Site Analytics Lead (SAL) | 6.2, 6.3 |
| Therapeutic Medical Advisor (TMA) | 6.2, 6.3 |
| Therapeutic Strategy Lead (TSL) | 6.2, 6.3 |

- DEFINITIONS

Refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services

- MATERIAL AND EQUIPMENT

Not Applicable

- PROCEDURE

  - Request for Feasibility and Resource Assignment

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | BD Rep | Triages feasibility request within Customer Relationship Management (CRM) system. | Pre-Award: Upon receipt of opportunity requiring feasibility assignment |
| 6.1.2 | RMT | Assigns feasibility request to appropriate FAL within CRM |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.3 | FAL | Reviews RFP to determine project requirements, size, and complexity | Pre-Award: Within 24 hours of assignment |
| 6.1.4 |  | Takes one of the following actions: - If feasibility request is part of the RFP / Proposal process, Early Engagement or a Strategic Partnership that include the RFP / Proposal process go to Section 6.2 - If feasibility request is Stand-alone awarded feasibility work, go to Section 6.3. |  |

  - Planning and Executing a Feasibility Exercise during the Pre-Award Phase

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | ASL | Schedules the Data Planning Call with TSL, FAL, MSL/TMA | Pre-Award |
| 6.2.2 | FAL | Attends the Strategy call (for Core Clinical studies) or Scoping call (for RW studies) to determine the SoW and feasibility requirements. |  |
| 6.2.3 |  | Performs initial data acquisition after initial scoping. Works closely with the proposal development team to refine deliverables for strategy development | As needed, and dependent on opportunity and SoW |
| 6.2.4 | TSL | With input from the proposal development team, creates the delivery strategy based on available data, data acquisition and sponsor requirements | Pre-Award |
| 6.2.5 | FAL | In consultation with the TSL, defines if opportunity will benefit from site outreach - If opportunity requires site outreach, FAL requests BD Rep to obtain written sponsor approval before conducting the site outreach exercise. | Pre-Award phase; during strategy call or other appropriate decision point prior to site outreach commencing |
| 6.2.6 | BD Rep | Requests specifics as to what, and how much, information can be released. If Sponsor gives permission to release some level of project information to sites/Investigators, skip to step 6.2.8, Unblinded Feasibility Site Outreach. Otherwise, go to step 6.2.7, Blinded Feasibility Site Outreach | Prior to any site outreach |
| 6.2.7 | FAL | ** Blinded Feasibility Site Outreach ** Ensures that no information regarding Sponsor, Investigational Product (IP), or other details that could “unblind” a project, is listed within the Feasibility Survey Questionnaire (FSQ) and involuntarily released to any sites released to any sites. Note: A feasibility project that is blinded to Sponsor and IP details does not require a Confidential Disclosure Agreement (CDA). | As required |
| 6.2.8 |  | ** Unblinded Feasibility Site Outreach** |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | An unblinded feasibility site outreach may be required for RFP support or as part of a standalone project. - For standalone projects go to Section 6.3 - For unblinded feasibility site outreach for RFP support,, go to step 6.2.9 Note: A CDA is required to be in place with the Investigator site. Works closely with the CSA Rep to execute CDA with the Investigator site(s) if CDA is not in place already (e.g., Partner/Prime site). |  |
| 6.2.9 | FAL | Gathers additional data (e.g., IQVIA experience, IQVIA past performance, Sponsor experience, site/primary Investigator experience, and market environment) Where a CDA is required, FAL determines the type of CDA that should be used: - If a CDA is not required or is already executed (e.g., Master CDAs (mCDA) - If an existing CDA template is not used, confirms the appropriate CDA template and fallback language to be used. | As required |
| 6.2.10 |  | Launches site outreach activity | If Sponsor has agreed on site outreach |
| 6.2.11 | CSA Rep | Performs site outreach - Blinded Feasibility Site Outreach – CSA Rep distributes FSQ to a list of “suitable for the study” sites by sharing the FSQ link and FSQ Word Document - Unblinded Feasibility Site Outreach – CSA Rep approaches the “suitable for the study” sites and invites them to sign a CDA form in line with confidentiality requirements. - Notifies the FAL if the site requests changes to the approved CDA template. - Upon receiving the executed CDA CSA Rep sends the FSQ by sharing the FSQ link and FSQ Word Document - Tracks all finalized CDA, FSQ and follow-up attempts in the Clinical Trial Management System (CTMS) | As required |
| 6.2.12 |  | Follows up with non-responding sites via email/telephone call |  |
| 6.2.13 |  | Provides the FAL with list of contacted sites |  |
| 6.2.14 | FAL | Interprets feasibility results | Upon receipt of data from sites |
| 6.2.15 |  | Produces feasibility deliverable to include feedback/ recommendations/reporting based upon agreed scope and expectations | By requested deadline |
| 6.2.16 | FAL | Includes feasibility deliverable in Proposal Knowledge Information Transfer (P-KIT) | Upon award |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.17 |  | Collaborates with ASL, TSL and / or MSL / TMA to add strategic and/or medical input to feasibility. | When requested |
| 6.2.18 |  | Performs data analysis of all available data gathered as part of data acquisition. | By requested deadline. |

  - Conducting a Paid Feasibility Exercise

A “paid feasibility” typically results in a Feasibility Report or comparable client deliverable (e.g., slides)—independent of the vehicle type (e.g., RFP, stand-alone work, etc.). Each is designed to meet the specific needs of the project.

The three main steps performed as part of a paid feasibility include:

- Prepare a customized proposal covering scope, objectives, methodology and budget to conduct feasibility.

- Lead a cross functional team for study conduct and data collection.

- Data analysis and reporting.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | BD Rep; RMT | Secures functional leads to support feasibility (e.g., TSL, Project Leader (PL) / Project Leadership Representative (PL Rep), MSL or TMA, etc.) | Pre-Award |
| 6.3.2 | FAL | Defines initial scope and objectives for paid feasibility and prepares a detailed costing and proposal. | Setup |
| 6.3.3 |  | Performs initial data acquisition (dependent on opportunity and SoW) |  |
| 6.3.4 | FAL | In consultation with the TSL/PL/PL Rep, confirms setup of project systems (e.g., IQVIA Resource and Portfolio Management (QRPM), CTMS, project SharePoint) with project code included, as appropriate | Upon award |
| 6.3.5 |  | Schedules Feasibility External Kick-off Meeting (KOM) with Sponsor |  |
| 6.3.6 |  | Attends Feasibility External KOM with supporting team to confirm / refine scope and objectives, discuss methodology, and reporting requirements. Note: It is mandatory that FAL and BD Rep attend this External KOM. It is suggested that TSL, MSL / TMA also be invited. | Set up |
| 6.3.7 |  | Contributes to Work Order |  |
| 6.3.8 |  | Upon draft or agreed country list, sends heads-up email to Country Lead Mailbox | Start Up |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.9 |  | Ensures and verifies appropriate regional CDAs being used, and that Sponsor/IQVIA are both in agreement |  |
| 6.3.10 |  | Ensures that Sponsor-provided CDA templates are approved by IQVIA’s Office of General Council | Prior to distribution to sites |
| 6.3.11 | FAL | Informs all countries of interest through the regional mailboxes about the upcoming Paid Feasibility and requests resources to support the project accordingly | Start Up |
| 6.3.12 | FAL | ** Feasibility Survey Questionnaire ** Reviews additional information provided by Sponsor during data acquisition, to generate the Feasibility Survey Questionnaire (FSQ). | Start Up |
| 6.3.13 |  | Sends FSQ to TSL, PL/PL Rep, and MSL or TMA for review and revisions. | As needed |
| 6.3.14 |  | Makes any required revisions |  |
| 6.3.15 |  | Sends FSQ to Sponsor for review and approval | Start up |
| 6.3.16 |  | Creates Feasibility Launch Package. The Launch Package includes (but is not limited to): Information on study (Indication, targeted patient segment, Sponsor etc.), Sites’ profile, required number of site responses, timelines. Attachments with Study protocol (where available), CDA (for unblinded site outreach), FSQ in Word format, Tiered Site List (if provided for the site outreach) etc. Note: “Launch” refers to the process of creating and gathering all applicable information and documents that will be provided to the CSA Reps for use in the site outreach. | After receiving Sponsor’s approval on any documents or information to be sent to sites |
| 6.3.17 | FAL | Conducts training call with CSA Reps with input from MSL or TMA, TSL,PL/PL Rep | Prior to feasibility launch, and if applicable |
| 6.3.18 |  | Sends Feasibility Launch Package to CSA Rep (i.e., applicable country and/or regional mailboxes) |  |
| 6.3.19 | CSA Rep | Collects CDA (for unblinded site outreach) from sites, if needed. (refer to step 6.2.11). | Conduct as needed |
| 6.3.20 |  | Distributes FSQ to sites, along with instructions and due dates |  |
| 6.3.21 | MSL or TMA | Addresses therapeutic questions raised by site/Investigator | If applicable |
| 6.3.22 | CSA Rep | Manages/collates CDAs and survey responses and other relevant country/site information including clarifying any survey responses with the site | Conduct as needed |
| 6.3.23 | FAL | Performs QC on survey data, and clarify any unclear survey responses with the CSA Rep. | Conduct as needed |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.24 | FAL | Compiles, reviews, cleans, and analyzes data received from sites, as well as any country summary information received from CSA Rep with input from all the cross functional team members. |  |
| 6.3.25 |  | Provides regular status updates to the sponsor as agreed in the scope and the KOM. |  |
| 6.3.26 | MSL or TMA | - Addresses therapeutic questions raised by the sites/investigators. (These would be referred to the MSL/TMA by the FAL) - Contributes to analysis of feasibility data based on searches, using resources such as medical journals, country standard of care guidelines, etc. - Provides input on projection of Serious Adverse Event (SAE) percentages for certain therapeutic indications - Gathers input on variations in standard of care and recruitment between countries | Conduct as needed |
| 6.3.27 | FAL | Schedules a Metrics Analytics Projections (MAP) call with the TSL/ MSL/ ASL to run enrollment simulation and create enrollment scenarios | Conduct as needed |
| 6.3.28 | FMT | Reviews Feasibility Report/deliverable, with input from TSL,PL/PL Rep, MSL or TMA | Consuct as needed |
| 6.3.29 | FAL | Sends deliverable to Sponsor | As agreed in SoW |
| 6.3.30 |  | Hosts feasibility review meeting with Sponsor, including FAL, TSL, MSL or TMA, PL, Global Solutions Manager (GSM) | If needed |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_TSS0005 | Feasibility | 3 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Update to job roles | 3 | Organizational changes. |
| Additional text to clarify responsibilities for FAL and CSA Rep | Throughout | Unclear / missing detail around responsibility and confidentiality. |

| Process steps updated throughout | Throughout | To reflect current process and add clarity |
| --- | --- | --- |

- APPENDICES

Not Applicable

Page 8 of 8

Copyright © 2016, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Ferrari, Antonio (q844337) Title:

Date: Friday, 25 February 2022, 07:24 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Obara, Kris (kobara) Title:

Date: Friday, 25 February 2022, 09:04 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Monday, 28 February 2022, 11:15 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Sneed, John (q109205) Title:

Date: Wednesday, 02 March 2022, 11:54 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================