|  | IQVIATM Operating Procedure Study Close Out |
| --- | --- |
|  | Document Number and Revision: CRO_OP_CTS0004 Revision 3 |
| Document Owner: Lewis Prior | Author(s): Stacy Lamb, Kerry Tingley, Karolina Zabawa, Ulrika Böiers |

- PURPOSE

To provide instruction on the handling of clinical supply returns, destructions and all core study close out related activities that need to be executed by the Clinical Trial Supplies (CTS) Team.

- SCOPE

This operating procedure (OP) applies to all studies where the CTS team are contracted to provide Clinical Supply Chain Management Services.

It applies to all Clinical Trial materials that are managed by the IQVIA CTS team and located at the vendor depots and/or at clinical sites.

All documentation related to Clinical Supplies that are managed by the IQVIA CTS team are also in scope.

- ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this OP:

| Role | Sections |
| --- | --- |
| Clinical Trial Supplies (CTS) Personnel (see Section 4.0) | All |

- DEFINITIONS

Ancillaries: Other tools and equipment used throughout the clinical trial which either aid in IP/Comparator administration or vital in the preparation of the IP/comparator to be used throughout the study.

CoD: Certificate of Destruction – A document provided as evidence that Clinical Trial Material has been disposed of safely.

Clinical Trial Supplies: Any IP, NIMP, placebo product, marketed drug product (i.e. comparator) or ancillary item for drug preparation or administration (i.e. intravenous (IV) saline bag, syringe) used by investigator sites in the conduct of a clinical trial.

CTS Team: Clinical Trial Supplies Team (This could be a Clinical Supply Coordinator, Associate Clinical Supply Chain Manager, Clinical Supply Chain Manager, Senior Clinical Supply Chain Manager, Associate Director, Director or Senior Director)

Comparator: An Investigational or marketed product used as a reference in a clinical trial.

IRT: Interactive Response Technology, also known as IVRS or IWRS – A Web based platform that provides complex subject/activity management functionality and robust management of drug supply and shipping throughout the trial.

IPs: Investigational Products – A product being tested or used as a reference in a clinical trial.

SmPC: Summary of Product Characteristics – A legal document approved as part of the marketing authorization of each medicine; it is the basis of information for healthcare professional on how to use the medicine, which information is updated throughout the lifecycle of the product as new data emerge.

- MATERIAL AND EQUIPMENT

Trial Master File (TMF)

- PROCEDURE

Timelines given for each step are for guideline purposes only. The bespoke requirements of individual studies may impact the timelines.

  - Oversight of Returned Goods and The Reconciliation Process

Strategy for the destruction of damaged, unused and/or expired clinical supplies is devised and agreed upon at the start of all studies.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | CTS Team | Liaise with the sponsor and study team to determine the level of accountability and reconcilation (i.e. tablet/capsule/vial level, kit level etc) to be performed. For instructions on accountability performed at clinical sites, see CS_WI_SM0010 Investigational Product (IP) Handling and Monitoring. | Study Start |
| 6.1.2 | CTS Team | Liaise with the sponsor and study team in order to understand if destruction can be performed at site or if material needs to be returned to local depots for destruction. For instructions on destruction performed at clinical sites, see CS_WI_SM0010 Investigational Product (IP) Handling and Monitoring | Study Start |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.3 | CTS Team | Ensure any relevant vendor quotes contain the required budget for the execution of the agreed upon reconciliation and destruction strategy (where applicable). Note: Prior to closing out all Purchase Orders, CTS will ensure all outstanding invoices have been received from all vendors and processed accordingly. | Following steps 6.1.1 and 6.1.2 if local depot is performing reconciliation and destruction |
| 6.1.4 | CTS Team | Liaise with the clinical team, distribution vendor, IRT vendors and any other vendors required to ensure the return and destructions process runs smoothly. CTS must ensure that all requirements are met, and any discrepancies are investigated by the team and recorded appropriately. | During Study Close Out or When Required |
| 6.1.5 | CTS Team | Where applicable, the CTS personnel track stock returns from initiation of the process to its completion. It is the responsibility of CTS to ensure that the returns and destruction process is completed. See CRO_TP_CTS0011 for Returns and Destruction tracker template Note: Liaising closely with CRAs/Clinical Study teams and IRT vendors is vital in order to ensure that the destruction strategy is fully executed and as planned. | During Study Close Out/ End of Study Close Out or When Required |
| 6.1.6 | CTS Team | Where sites are destroying material locally ensure you receive confirmation from Clinical that all destruction has been completed fully and to ensure that IRT is updated accordingly. | Upon completion of Destruction |

  - Inventory Destruction at Vendor Depots

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | CTS Team | Liaise with the distribution vendor in order to facilitate the destruction process and to provide support with any IRT related issues as required (see Distribution Setup & Product Disposition at Vendor Facility CRO_OP_CTS0003 for approval of product disposition process steps) | During Study Close Out/ End of Study Close Out or When Required |
| 6.2.2 | CTS Team | Resolve any discrepancies with returned stock and documentation at the depot by being the link between the clinical team, distribution vendor and IRT vendor. | During Study Close Out/ End of Study Close Out or When Required |
| 6.2.3 | CTS Team | Where appropriate, ensure that the distribution vendor confirms returns in the IRT system. | Upon completion of Destruction |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.4 | CTS Team | Once destruction has been carried out, obtain a Certificate of Destruction (CoD) from the distribution vendor and upload into eTMF. | Upon completion of Destruction |
| 6.2.5 | CTS Team | Where appropriate, ensure that the distribution vendor confirms stock destruction in the IRT system. | Upon completion of Destruction |

  - Archiving

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | CTS Team | Ensures all documentation collected through the lifecycle of any given study are uploaded into the relevant IQVIA e-TMF platform as they become available. Including but not limited to: TE excursion tracker, manual or Berlinger | Throughout the lifecycle of the study During Study Close Out/ End of Study Close Out |
| 6.3.2 | CTS Team | Reference Distribution Setup & Product Disposition SOP CRO_OP_CTS0003 for information on requesting disposition reports from distribution vendor for all clinical materials in order to review and process for destruction. Note: File all approved disposition reports in the e-TMF | During Study Close Out/ End of Study Close Out |
| 6.3.3 | CTS Team | Prior to IRT Close Out, liaises with the clinical lead on closing out the IRT system. Prior to IRT closure, CTS will download a batch to patient report (showing specific material administered to specific patients) and any other relevant reports from the IRT system and upload to the e-TMF | Prior to IRT Close Out |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CRO_OP_CTS0003 | Distribution Setup & Product Disposition at Vendor Facility |
| 7.2 CS_WI_SM0010 | Investigational Product (IP) Handling and Monitoring |
| 7.3 CRO_TP_CTS0011 | Returns and Destruction Tracker Template |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CRO_OP_CTS0004 | Study Close Out | 2 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Definitions for CTS team and Clinical Trial Supplies listed | 4.0 | To state CTS definitions for CTS Team and Clinical Trial Supplies |
| References to CS_WI_SM0010 Investigational Product (IP) Handling and Monitoring | 6.1 | To cross reference the handling and monitoring procedures for Investigational Product (IP) at clinical sites |
| Reference to CRO_TP_CTS0011 Returns and Destruction Tracker Template added and appendix 10.1 (a sample tracker) removed | 6.1 | To reference the Returns and Destruction Tracker Template |
| Removed section related to CTS providing Clinical and CRAs with training on close out requirements Section numbers updated | 6.1.4 | CTS are not responsible for training Clinical and CRA during the study we will work closely with all groups to ensure that activities are understood and carried out as required. |
| Wording changes made throughout for clarity | Throughout | Ensure consistency and clarity |
| Section reworded to clarify the role CTS play when sites destroy material locally | 6.1.7 to 6.1.6 | CTS do not need to track destruction of material when this is performed locally by sites. Oversight of this activity is performed by Clinical. |
| Documentation examples added | 6.3.1 | Additional clarity |
| Removed section as eTMF upload covered in section 6.3.1 Section numbers updated accordingly | 6.3.2 | 6.3.1 already covers the need to upload documents into eTMF |
| Updated IMP to IP | Throughout | Ensure consistency through document |

- APPENDICES

Not Applicable

Page 5 of 5

Copyright © 2020, 2023 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Lamb, Stacy (u1082363) Title:

Date: Tuesday, 14 February 2023, 03:13 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Prior, Lewis (lprior) Title:

Date: Thursday, 16 February 2023, 07:32 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================