|  | IQVIATM Operating Procedure Clinical Trial Supplies Project Setup |
| --- | --- |
|  | Document Number and Revision: CRO_OP_CTS0016 Revision 2 |
| Document Owner: Lewis Prior | Author(s): Stacy Lamb |

# PURPOSE

The purpose of this SOP is to describe the process for initiating a study for projects involving IQVIA CTS Team services.

# SCOPE

  - This operating procedure (OP) applies to all IQVIA CTS staff, including contract and temporary staff.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this OP:

| Role | Sections |
| --- | --- |
| Clinical Trial Supplies (CTS) Personnel | 6.1, 6.2, 6.3, 6.4, 6.5 |

# DEFINITIONS

Comparator: An investigational or marketed product used as a reference in a clinical trial

CMO: Contract Manufacturing Organization (provides drug packaging and distribution services)

CTS: Clinical Trial Supplies – Any IMP, placebo product, marketed drug product (i.e. comparator), or ancillary item for drug preparation or administration (i.e. intravenous saline bag, syringe) used by investigator sites in the conduct of a clinical trial.

CTS Team: Clinical Trial Supplies Team – This could be a Clinical Supply Chain Coordinator, Associate Clinical Supply Chain Manager, Clinical Supply Chain Manager, Senior Clinical Supply Chain Manager, Associate Director, Director, or Senior Director.

FPI: First Patient In – First Subject Screened, if this is a project milestone; OR First Subject Enrolled, if First Subject Screened is not a relevant project milestone; OR First Subject Randomized, if First Subject Enrolled is not a relevant project milestone.

GMP: Good Manufacturing Practice – regulations and standards for drugs stating minimum requirements for the methods, facilities and controls used in manufacturing, processing and packing of a drug product. The regulations make sure that a product is safe for use and that is meets the relevant specifications.

Page 1 of 6

Copyright © 2021, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

IRT: Interactive Response Technology – Electronic system that provides complex subject/activity management functionality and robust management of drug supply and shipping throughout the trial.

IMP: Investigational Medicinal Product – A pharmaceutical form of an active ingredient or placebo being tested or used as a reference in a clinical trial, including a product with a marketing authorization when used or assembled (formulated or packaged) in a way different from the approved form, or when used for an unapproved indication, or when used to gain further information about an approved use.

PL: Project Leader – Ensures overall project delivery and financial success, drives project quality and performance excellence, owns customer relationship for the project, develops integrated Project Management Plan and manages project performance (with PMA), proactively manages project risks and contingencies, and project team resourcing.

PMA: Project Management Analyst – Assists in ongoing project performance, monitoring and communication, directs and coordinates project scheduling, finance and risk management, facilitates timely project execution and objectives, assures effective project reporting, and develops and manages Integrated Project Management Plan sections.

QP: Qualified Person – Under European Union law, the qualified person is responsible for certifying that each batch of a medicinal product meets all required provisions when released from a manufacturing facility within the EU, or imported into the EU. Such provisions include that the batch was manufactured under appropriate standards, and that it passed all required testing.

RACI: A document which defines which party is Responsible, Accountable, Consulted, and Informed of each activity during a study.

TMF: Trial Master File – All of the documentation (i.e., documents, records, data) relating to a clinical trial. The TMF is the primary document repository maintained throughout the project lifecycle.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - CRO_TP_CTS0014 Clinical Supply Plan and Project Scope Document

A Clinical Supply Plan and Project Scope Document is required for every study in which CTS is involved. This document must be finalized prior to First Patient In (FPI) date.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | CTS Team | Completes a Clinical Supply Plan and Project Scope Document Reference CRO_TP_CTS0014 Clinical Supply Plan and Project Scope Document | After kickoff meeting |
| 6.1.2 | CTS Team | Confirms Insurance - check with sponsor if they have insurance or require additional | Kickoff meeting, or immediately following |
| 6.1.3 | CTS Team | Saves a signed copy of the Clinical Supply Plan and Project Scope Document in the study folder | Prior to FPI |
| 6.1.4 | CTS Team | Where tasks are to be performed according to Sponsor SOPs this should be documented in the Clinical Supply Plan and Project Scope Document along with relevent SOPs references. | Upon identification of requirement |
| 6.1.5 | CTS Team | Where tasks to be performed are not covered by IQVIA CTS SOPs or Sponsor SOPs these should be documented in a Project Instruction (PI) Reference CS_WI_PL0022 Applying SOPs and Project Instructions to the Project. | Upon identification of requirement |
| 6.1.6 | CTS Team | Updates the Clinical Supply Plan and Project Scope Document, as necessary, saving a new version in the study folder each time, and logging changes made from the previous version in the document table. | During study execution |

# RACI

A RACI is required for every study in which CTS is involved. This document should be initiated immediately following the kickoff meeting.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | CTS Team | Completes a RACI document. Specific stakeholders and details for each action may be edited as dictated by study requirements. | Immediately following the kickoff meeting |
| 6.2.2 | CTS Team | Reviews responsibilities with sponsor and all other relevant stakeholders | During an early stakeholder meeting |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.3 | CTS Team | Obtains signatures from all stakeholders on final RACI document | Immediately following review and agreement |
| 6.2.4 | CTS Team | Saves a signed copy of the RACI in the study folder, and uploads to eTMF | Upon obtaining signatures |

  - eTraining

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | CTS Team | Navigates to eTraining from the IQVIA home page Reference CS_WI_PL0024 Project Specific Training and Team Member Transition | Study start up |
| 6.3.2 | CTS Team | Adds the appropriate sponsor(s) and studies which have been assigned | Study start up |
| 6.3.3 | CTS Team | Ensures that training is updated to include (but not limited to) all items listed in the Project Scope Document: - Communication plan - Vendor Management plan - User Requirement Specification - Risk Log - Q&A Log - Pharmacy Manual - Investigator Brochure - Study Protocol Liaise with the assigned Project Management Analyst (PMA) or Project Leader (PL) to update training content as required. | Study start up |
| 6.3.4 | CTS Team | Completes all required study/sponsor specific training. Ensures general GMP training has been completed within 12 months and is reported in the Self-Reported Training section of Learning Edge. | Study start up |

  - Forecast

A Clinical Supplies forecast is required for every study in which CTS is involved.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | CTS Team | Conducts an initial forecast of all clinical trial supplies required for the study. | Study start up |
| 6.4.2 | CTS Team | Liaise with your packaging vendor and sponsor to understand if reference samples and retention samples will need to be held by the depot and not made available for patient supplies. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: Where the packaging vendor is responsible for the collection and storage of reference samples, ensure a quantity is known at the earliest opportunity to ensure this is included in supply provisions. |  |
| 6.4.3 | CTS Team | Maintain and update forecast (as required) as enrollment data and IRT reports are made available. | Study execution |
| 6.4.4 | CTS Team | Stores the study forecast in the study forecast folder. | Study execution |

  - eTMF (Wingspan)

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | CTS Team | Liaises with Project Lead to ensure that master list contains, at a minimum (where applicable): - Temperature excursion reports - Packaging Batch Records - IRT releases - User Requirements Specification - MRS (Material Requirement Specification, or equivalent from IRT vendors outside of Cenduit - User Acceptance Testing - Packaging Request Form - Certificate of Analysis, Certificate of Compliance - QP release certificates - Vendor Management Plan - Kit list (in unblinded section) - Manual drug order forms and proof of receipt - Site to site transfer documentation | Study start up |
| 6.5.2 | CTS Team | Uploads applicable documents into Wingspan (or designated eTMF system), ensuring that unblinding documents are stored in the appropriate section. | Within 30 days of receipt/creation |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CRO_TP_CTS0014 | Clinical Supply Plan and Project Scope Document |
| 7.2 CS_WI_PL0024 | Project Specific Training and Team Member Transition |
| 7.3 CS_WI_PL0022 | Applying SOPs and Project Instructions to the Project |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CRO_OP_CTS0016 | Clinical Trial Supplies Project Setup | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Inclusion of guidance around Sponsor SOPs and IQVIA Work Instructions | 6.1.4 & 6.1.5 | Not previously included |
| Who column updated to replace CTS personnel with CTS Team | 6.1, 6.2, 6.3, 6.4, 6.5 | To clarify who takes responsibility for tasks |
| Updated definitions | 4.0 | Not all definitions were previously included |
| Added section about confirming Sponsor insurance | 6.1.2 | Not previously included |
| Additional forecasting step in respect to the packaging vendor | 6.4.2 | Not previously included |

- APPENDICES

Not Applicable

Page 6 of 6

Copyright © 2021, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Lewis, Ed (q818018) Title:

Date: Friday, 04 March 2022, 07:11 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Prior, Lewis (lprior) Title:

Date: Friday, 04 March 2022, 01:31 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================