|  | IQVIATM Operating Procedure DCT Operating Manual |
| --- | --- |
|  | Document Number and Revision: CS_OP_DCT0016 Revision 1 |
| Document Owner: Patricia Salter | Author(s): Jose Carbajales, Mariana Carregal |

# PURPOSE

To describe the end-to-end process for the Decentralized Clinical Trials (DCT) hybrid operating model and provide project teams with the information and guidance needed to consistently deliver quality and ensure ongoing participant safety and data integrity. This DCT Operating Manual (DCTOM) is meant to supplement the project specific DCT plans and existing DCT Standard Operating Procedures (SOPs).

# SCOPE

This document is applicable to DCT hybrid projects which utilize Study Hub and have been selected to work in the DCT operating model as captured in the Integrated Project Management Plan (IPMP).

Note: For DCTs where there is no Project Leader (PL)/Clinical Lead (CL), steps that involve/consult the role of the PL/CL may be fulfilled by the DCT Lead (DCTL), depending on the project scope.

Note: For studies with sites in China, the China Project Instruction (CS_PI_ China IQVIA Decentralized Clinical Trials) will be followed to meet the regulatory and local requirements.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this SOP:

Note: Please refer to the comprehensive DCT Division of Responsibilities.

| Role | Sections |
| --- | --- |
| DCT Solution Specialist (DCT SS) | 6.1 |
| DCT Implementation Manager (DCT IM) | 6.1 |
| DCTL | 6.1, 6.2, 6.3, 6.4 |
| DCT Study Coordinator (DCT SC) | 6.2, 6.3 |
| DCT Study Assistant (DCT SA) | 6.2, 6.3 |
| DCT Regulatory Specialist (DCT RS) | 6.1, 6.2 |
| CL | 6.1 |

Page 1 of 25

Copyright © 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

| Role | Sections |
| --- | --- |
| DCT Site Operations Resource Manager (DCT SO RM) | 6.1 |
| Monitor | 6.2, 6.3, 6.4 |
| Access Request Management Group (ARMG) Representative (Rep) | 6.2, 6.3 |
| Site Activation Manager (SAM) | 6.2 |
| DCT Information Technology Implementation Manager (DCT IT IM) | 6.2 |
| Study Hub IT Product Team Rep | 6.4 |

# DEFINITIONS

DCT: Any trial that leverages technology and specialized services to engage participants in the community and facilitate patient-centric care, including remote pre-screening, telemedicine visits, at-home treatment, or mobile Research Nurses (RNs) and staff. This approach aims to bring the patient voice into the trial, reduce the burden on sites and patients, and increase representative participation by expanding traditional site boundaries to deliver a more personalized trial experience.

DCT Hybrid Project: A project that combines remote, home-based participant visits along with traditional participant site visits to reduce participant burden and streamline operational execution. These projects will have DCT resources working as part of the full-service project delivery team.

DCT SS: Works with Sales and project teams to define DCT technology, data and Site Operations strategy.

DCT IM: Leads Study Hub set up, configuration and implementation. Oversees integration set up for Study Hub.

DCTL: Oversees DCT tech implementation and ongoing DCT tech activities, in addition to oversight of the DCT Site Operations team and related deliverables. The DCTL is considered an Operational Team Lead (OTL) on the project.

Decentralized Trial Analyst (DTA): Supports the DCTL in the management and execution of all aspects of the DCT.

DCT SA: Member of the DCT Site Operations team who supports sites and participants with the Study Hub set up, ongoing administrative support/questions and follow-up of certain project activities.

DCT SC: Member of the DCT Site Operations team who provides the Principal Investigator (PI)/site support with regulatory documents; participant support with e-consent, medical records management, scheduling visits, and conducts remote participant visits.

Study Hub: IQVIA’s DCT Technology Platform used to interact with participants and sites on a DCT project.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Set Up Procedures

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | DCT SS | Schedules a Strategy Handover Meeting and provides the DCT Solution Strategy to the DCTL, DCT IM, DCT IT IM and Customer Success team. | Within 2 weeks of project award |
| 6.1.2 | DCTL | Attends the Award Briefing Meeting, Customer Expectations Meeting, Internal Planning Meeting, Kick-off Meeting and provides the PL / Project Management Analyst (PMA) with required DCT input. Refer to: CS_WI_PL0023, Project Lifecycle Planning | Setup, prior to and during Meetings |
| 6.1.3 | DCTL | Reviews the initial Scope of Work (SoW) with regards to DCT deliverables and related budget. Requests clarifications and/or changes, if needed, and provides feedback to the PL. Refer to: CS_WI_PL0018, Project Scope and Customer Contract Management | Setup |
| 6.1.4 | DCTL | Provides the PL/PMA with DCT input to the Project Launch Form. Refer to: CS_WI_PL0052, Project System Management | Setup, upon confirmed /finalized Protocol |
| 6.1.5 | DCTL | Refines and finalizes the DCT Operations Strategy, including the DCT Site Operations team, DCT IM team and DCT-related Vendors/Third Party Vendors (TPVs). Refer to: CS_WI_PL0027, Project Vendor Management | Setup, before starting study- specific activities |
| 6.1.6 | DCTL | Presents the DCT Operations Strategy to the PL and Sponsor (if required) for approval. Note: Organizes a meeting for the presentation of the strategy, if applicable. | Setup, prior to Study Hub Configuration Plan sign-off |
| 6.1.7 | DCTL | Provides the PL and CL with DCT input to the clinically related Critical Data and Processes (CD/P) categories, as per the Risk | Setup, at least 5 days prior to RAMP call |

|  |  | Assessment Mitigation Plan (RAMP), and to document in the Risk Issue Log. Refer to: - CS_MAN_PL0076, IQVIA Risk-Based Monitoring Project Manual - CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management |  |
| --- | --- | --- | --- |
| 6.1.8 | DCT RS | Completes a regulatory evaluation of the study Protocol for the key DCT processes (including DCT Site Operations and Study Hub Configuration). | Setup |
| 6.1.9 | DCTL | Creates the DCT Operations Plan (DCTOP) to be delivered to the PL for inclusion in the IPMP. Refer to: - CS_TP_DCT0009, DCT Operations Plan Template - CS_WI_PL0023, Project Lifecycle Planning - CS_WI_PL0042, Integrated Project Review - CS_TP_PL0013, Integrated Project Management Plan | Setup, prior to Stage Gate Review (SGR) 3 |
| 6.1.10 | DCTL | - Creates the DCT Site Operations Playbook (if applicable due to complexity of the study) to define the DCT Site Operations strategy and establish key workflows for the DCT SCs and DCT SAs. - Develops Project Instructions (if applicable). - Communicates these workflows to the DCT Site Operations team members. Notes: - The Playbook, if created, is referred to in the DCTOP. - Processes need to be defined, documented and training provided to the DCT Site Operations team prior to implementing them. Refer to: - CS_WI_PL0022, Applying SOPs and Project Instructions to the Project - CS_TP_DCT0009, DCT Operations Plan Template | Setup, before starting study- specific activities |
| 6.1.11 | DCTL | - Develops the DCT site engagement strategy to enable site participation in the project, including the “opt-in” strategy for both the sites and the participants agreed with the CL, and documents it in the DCTOP. - Develops the strategy and relevant materials for training site staff and participants (if applicable) and documents them in the DCTOP. - Works with the Site Training Solutions Lead (STSL) (when the Site Training Solutions team is contracted) to provide site training support. | Setup, before starting study- specific activities |

|  |  | Refer to: - CS_WI_PL0023, Project Lifecycle Planning - CS_WI_PL0024, Project Specific Training and Team Member Transition - CS_TP_DCT0009, DCT Operations Plan Template |  |
| --- | --- | --- | --- |
| 6.1.12 | DCTL | - Reaches out to the DCT Privacy Specialist (DCT PS) to develop a country data protection strategy and begins the Data Protection Impact Assessment (DPIA) drafting process. - Works with the Sponsor to document the process for referring data subjects rights requests to the Sponsor, study close out and data retention process, data correction rules and documents these agreements in the DPIA. Refer to: CS_WI_DCT0003, DCT Data Protection Impact Assessment Process | Setup, and throughout the Start-up |
| 6.1.13 | DCTL | Works with the PL to ensure the DCT budget is correctly loaded in PeopleSoft and baseline Estimate at Completion (EAC) forecasting is put in place. Refer to: - EAC Training and Reference Materials - CS_WI_PL0069, Project Finance Using Estimate at Completion | Setup, prior to Start-up (ahead of First Patient In (FPI)) |
| 6.1.14 | DCTL | - Provides DCT input to the PL and PMA for QRPM (PPM and RM) set-up. - Works with the DCT IM to obtain Study Hub configuration timelines. Provides the PMA with timelines for entry into QRPM: PPM. Refer to: - CS_WI_PL0060, Project Resource Management - CS_WI_PL0052, Project System Management | Setup, prior to Start-up (ahead of FPI) |
| 6.1.15 | DCTL | - Discusses the Informed Consent Form (ICF) strategy with the Clinical Trial Regulatory Manager (CTRM) and DCT RS for inclusion of DCT elements in the core Quality Control (QC) and cover letter of regulatory core pack to be provided to countries. - Completes the DCT Regulatory Submission Packet QC Checklist and keeps it in the Internal Business Records. Note: Where IQVIA is scoped to write the project’s global master ICFs, the PL or ICF Lead (ICFL) (if already assigned) ensures the VIA ticket to the Global Patient and Site Solutions (GPSS) ICF writing team includes the applicable DCT elements. Refer to: | Prior to regulatory core pack finalization |

|  |  | CS_WI_RSU0033, Creation and Review of the Informed Consent Form |  |
| --- | --- | --- | --- |
| 6.1.16 | DCTL | - Confirms the systems (internal, vendor, and/or Sponsor systems) related to DCT services to be used on the project with the core project team (e.g., PL, PMA, Project Vendor Manager (PVM), CL, other OTLs (if applicable), DCT IM, DCT SS, etc.) and ensures vendors are added to the DPIA and data flow. - Works with the PVM/PL to obtain written Sponsor agreement to use each of the vendors. - Works with the DCT PS to review data flows and vendor handling if the vendor is to handle personal data of study participants. - Provides input on DCT vendors to the PVM and SAM (for the Site Ready to Enroll (SRtE) planning). Refer to: - CS_WI_DCT0003, DCT Data Protection Impact Assessment Process - CS_WI_PL0027, Project Vendor Management - CS_TP_PL0013, Integrated Project Management Plan - CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight | Setup, prior to Start-up (ahead of FPI) |
| 6.1.17 | DCTL | Provides the PMA with DCT input on the setup of applicable placeholders in the Trial Master File (TMF). Refer to: - CS_OP_TMF0007, Trial Master File (TMF) - CS_TP_TMF0054, IQVIA eTMF Trial Master File (TMF) Quality Plan | Setup |
| 6.1.18 | DCTL | - Works with the CL and SAM to include the relevant DCT elements to the Clinical Operations Plan (COP) and Site Activation Management Plan (SAMP), and ensures adequate training is available for the clinical team. - Understands and monitors the project milestones relevant for DCT deliverables and communicates them to the key stakeholders in a timely manner. Refer to: - Appendices 1 and 2 in this document for added content related to site and participant communication workflows - CS_WI_PL0023, Project Lifecycle Planning - CS_TP_SM0021, Clinical Operations Plan Template - CS_TP_RSU0013, Site Activation Management Plan | Setup, prior to Start-up (ahead of FPI) |
| 6.1.19 | DCTL | Endpoint (Primary/Secondary) Review Process: - Provides the PL and CL with DCT input to the Primary Risk Management Discussion | Setup Before or during the |

|  |  | - Confirms there is a robust DCT-related data and primary/secondary endpoint/ Essential Subject Safety (ESS) strategy discussion. - Confirms that DCT identified risks are provided to the PL and PMA for recording in the applicable risk log, as well as input to define Quality Tolerance Limits (QTLs) for the CD/P risks on the project. Note: By exception, some studies may need a separate Project Level Data Surveillance Plan depending on the complexity of the data reviewed and compliance of participants, as determined by the DCTL in consultation with the PL and CL. Refer to: - CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management - CS_TP_PL0062, Standards/Minimum Requirements for Electronic Clinical Outcomes Assessment (eCOA) Collection in Projects - CS_WI_CMSV0011, Centralized Support of Clinical Projects - Project Level Data Surveillance Plan Template | Internal Planning Meeting Within 2 weeks following the Internal Planning Meeting, prior to SGR 3 Starting at the risk planning stage and continuing throughout Start-up and Conduct |
| --- | --- | --- | --- |
| 6.1.20 | CL | Documents the DCT-related primary/secondary endpoints for the project to include the frequency of data and compliance review in the COP and/or RAMP. Refer to: CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management | Setup |
| 6.1.21 | DCTL | - Identifies recruitment strategies related to DCT elements/activities and DCT team scope to support those activities with the PL, CL, and other OTLs (e.g., Patient Recruitment Lead (PRL), SAM). - Documents these activities in the DCTOP or project- specific instructions (if applicable). | Setup |
| 6.1.22 | DCTL | - Informs the IQVIA Contact Center and DCT Site Operations teams of the project specifics; including countries, languages, site and participant counts, consistently with the | Setup |

|  |  | DCTOP and the DCT Site Operations Playbook, to guide staffing and resourcing decisions. - Provides necessary project-specific training to the IQVIA Contact Center team. Refer to: CS_WI_CC0258, IQVIA Contact Centre Virtual Trials Processes |  |
| --- | --- | --- | --- |
| 6.1.23 | DCTL | Requests DCT Site Operations resources for the study (via QRPM: RM and/or using the Resource Request Form) to the DCT SO RM indicating the tasks/activities to be covered for the study. Note: DCT Site Operations Resource Request Form must be sent to the corresponding mailbox (if applicable). | Setup, prior to Start-up (ahead of FPI) |
| 6.1.24 | DCT SO RM | Provides DCT Site Operations resources as requested by the DCTL. | Setup, prior to Start-up (ahead of FPI) |
| 6.1.25 | DCTL | Works with the DCT IM and DCT Privacy team to ensure Study Hub data flows are updated based on Sponsor-specific data correction, retention, and deletion rules. Refer to: CS_WI_DCT0008, Study Hub Project Closure and Decommissioning | Setup |
| 6.1.26 | DCT IM | - Plans and builds the Study Hub Configuration Plan and Study Hub Configuration Checklist. - Reviews personal data to be collected from participants in each country and confirms that only the minimal data needed to be collected to support the study is reflected in fields for study collection, visible to the site or participant, as appropriate for each study. Contacts the DCT PS for support. - Works with Study Hub Super Users (SHSUs) in the configuration of Study Hub. - Assists in completing testing, launches Study Hub and checks it against the agreed project contract. - Implements Study Hub integration with other DCT technologies with input from the DCT IT IM. Refer to: - CS_WI_DCT0001, Study Hub Configuration and Testing - CS_WI_CSM0036, Centralized UAT Process - CS_WI_PL0052, Project System Management - RWI_WI_IT0064, Study Geography and Language Implementation Process for Integrated Systems with Study Hub | Setup |

| 6.1.27 | DCTL | Sends the PL the Study Hub Go-Live Notification. | Prior to FPI and SGR 3 |
| --- | --- | --- | --- |

  - Start-Up Procedures

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | DCTL | Provides the SAM with DCT input on the Site Identification (ID) strategy, procedures, and the technical parameters associated with the project which may impact the site selection process. Refer to: - CS_WI_RSU0065, Site Identification and Selection - CS_TP_RSU0063, Site Selection Questionnaire | Site ID |
| 6.2.2 | SAM | - Updates the SAMP and informs the DCTL and PL where there are changes in country strategy from what was in the original SoW, to ensure languages not supported in Study Hub which require set-up and other regulatory considerations are addressed. - Communicates to the CTRM any scope impacting ICF language. Refer to: - CS_OP_RSU0060, Site Activation - CS_WI_RSU0065, Site Identification and Selection | Site ID |
| 6.2.3 | DCTL | - Provides the SAM and Site ID team with the DCT briefing notes to be included with the Site Selection Questionnaire (SSQ) to explain the DCT project strategy. - Contacts the CL to ensure that DCT elements will be considered during the Site Selection Visits (SSVs) conducted by the Monitor. - Provides input to the CL on the COP and Site Visit Report Annotations. Refer to: - CS_TP_RSU0063, Site Selection Questionnaire - CS_FM_SM0031, Site Selection Visit Checklist | Prior to Site Selection |
| 6.2.4 | DCTL | Works with the PL/SAM to determine if DCT updates are needed in selecting sites and updates the SSQ. Examples include: - Adds question about internet connection bandwidth or firewall restrictions - Adds questions about desktop stand-alone web camera or built into computer for tele-visits Note: Computers with audio/visual capabilities are required to conduct tele-visits through Study Hub - Adds any equipment testing needed - Adds any site training requirements | Prior to Site Selection |

|  |  | - Any site-specific data privacy matters - Any impact on recruitment of the Protocol targeted participant population considering DCT related activities Refer to: - CS_WI_RSU0065, Site Identification and Selection - CS_TP_RSU0063, Site Selection Questionnaire |  |
| --- | --- | --- | --- |
| 6.2.5 | Monitor | Conducts SSVs with consideration of the DCT elements for the study as per the COP. Refer to: - CS_WI_SM0005, Monitoring Visits - CS_FM_SM0031, Site Selection Visit Checklist | During SSV |
| 6.2.6 | DCTL | - Confirms with the Contract Budget and Solutions Lead (CBSL) if the DCT technology and assignment of a DCT SC/SA at the site will impact the site’s budget and contract. - Works with the SAM and PL to ensure DCT is considered and incorporated in the site contract and budgeting process, and coordinates changes if needed. - Consults with the DCT Regulatory team. Refer to: CS_OP_RSU0060, Site Activation | Start-up, prior to Site Activation |
| 6.2.7 | DCT IT IM | In collaboration with DCT IM, completes the study specific DCT Study Hub IT Support Handbook (using the corresponding template) documenting the scope and type of standard IT support activities agreed for the study. Refer to: - DCT Study Hub Standard IT Support Services Handbook - DCT Study Hub XX Study IT Support Handbook Template | Start-up, prior to Site Activation |
| 6.2.8 | DCTL | Submits Study Hub related materials for translation to languages included in the project. | Start-up, prior to Site Activation |
| 6.2.9 | DCT RS | Provides the SAM with guidance and documents related to the DCT requirements needed for the Ethics Committee (EC) / Regulatory Authority (RA) applications. Refer to: CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications | Start-up, prior to Site Activation |
| 6.2.10 | DCTL | - Works with the CTRM, SAM and DCT RS to define and agree on what should be included in the Core and Country Specific regulatory packages in relation to DCT requirements. - Consults with the DCT RS to ensure accuracy in what is provided. - Provides the SAM with the necessary Study Hub screenshots, DCT participant materials and other | Start-up, prior to Site Activation |

|  |  | applicable DCT content (as agreed in the initial scope and in line with the Core Pack) for inclusion in the EC/RA submissions, to meet agreed submission timelines. Refer to: CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications |  |
| --- | --- | --- | --- |
| 6.2.11 | DCTL | - Provides the internal project team with DCT training materials, including those to train the sites on Study Hub. - Provides the internal project team (including DCT Site Operations staff) with initial trainings. Ensures that documentation of the training completion is filed in the eTMF. - Provides the PL, CL and/or STSL with DCT training input to, including the DCT materials for the Investigator Meeting. - Works with the STSL (when the Site Training Solutions team is contracted) to provide site training support. Refer to: - CS_WI_PL0024, Project Specific Training and Team Member Transition - CRO_WI_VT0013, Virtual Trials Training Procedures | Start-up, prior to Site Activation |
| 6.2.12 | DCTL or designee | - Grants the internal project team with access to the DCT Training Platform. - If applicable, provides DCT Training Platform access to site staff and performs corresponding follow-up. Refer to: CRO_WI_VT0013, Virtual Trials Training Procedures | Prior to Site Activation |
| 6.2.13 | ARMG Rep or DCTL | - Requests study-level access to Study Hub for DCT Site Operations staff, RNs, and site staff through a VIA ticket. - When ARMG is not involved in the study, the DCTL is responsible for requesting Study Hub access by raising the VIA ticket. - Both the ARMG Rep and the DCTL must ensure mandatory training is completed before requesting access, as per the DCTOP. Refer to: - CS_WI_ DCT0005, Study Hub User Account Management - CS_WI_PL0052, Project System Management - CS_WI_CMSV0018 Access Management using the Access Request Management Group | Prior to Site Activation |

| 6.2.14 | DCTL | Works with the SAM to determine the DCT site onboarding strategy and requirements (including Study Hub training and access) and processes are included during site activation, to enable the sites to be ready with technology for participant recruitment. Note: DCT technology training is included as part of the site activation processes. Refer to: - CS_OP_RSU0060, Site Activation - CS_WI_RSU0021, Essential Documents Pack | Prior to Site Activation |
| --- | --- | --- | --- |
| 6.2.15 | SAM | Ensures the DCT requirements are added to the SRtE tracker. Refer to: - CS_OP_RSU0060, Site Activation - CS_WI_RSU0021, Essential Documents Pack - CS_WI_RSU0068, Site Ready to Enroll execution and oversight | Prior to Site Activation |
| 6.2.16 | DCTL | Conducts the Patient Zero exercise with the project’s DCT Site Operations team and assures that documentation of this exercise is kept in the Internal Business Records. | Prior to Site Activation |
| 6.2.17 | Monitor and/or DCT SA | Provides general DCT training to the site staff in accordance with project-specific processes and as described in the DCTOP and COP. Refer to: - CS_FM_SM0032, Site Initiation Visit Checklist - CS_WI_SM0005, Monitoring Visits - CRO_WI_VT0023, Study Hub Site Onboarding | Prior to Site Activation |
| 6.2.18 | DCT SA (or DCT SC) | Provides Study Hub Orientation training to the site staff in accordance with project-specific processes and as described in the DCTOP. Refer to: CRO_WI_VT0023, Study Hub Site Onboarding | As defined by DCTOP (could be before, during or after SIV, or when agreed for the study) |
| 6.2.19 | DCTL | Works with the project’s key stakeholders to identify any lessons learned from project Start-up stage and provides to the PL and PMA’. Refer to: CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management | Upon site activation |

  - Conduct Procedures

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | Monitor | Performs site monitoring according to the project-specific COP, which includes the relevant DCT elements. Refer to: - CS_WI_SM0005, Monitoring Visits - CS_FM_SM0033, Site Monitoring Visit Checklist | Conduct |
| 6.3.2 | DCTL | Provides the CL with ongoing input on DCT-related impacts to recruitment and the overall study conduct. Refer to: - CS_WI_SM0023, Subject Recruitment and Retention - CRO_WI_VT0025, Virtual Trials Patient Recruitment and Consent | Conduct |
| 6.3.3 | DCTL | - Provides oversight of the DCT Site Operations Team to ensure their activities are managed in accordance with the DCTOP and DCT Site Operations Playbook. - Oversees team scheduling of activities to support the delivery of the DCT Site Operations activities. - Provides the DCT Site Operations team with ongoing training relevant for their scope for the project. - Ensures that documentation of the training is filed in the eTMF. - Provides the DCT Site Operations team with guidance documents and scripts for relevant communications with sites and/or participants and uploads them in the relevant project location (e.g., SharePoint). - Organizes regular internal project meetings (touch-base meetings) with the DCT Site Operations staff assigned to the project for ongoing support. - Serves as escalation point for project-related questions and issues from the DCT Site Operations team. Refer to: - CS_WI_PL0024 Project Specific Training and Team Member Transition - CS_WI_PL0029 Project Management, Communications and Reporting | Conduct |
| 6.3.4 | DCT SC/ DCT SA | Manages the DCT related documents of the Investigator Site File (ISF) (if in scope and in accordance with the DCTOP and DCT Site Operations Playbook). Refer to: - CS_WI_SM0007, Investigator’s Site File - CRO_WI_VT0028, Virtual Trial Investigator Site File Management | Conduct |

| 6.3.5 | DCTL or designee | Manages the TMF records for DCT documents. Refer to: - CS_OP_TMF0007, Trial Master File (TMF) - CS_TP_TMF0054, IQVIA eTMF Trial Master File (TMF) Quality Plan | Conduct |
| --- | --- | --- | --- |
| 6.3.6 | DCT SC, DCT SA | Performs DCT Data Surveillance and other project-specific tasks as defined in the DCTOP and/or Project Level Data Surveillance Plan Template (e.g., safety events data collection and reporting to the sites/PI). Refer to: Project Level Data Surveillance Plan Template | Conduct |
| 6.3.7 | DCTL | Provides the PVM with guidance and support for DCT vendor related questions. Refer to: CS_WI_PL0027, Project Vendor Management | Conduct |
| 6.3.8 | DCTL | - Provides key internal stakeholders with DCT status reports and updates them relevant to DCT Operations deliverables, as agreed by the PL and Sponsor, and for inclusion in the Project Monthly Reports (PMRs). - Participates in regular project team meetings as the DCT OTL, as invited. Note: Status reports and frequency should be determined during Start-up. Refer to: - CS_WI_PL0029, Project Management, Communications, and Reporting - CS_WI_PL0042, Integrated Project Review | Conduct |
| 6.3.9 | DCTL or designee | Provides the PL and PMA with DCT input on ongoing EAC forecasting updates. Refer to: EAC Training and Reference Materials | Conduct |
| 6.3.10 | DCTL | Provides the PL and PMA with ongoing DCT financial management of contract and budget, to include Out of Scope (OOS) DCT activities and Change Orders (CO) in relation to the DCT budget. Refer to: CS_WI_PL0018, Project Scope and Customer Contract Management | Conduct |
| 6.3.11 | DCTL | Updates the DPIA on a regular basis with the assistance of the DCT PS. | Conduct |

|  |  | Refer to: CS_WI_DCT0003, DCT Data Protection Impact Assessment Process |  |
| --- | --- | --- | --- |
| 6.3.12 | DCTL | DCT impacts with Protocol Amendment: - Works w/the DCT RS to complete a regulatory evaluation of the impact of the Protocol Amendment in the key DCT processes (including Site Operations and Study Hub Configuration). - Implements the changes defined during the regulatory impact assessment. Refer to: CS_WI_SM0020, Management of Revised Clinical Study Documents | Conduct |
| 6.3.13 | DCTL | DCT impacts with Protocol Amendment: - Initiates an assessment of DCT technical impact to Study Hub. - Works with the DCT IM to implement any changes to the Study Hub configuration and its integration with other systems used in the project. Refer to: CS_WI_PL0052, Project System Management | Conduct |
| 6.3.14 | DCTL | DCT impacts with Protocol Amendment: - Evaluates if the Protocol Amendment also impacts DCT key processes e.g., DCT Site Operation activities, for the project. - Confirms if updates to site and internal team DCT training materials are needed. Works with the Site Training Solutions team and Study Hub training team (if applicable). Refer to: CS_WI_SM0020, Management of Revised Clinical Study Documents | Conduct |
| 6.3.15 | DCTL | DCT impacts with Protocol Amendment: - Ensures changes in Study Hub configuration and DCT Site Operation activities (if applicable) are included in the CO associated with the Protocol Amendment and on a country/site basis. - Works with the SAM/Maintenance Lead (ML) to update Clinical Trial Agreement (CTA) with any changes that impact site invoicing or payments. Refer to: CS_WI_SM0020, Management of Revised Clinical Study Documents | Conduct |
| 6.3.16 | DCTL | DCT impacts with Protocol Amendment: | Conduct |

|  |  | - Works with the PL, PMA, CL and ML to ensure any changes to the Protocol and ICF that significantly impact DCT technology are included in the revised Clinical Study Documents (rCSDs). - Assesses potential risks and liaises with the PL and PMA to ensure the project-specific risk log/risk mitigation plans are updated. - Attends RAMP related review meetings for RBM projects, supports with input on primary/secondary endpoints and EES, and provides input for DCT related CD/Ps. Note: In case DCT changes due to the Protocol Amendment are only to be implemented per site or per country, ensures this is highlighted to the DCT IM, CL, SAM/ML as applicable, to ensure proper implementation of the rCSDs and inspection readiness. Refer to: - CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management - CS_WI_SM0020, Management of Revised Clinical Study Documents |  |
| --- | --- | --- | --- |
| 6.3.17 | DCTL | - Provides ongoing DCT project level resource management for DCT roles (DCT IM, DCT SC, DCT SA). - Coordinates the completion of required activities and documentation for transition of DCT key team members (DCTL and DCT IM). - When there is a change in the DCT Site Operations team, communicates the ongoing changes the DCT SO RM, ensures the transition of information is properly performed, and organizes and documents the transition meeting. Refer to: - CS_WI_PL0024, Project-Specific Training and Team Member Transition - CS_FM_PL0037, Key Team Member Transition Form | Conduct |
| 6.3.18 | DCTL | - In collaboration with the DCT Site Operations Manager (DCT SOM), ensures that handover activities between the project’s DCT Site Operations team are completed and documented. - Organizes and documents the transition meeting to ensure that the transition of information is complete. Refer to: CS_WI_PL0024, Project-Specific Training and Team Member Transition | Conduct |
| 6.3.19 | DCTL | Provides DCT input to ongoing management of the project-level risks, as related to DCT conduct. | Conduct |

|  |  | Refer to: CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management |  |
| --- | --- | --- | --- |
| 6.3.20 | DCTL | Performs oversight of operational Study Hub performance metrics. Identifies enhancements needed, escalates to the Study Hub IT team and the PL. Note: RDS IT is responsible for ongoing Study Hub monitoring and system performance. Refer to: CS_WI_DCT0001, Study Hub Configuration and Testing. | Conduct |
| 6.3.21 | ARMG Rep or DCTL | Performs ongoing management of Study Hub system access with input from the DCTL, Centralized Monitor (CM), Centralized Monitoring Lead (CML), Centralized Monitoring Assistant (CMA) and Monitors. Refer to: - CS_WI_DCT0005, Study Hub User Account Management - CS_WI_PL0052, Project System Management - CS_WI_CMSV0018 Access Management using the Access Request Management Group | Conduct |
| 6.3.22 | DCT SC, DCT SA | - Performs ongoing Study Hub site training and support, as scoped and where needed. - Provides feedback to the DCTL regarding site challenges with Study Hub usage and site experience as part of issue escalation pathway or communication plan outlined in the DCTOP. Note: The Monitor oversees site project-specific training in accordance with the Site Management SOPs. Refer to: CRO_WI_VT0023, Study Hub Site Onboarding | Conduct |
| 6.3.23 | DCTL | - Manages issues related to the scoped DCT deliverables and the corresponding Corrective and Preventive Actions (CAPAs) until resolution. - Provides input to the PL and PMA on DCT related issues to record in the Risk Issue Log. - Determines the level of severity of the issue and implements the Quality Issue (QI) process (if it is considered a QI). - Supports CAPA management for audit/inspection findings related to DCT components. - Communicates to the DCT SOM if there is a performance issue with the DCT Site Operations staff, for appropriate action. |  |

|  |  | Refer to: - CS_OP_QA002, Quality Issue Management - CS_WI_QA0292, CAPA Management - CS_WI_DCT0006, DCT Audit and Inspection Readiness - CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management |  |
| --- | --- | --- | --- |

  - Close Out Procedures

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | DCTL | Works with the CL and CML to ensure any DCT specific activities related to site closure are added to the project-specific COP and associated clinical documents. Refer to: - CS_WI_PL0023, Project Lifecycle Planning - CS_TP_PL0013, Integrated Project Management Plan | Close |
| 6.4.2 | Monitor | Completes site close out process activities. Refer to: - CS_WI_SM0005, Monitoring Visits - CS_FM_SM0034, Site Close-out Visit Checklist | Close |
| 6.4.3 | DCTL | Provides input to the PL and PMA for DCT Lessons Learned activities. Refer to: - CS_WI_PL0025, Project Risks, Issues and Lessons Learned Management - CS_WI_PL0042, Integrated Project Review | Close During SGR 5 |
| 6.4.4 | DCTL | - In collaboration with the PL, completes DCT Financial Reconciliation. - Works with the PVM on the financial reconciliation of the DCT vendors. Refer to: CS_WI_PL0069, Project Finance Using Estimate at Completion | Close |
| 6.4.5 | DCTL | - Completes Study Hub System close out procedures with the support from DCT IM. - Verifies that all the Study Hub user accounts specific for the study have been disabled. Refer to: - CS_WI_DCT0005, Study Hub User Account Management - CS_WI_DCT0008, Study Hub Project Closure and Decommissioning | Close |
| 6.4.6 | DCTL | - Completes a VIA ticket for Study Hub data extraction to be sent to sites and Sponsor. | Close |

|  |  | - Ensures that the sites and Sponsor (if applicable) receive their part of the data and obtains confirmation of receipt. Refer to: CS_WI_DCT0008, Study Hub Project Closure and Decommissioning |  |
| --- | --- | --- | --- |
| 6.4.7 | Study Hub IT Product Team Rep | Completes the Study Hub archiving process and system closeout procedures with input from the DCTL and DCT IM. Refer to: - CS_WI_PL0052, Project System Management - CS_WI_DCT0002, Study Hub Audit Trail Review - CS_WI_DCT0008, Study Hub Project Closure and Decommissioning | Close |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| eSOP References |  |
| 7.1 CS_WI_DCT0001 | Study Hub Configuration and Testing |
| 7.2 CS_WI_DCT0002 | Study Hub Audit Trail Review |
| 7.3 CS_WI_DCT0003 | DCT Data Protection Impact Assessment Process |
| 7.4 CS_WI_DCT0005 | Study Hub User Account Management |
| 7.5 CS_WI_DCT0006 | DCT Audit and Inspection Readiness |
| 7.6 CS_WI_DCT0008 | Study Hub Project Closure and Decommissioning |
| 7.7 CS_TP_DCT0009 | DCT Operations Plan Template |
| 7.8 RWI_WI_IT0064 | Study Geography and Language Implementation Process for Integrated Systems with Study Hub |
| 7.9 CS_TP_PL0013 | Integrated Project Management Plan |
| 7.10 CS_TP_PL0062 | Standards/Minimum Requirements for Electronic Clinical Outcomes Assessment (eCOA) Collection in Projects |
| 7.11 CS_WI_PL0018 | Project Scope and Customer Contract Management |
| 7.12 CS_WI_PL0022 | Applying SOPs and Project Instructions to the Project |
| 7.13 CS_WI_PL0023 | Project Lifecycle Planning |
| 7.14 CS_WI_PL0024 | Project Specific Training and Team Member Transition |
| 7.15 CS_WI_PL0025 | Project Risks, Issues and Lessons Learned Management |
| 7.16 CS_WI_PL0027 | Project Vendor Management |
| 7.17 CS_WI_PL0029 | Project Management, Communications, and Reporting |
| 7.18 CS_WI_PL0042 | Integrated Project Review |
| 7.19 CS_WI_PL0052 | Project System Management |
| 7.20 CS_WI_PL0060 | Project Resource Management |
| 7.21 CS_WI_PL0069 | Project Finance Using Estimate at Completion |
| 7.22 CS_FM_PL0037 | Key Team Member Transition Form |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.23 CS_MAN_PL0076 | IQVIA Risk-Based Monitoring Project Manual |
| 7.24 CS_OP_TMF0007 | Trial Master File (TMF) |
| 7.25 CS_TP_TMF0054 | IQVIA eTMF Trial Master File (TMF) Quality Plan |
| 7.26 CS_WI_SM0005 | Monitoring Visits |
| 7.27 CS_WI_SM0007 | Investigator’s Site File |
| 7.28 CS_WI_SM0020 | Management of Revised Clinical Study Documents |
| 7.29 CS_WI_SM0023 | Subject Recruitment and Retention |
| 7.30 CS_TP_SM0021 | Clinical Operations Plan Template |
| 7.31 CS_FM_SM0031 | Site Selection Visit Checklist |
| 7.32 CS_FM_SM0032 | Site Initiation Visit Checklist |
| 7.33 CS_FM_SM0033 | Site Monitoring Visit Checklist |
| 7.34 CS_FM_SM0034 | Site Close-out Visit Checklist |
| 7.35 CS_WI_RSU0021 | Essential Documents Pack |
| 7.36 CS_WI_RSU0033 | Creation and Review of the Informed Consent Form |
| 7.37 CS_WI_RSU0065 | Site Identification and Selection |
| 7.38 CS_WI_RSU0067 | Project Lifecycle Clinical Trial Applications |
| 7.39 CS_WI_RSU0068 | Site Ready to Enroll Execution and Oversight |
| 7.40 CS_OP_RSU0060 | Site Activation |
| 7.41 CS_TP_RSU0013 | Site Activation Management Plan |
| 7.42 CS_TP_RSU0063 | Site Selection Questionnaire |
| 7.43 CS_OP_QA002 | Quality Issue Management |
| 7.44 CS_WI_QA0292 | CAPA Management |
| 7.45 CRO_WI_VT0013 | Virtual Trials Training Procedures |
| 7.46 CRO_WI_VT0023 | Study Hub Site Onboarding |
| 7.47 CRO_WI_VT0025 | Virtual Trials Patient Recruitment and Consent |
| 7.48 CRO_WI_VT0028 | Virtual Trial Investigator Site File Management |
| 7.49 CS_WI_CMSV0011 | Centralized Support of Clinical Projects |
| 7.50 CS_WI_CMSV0018 | Access Management using the Access Request Management Group |
| 7.51 CS_WI_CSM0036 | Centralized UAT Process |
| 7.52 CS_WI_CC0258 | IQVIA Contact Centre Virtual Trials Processes |
| External References |  |
| 7.53 | DCT Division of Responsibilities |
| 7.54 | DCT Site Operations Playbook Template |
| 7.55 | Project Level Data Surveillance Plan Template |
| 7.56 | DCT Study Hub Standard IT Support Services Handbook |
| 7.57 | DCT Study Hub XX Study IT Support Handbook Template |
| 7.58 | EAC Training and Reference Materials |
| 7.59 CS_PI_ China IQVIA Decentralized Clinical Trials | Decentralized Clinical Trial Process and Requirements in the People’s Republic of China) |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| Not Applicable | Not Applicable | Not Applicable |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| This is a New Document | Not Applicable | To describe the end-to-end process for the DCT hybrid operating model and replace the previous Project Instruction - CS_PI_DCT Transformation 2.0_001_V1 DCT Operating Manual |

- APPENDICES

Appendix 1: Example of Site Communication Workflow Appendix 2: Example of Participant Communication Workflow Appendix 3: Japan Specific Workflow

Appendix 1: Example of Site Communication Workflow (Project-specific communication pathways are defined in the DCTOP)

| Examples of different types of site communications related to DCT | Who develops | Who delivers | How Communicated |
| --- | --- | --- | --- |
| Initial and ongoing Study Hub training and support | DCTL | DCT SA or DCT SC | Virtual |
| Study Hub Release Update Notification | DCTL | Central Monitor | Email from central or personal mailbox |
| Study Hub Release Training (when applicable and evaluated with CL and DCTL) | - Study Hub Training team creates centralized training - DCTL (with Site Training Solutions team) customizes as needed | DCT SA or DCT SC | - Virtual - Leverage DrugDev or DCT Training Platform portal to post trainings |
| DCT Frequency Asked Questions (FAQ) document (to be started before FPI) | DCTL | Contact Center DCT Site Operations Team | Phone |
| Site has a Study Hub issue and can’t progress (Just In Time support) | Contact Center and DCT Site Operations team | Contact Center and DCT Site Operations team | Phone |
| Trending of site issues from Contact Center | DCTL | DCTL | CL and PL |
| DCT tech related issue escalation from site | DCT Site Operations team creates a help desk ticket | Contact Center | Phone |
| DCT related participant compliance trending/escalation to site | CM DCTL Site Operations team | CM (copy CL and Monitor) DCTL Site Operations team | Phone/email |
| Protocol deviations related to DCT SC (acting as site). | CL | Monitor | Communicate to DCT SC |
| Study Hub system issues/outages | DCTL | CL | Email, Study Hub Messages |
| eISF Management (when in scope) | DCTL | DCT SC/SA (keep PI and Monitor in the loop) | Phone/email |
| DCT documents related to ISF checklist | DCTL | CL | Applicable tracker (Excel) |

Appendix 2: Example of Participant Communication Workflow (Project-specific communication pathways are defined in the DCTOP)

| Examples participant communications related to DCT | Who develops | Who delivers | How communicated | Confirm Reg/EC approval with DCT Regulatory Lead (DCT RS)? |
| --- | --- | --- | --- | --- |
| Participant training of Study Hub and related DCT tech | DCTL | DCT SA or DCT SC | Phone/email | Yes |
| DCT Participant Compliance with Study Hub for participant reported events/data | CM DCT Site Operations team | Site, DCT SC or DCT SA | Phone/email | No |
| Communication with participant via Study Hub chat feature | DCT SA/DCT SC | DCT SA/DCT SC | Online chat | No |
| Study Hub chat scripts development | DCTL | DCT SA/DCT SC | Online chat | Yes |
| Participant communication plan with Contact Center | DCTL | Contact Center | Phone/email | No |
| Communication needed with participant to closing help deck tickets | DCT SA/DCT SC | Contact Center | Phone/email | No |
| Communication with participant regarding tele-visit scheduling | DCT SA/DCT SC | DCT SA/DCT SC | Phone/email | No |
| Support site and participant with ICF | DCT SC | DCT SC | Phone/email | No |
| Address questions from participant about visit schedule | DCT SA/DCT SC | DCT SA/DCT SC | Phone/email | No |
| Protocol related questions from participant | Site | Site | Phone/email | No |
| Address questions from participant regarding payments | Site | Site | Phone/email | No |

Appendix 3: Japan Specific Workflow

The Japan specific workflow should be followed for all DCT studies in Japan in addition to the global procedures outlined in this operating manual.

Set Up Procedures (Corresponding to 6.1 Setup in global process)

| Who: | Step: | When: |
| --- | --- | --- |
| DCTL | A Global DCTL will be assigned responsibility for both global and local DCT studies conducted in Japan. When Japan is included in a global project or a local project, contact Japan DCT Liaison to confirm role and responsibility* | Setup |
| DCT Liaison | Acts as a liaison between DCTL and Japan local Sponsor Affiliates and performs the following: - Resource for DCT requirements in Japan to Global DCT team - Communicates with Site Operation (VSC) in Japan - Supports communication between DCTL and local Sponsor Affiliates. - Contact for Japan system support team (Tech) for Study Hub update release, translation, functional and facilitating understanding with local sponsor affiliates as required | Setup/ Ongoing |

Start-up Procedures (Corresponding to 6.2 Site Activation in global process)

| Who: | Step: | When: |
| --- | --- | --- |
| DCTL | - Reviews Budget allocation for Japan considering the following J- GCP requirements: - Japan GCP 39-2 requires that Japan Investigator (site) should execute contract directly with Home Health Nurse (HHN) and/or DCT Site Operations that support Investigator/Site - Contract negotiation is needed between investigator/sites and IQVIA DCT Site Operations since each site has specific requirements for contract. - Payment to DCT Site Operations should only be made once the contract has been executed between DCT Site Operations and or HHN and the Investigator | Site Activation |
| DCT Liaison | Assists and guides DCTL regarding Japan budget | Site Activation |
| DCT SC/ DCT SA | Negotiates with investigator/sites about DCT Site Operations tasks and requirements and has contract with them before start working. | Site Activation |
| SAM/ Monitor | Confirms contract between investigator/site and DCT Site Operations is included in ERDP | Site Activation |

Project Conduct Procedures (Corresponding to 6.3 in global process)

| Who: | Step: | When: |
| --- | --- | --- |
| DCTL | - Ensures timing of invoice to Sponsor should correspond with contract between investigator (site) and DCT Site Operations contract. - When scope change is identified, consults with Japan DCTL Liaison and DCT Site Operations to check if an amendment to the contract between investigator (site) and DCT Site Operations is required** | Conduct |

Page 25 of 25

Copyright © 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

UserName: Vijay, Mili (q733303) Title:

Date: Thursday, 17 November 2022, 08:42 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Sanford, Kelly (q706820) Title:

Date: Thursday, 17 November 2022, 09:08 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Rider, Debra (q100547) Title:

Date: Thursday, 17 November 2022, 09:09 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Thursday, 17 November 2022, 09:58 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Corbin, Owen (q776286) Title:

Date: Sunday, 20 November 2022, 06:51 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Salter, Patricia (q731460) Title:

Date: Tuesday, 22 November 2022, 07:21 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Cress, Bradley (q716662) Title:

Date: Tuesday, 22 November 2022, 09:10 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Howley, Amanda (u1106467) Title:

Date: Tuesday, 22 November 2022, 02:00 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================