|  | IQVIATM Work Instruction Study Hub Configuration and Testing |
| --- | --- |
|  | Document Number and Revision: CS_WI_DCT0001 Revision 1 |
| Document Owner: Leora Sheffer | Author(s): Prashanth Kotriki |

# PURPOSE

To define the process and activities necessary to ensure accurate project-specific configuration of the Study Hub system, including internal testing and testing with the Sponsor for approval.

# SCOPE

This Work Instruction (WI) applies to IQVIATM Decentralized Clinical Trials (DCT) staff globally across all projects within the IQVIA DCT model.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| DCT Lead (DCTL) | 6.1, 6.3 |
| DCT Implementation Manager (DCT IM) | 6.1, 6.2, 6.3 |
| Study Hub Super User | 6.1, 6.3 |
| Test Lead | 6.2 |
| Study Hub Product Manager | 6.2 |

# DEFINITIONS

  - Configuration Error: An error that occurs because of an incorrect study setup/configuration.

  - Decentralized Clinical Trials (DCT): A project that uses Study Hub and interfaced systems.

  - Defect: When the system does not behave in accordance to the requirements/user stories.

  - Enhancement: When changes are needed to a system to meet a business need.

  - HP Application Lifecycle Management (HP ALM): System used to track defects found during System Validation Testing (SVT), User Acceptance Testing (UAT), Study Configuration Internal UAT and Study Configuration External UAT.

  - Hybrid DCT Project: A hybrid trial combines remote, home-based visits along with traditional site visits. These projects will have a DCT team working closely with the full-service project team.

  - In Flight Studies: Projects already started where DCT Solution is applied after first subject in.

  - JIRA: System used by the business analysts to track epics and stories for the Study Hub Development Team to action. Requirements gathered from these tasks are entered in Top Team and pushed to HP ALM.

  - Light Build Studies: Studies utilizing Study Hub that do not require custom descriptions, integrations or complex operational workflows. Light Build Studies rely on core functionality of Study Hub (I.e., ad hoc tele-visits, uploading of documents or CRA/Site tele-visits).

  - Script Library: A library of test scripts to be used for Study Configuration Internal UAT and Study Configuration External UAT activities located in ELVIS.

  - Study Configuration External UAT: Sponsor review and approval process of the study specific Study Hub configuration and associated integrations.

  - Study Configuration External UAT Report Template: Extract from HP Application Lifecycle Management (HP ALM) documenting evidence collected during Study Configuration Internal UAT and Study Configuration External UAT demonstrating pass or failure of each test script / test scenario.

  - Study Configuration Internal UAT: Internal review of the study-specific Study Hub configuration and associated integrations.

  - Study Hub: IQVIA’s DCT Technology Platform used to interact with the subject and sites on a DCT project.

  - Study Hub Admin: Tier 3 IT support, provide advanced support and delivery by dealing with issues, backend set up or tasks beyond study configurations in Study Hub.

  - Study Hub Configuration Tracker: Used to formally request set up and configuration of Study Hub. The Study Hub Configuration Tracker is an Excel document maintained by the DCT IMs in the Microsoft Team Channel designed for Study Hub set up and configuration requests.

  - Study Hub Configuration Checklist: Form to document study specific configuration requirements for projects utilizing Study Hub technology.

  - Study Hub Configuration Plan: A study specific specification document that describes the Study Hub study specific set up, configuration and testing plan.

  - Study Hub Super User: IT System Administrators managing project setup, maintenance & configuration in Study Hub, access management (provisioning, modifying, and removing) based on updated Study Hub Configuration Checklists and providing end-user support, as necessary.

  - System Validation Testing (SVT): The execution of the test cases against the requirements/user stories, in TopTeam, by the testing team (aka formal system testing).

  - Test Lead: Member of IQVIA team who plans, monitors and controls the Study Configuration Internal UAT activities and tasks.

  - Test Scripts / Test Scenarios: designed to test core features of Study Hub. Test scripts are stored in a validated test system (e.g. HP ALM) and are executed during Study Configuration Internal UAT and Study Configuration External UAT cycles.

  - Traceability Matrix: Tool within the Study Hub Configuration Checklist to document study specific configuration to the protocol; testing scenarios and testing documentation.

  - Trial Master File (TMF): the collection of essential documents which allows the conduct of a clinical trial to be reconstructed and evaluated”.

  - IQVIA Support Portal: System used to track change requests including requests to set up study configuration in Study Hub, requests to gain access to Study Hub, or issues users may experience while using Study Hub.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Configuration of Study Hub

Note: For In FlightStudies and Light Build Studies, configuration and Study Configuration Internal UAT may be accelerated and completed within 1-2 weeks. Otherwise, the following process is completed for full build studies and usually

takes 6-8 weeks, or more, depending on translations and integrations required to complete.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | DCTL | Confirms the study award to DCT IM via email, including the approved protocol | After project award |
| 6.1.2 | DCT IM | Confirms study timelines with the DCTL, Project Leader (PL) and Clinical Lead (CL) | After project award |
| 6.1.3 | DCT IM | Develops DCT Platform Implementation Schedule | After project award |
| 6.1.4 | DCT IM | During Internal Kick-Off Meeting, reviews DCT Platform Implementation Schedule with the internal project team (DCTL, DCT IT IM and PL) | After project award |
| 6.1.5 | DCT IM | Completes DCT Platform Implementation Schedule to define study-specific timelines for configuration, testing, and go-live of Study Hub, in line with study requirements. | After project kick off meeting. |
| 6.1.6 | DCT IM | Shares details of DCT Platform Implementation Schedule with stakeholders (DCTL, Test Lead, Study Hub Super User, PL, IT Support) | Upon completion of draft DCT Platform Implementation Schedule |
| 6.1.7 | DCT IM | Develops initial draft of Study Hub Configuration Plan | After internal implementation kick- off meeting |
| 6.1.8 | DCT IM | Schedules and conducts external Study Hub configuration kickoff meeting to review details of Study Hub Configuration Plan with Sponsor | Upon completion of Study Hub Configuration Plan |
| 6.1.9 | DCT IM | As required, revises Study Hub Configuration Plan, in collaboration with Sponsor | After external Study Hub configuration kick-off meeting |
| 6.1.10 | DCT IM | Provides final version of Study Hub Configuration Plan with Sponsor for signature | After revision of Study Hub Configuration Plan |
| 6.1.11 | DCT IM | Develops draft of Study Hub Configuration Checklist, using elements approved in Study Hub Configuration Plan | Upon Sponsor approval of Study Hub Configuration Plan |
| 6.1.12 | DCT IM | Submits completed Study Hub Configuration Checklist to the Study Hub Super User Team using an IQVIA Support Portal ticket. Note: For global trials, request at least one English site and one non-English site in Training environment, and one of the Site Coordinators (SCRs) to have ability to create subjects in all country/languages participating in study to obtain screenshots for IRB submissions. | 3 weeks prior to scheduled Configuration Acceptance Testing |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.13 | Study Hub Super User | Schedules and conducts checklist review meeting with DCT IM and DCTL to address any questions prior to configuration | Upon receipt of Study Hub Configuration Checklist from Study Hub IQVIA Support Portal ticket |
| 6.1.14 | DCTL | Meets with DCT IM to map out required data flows / data extracts required per project as per CS_WI_DM0424 Integrating Data Across Systems. This includes review and approval of the eDiary / questionnaire set up, configuration and scoring if required. | Prior to Study Configuration Internal UAT |
| 6.1.15 | Study Hub Super User | Configures Study Hub according to the study specific Study Hub Configuration Checklist provided | After checklist review meeting |
| 6.1.16 | Study Hub Super User | Configuration of Study Hub is reviewed by a second Study Hub Super User to ensure adherence to Study Hub Configuration Checklist. This review is documented in the configuration request IQVIA Support Portal ticket by the Study Hub Super User performing the task. Note: Quality check of Study Hub configuration encompasses all functionality required for the study, including but not limited to study geographies, study visits, eDiaries, and integration parameters and is documented in the IQVIA Support Portal ticket. The IQVIA Support Portal ticket number is recorded on the Study Hub Configuration Tracker. | After configuration is completed by Study Hub Super User, prior to notifying DCT IM and DCTL that configuration is complete |
| 6.1.17 | Study Hub Super User | Files Study Hub Configuration Checklist in ELVIS, accessible by Study Hub Super User Team, to update as needed throughout lifecycle of project | At completion of Study Hub configuration and QC process steps |
| 6.1.18 | Study Hub Super User | Confirms completion of Study Hub project-specific configuration with DCTL and DCT IM closing IQVIA Support Portal ticket | At completion of Study Hub configuration and QC process steps |
| 6.1.19 | DCT IM | Completes traceability matrix with DCTL after configuration is complete on Study Hub Configuration Checklist | Prior to Study Configuration Internal UAT |

# Study Configuration Internal UAT

Once project-specific configuration of Study Hub is complete and quality check by system administrators is complete, the Test Lead conducts Study Configuration Internal UAT of the system..

Note: Study Configuration Internal UATcan be waived by the Sponsor due to accelerated timelines if needed. Study Configuration External UAT will serve as

formal testing of configuration if Study Configuration Internal UAT is waived and must be signed off by Sponsor prior to go live. Written documentation of the waiver should be collected by the DCTL and filed in ELVIS and the project TMF.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | DCT IM | Emails Test Lead with study details to engage for Study Configuration Internal UAT | At submission of configuration documentation |
| 6.2.2 | DCT IM | Schedules meeting with Test Lead and DCTL to present project scope and requirements in advance of testing | At submission of configuration documentation |
| 6.2.3 | DCT IM | Completes internal validation exercise with Study Hub Super User to confirm successful end-to-end patient flow within study-specific configuration, prior to releasing study to the Test Lead. | At completion of study configuration in Train Environment |
| 6.2.4 | Test Lead | Follows processes outlined in CS_WI_CSM0036 Centralized UAT Process to complete UAT of Study Hub configuration | After meeting with DCT IM and DCTL |
| 6.2.5 | DCT IM | Reviews Validation Report, Issue Tracker Sheet & Objective Evidence Sheet, and Evidence of Traceability & Post Execution Summary report provided by Test Lead, as per CS_WI_CSM0036 | Following each Study Configuration Internal UAT session |
| 6.2.6 | DCT IM | Reviews findings log and confirms findings categorization; assigns HP ALM and JIRA entries for issue resolution | Following each Study Configuration Internal UAT session |
| 6.2.7 | DCT IM | Plans triage meeting with Study Hub Development Team and product management team to confirm timelines for defect and enhancement resolution | After all Study Configuration Internal UAT sessions are complete |
| 6.2.8 | Study Hub Product Manager | Communicates time estimates for product-level defect resolution; documents timelines in JIRA and coordinates with DCT IM for retests, if necessary | Following each Study Configuration Internal UAT session |
| 6.2.9 | DCT IM | Shares final report of testing process with all DCT study team members, DCT platform product management team, and relevant IT team members, including plans for resolution of all findings (if required). Note: For in-flight and light-build projects, the Study Configuration Internal UAT scripts and findings are made available to Sponsors for | After all Study Configuration Internal UAT sessions are complete |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | review and signature on Findings Report Template, accelerating approval for system go-live. The Findings report is filed in ELVIS and project TMF. |  |
| 6.2.10 | DCT IM | Updates Study Hub Configuration Plan and Traceability Matrix if needed | After all Study Configuration Internal UAT sessions are complete |
| 6.2.11 | DCT IM | Informs with DCTL Configuration Acceptance Testing is complete | Once Study Configuration Internal UAT final report is distributed |

# Study Configuration External UAT

The IQVIA team and study Sponsor complete Study Configuration External UAT to review Study Hub configuration and receive Sponsor approval prior to study initiation. Study Configuration External UAT can be waived by the Sponsor due to accelerated timelines, if needed. Study Configuration Internal UAT will serve as formal testing of configuration if Study Configuration External UAT is waived.

Written documentation of the waiver should be collected by the DCTL and filed in the project TMF.

Note: Study Configuration External UAT is not required for in-flight and light-build studies. For all other projects, the following process is followed unless waived by the Sponsor.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | DCT IM | In collaboration with DCTL, reviews scripts completed for Study Configuration Internal UAT and determine if any changes are required prior to finalization for Study Configuration External UAT. Agreed upon testing scenarios are documented in Study Configuration External UAT Kick Off Meeting (KOM) slides presented to client prior to Study Configuration External UAT testing. | Post-completion of Study Configuration Internal UAT |
| 6.3.2 | DCT IM | In collaboration with DCTL, finalizes Study Configuration External UAT dates | Post-completion of Study Configuration Internal UAT |
| 6.3.3 | DCTL | Provides DCT IM with contact information of Sponsor and study team members (PL or CL) to participate in Study Configuration External UAT | Post-completion of Study Configuration Internal UAT |
| 6.3.4 | DCT IM | Prepares draft scripts for Study Configuration External UAT using the Study Configuration External UAT Script Template and provides to DCTL | After review of scripts with DCTL |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.5 | DCTL | Reviews scripts for Study Configuration External UAT and provides feedback, if needed | After receipt of draft scripts for Study Configuration External UAT |
| 6.3.6 | DCTL | Approves Study Configuration External UAT testing scripts | After review of Study Configuration External UAT scripts |
| 6.3.7 | DCT IM | Shares the Study Configuration External UAT scripts, planned testing dates, relevant documentation (i.e. document templates for testing), and summarizes any changes made from Study Configuration Internal UAT with Study Hub Super User. | After DCTL approves Study Configuration External UAT scripts |
| 6.3.8 | DCT IM | Confirms Study Configuration External UAT dates with Sponsor, DCT study team members, DCTL, relevant IT team members, and, if applicable Bios Lead and Data Team Lead and shares calendar invite and proposed scripts | After confirmation of testing dates with DCTL and Study Hub Super User |
| 6.3.9 | DCT IM | Prepares slides for Study Configuration External UAT Kick-off Meeting, providing overview of Study Configuration External UAT process and expectations | At least one week prior to kick-off meeting |
| 6.3.10 | DCT IM | Schedules Study Configuration External UAT Kick-off Meeting with all applicable attendees to set Study Configuration External UAT expectations and outline testing plan | Within 3 business days of Study Configuration External UAT Session 1 |
| 6.3.11 | DCT IM | Loads finalized Study Configuration External UAT scripts into HP ALM in preparation for execution of test cases | One week prior to start of Study Configuration External UAT |
| 6.3.12 | DCT IM | Coordinates with Study Hub Admin, Study Hub Super User and Project Managers from associated integrated vendors / systems to verify testing environments are prepared for Study Configuration External UAT and to obtain tester role log-in credentials | One week prior to start of Study Configuration External UAT |
| 6.3.13 | DCT IM | If the study uses eCOA: - Ensures eCOA integration with the Study Hub environment used for Study Configuration External UAT is established accurately, based on input from the eCOA PM, i.e. Seek Study GUID, Site(s) GUIDs - Documents this in the Study Hub Configuration Checklist Makes sure it’s configured by the Study Hub Super User team) | One week prior to start of Study Configuration External UAT |
| 6.3.14 | DCT IM | If Study uses an IRT system for Randomization, and if integration of Study Hub with the chosen IRT system (e.g. Signant / Cenduit) is in scope for the study: - Ensures IRT integration with Study Hub environment used for Study Configuration External UAT is established | One week prior to start of Study Configuration External UAT |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | accurately, based on the input from the IRT System Subject Matter Expert and DCT IT IM 2. Documents integration parameters in the Study Hub Configuration Checklist Makes sure it’s configured by the Study Hub Admin and/or Study Hub Super User team) |  |
| 6.3.15 | DCT IM | Ensures sponsor attendees (i.e., participating testers) have the credentials to login to Study Hub in the role they are representing for testing. | No less than two days prior to start of Study Configuration External UAT |
| 6.3.16 | DCT IM | Sends Study Configuration External UAT Welcome Email to Sponsor attendees, study team, testers, Study Hub Development Team, and others involved in Study Configuration External UAT to confirm testing schedule, testing plan, and provide instructions for test log-in | No less than two days prior to start of Study Configuration External UAT |
| 6.3.17 | DCT IM | Manages Study Configuration External UAT sessions, coordinating system administrators and testers as scripts are evaluated | During Study Configuration External UAT |
| 6.3.18 | DCT IM | Submits IQVIA Support Portal ticket to communicate potential findings identified. Findings associated with a needed change to the system are identified as a Configuration Error, Defect/Bug, or Enhancement. - If Study Hub Super User assigned to the IQVIA Support Portal ticket determines the issue as a Defect/Bug by adding additional details to the work notes of the incident ticket, the DCT IM opens a Defect in ALM using the work notes added by the Study Hub Super User, assigns to Tier4 support and adds the Product Manager, Product Owner and DCT IT IM to the watchlist of the associated JIRA record. Note: A record is created in JIRA upon documentation of a finding in HP ALM. - If Study Hub Super User assigned to the IQVIA Support Portal ticket determines the issue as a gap to an existing Study Hub functionality by adding additional details to the work notes of the incident ticket, DCT IM will create a JIRA enhancement request as an EPIC, clearly documenting the needed functionality directly in JIRA and adds the Product Manager. Product Owner and DCT IT IM to the watchlist of the associated JIRA record. The DCT IM adds notes to the actual test result description about the functionality Gap and refers the JIRA # enhancement request. The DCT IM clearly communicates to the sponsor about the functionality gap in the Study Hub product and cannot | During Study Configuration External UAT |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | be assumed to get implemented before the study goes live. - If Study Hub Super User assigned to the IQVIA Support Portal ticket determines the issue as a configuration error by adding additional details to the work notes of the incident ticket, DCT IM updates the Study Hub Configuration Checklist as per the feedback received and gets the study configuration fixed prior to re-testing. Note: HP ALM will be used for management of findings (Defects/Bug) documented during testing. Enhancement Request(s) should be added to the backlog, prioritized by the Study Hub Product Management team and cannot be assumed to get implemented before the study goes live. |  |
| 6.3.19 | DCT IM | Takes screenshots of appropriate testing end results of tests to record successful passes and achieved requirements within HP ALM | During Study Configuration External UAT |
| 6.3.20 | DCT IM | Takes screenshots of findings identified during Study Configuration External UAT testing within HP ALM, to assist in defect resolution and enhancement planning | During Study Configuration External UAT |
| 6.3.21 | DCT IM | Records PASS/FAIL results for each test step of the testing script, and all findings discussed during testing, within HP ALM | During Study Configuration External UAT |
| 6.3.22 | DCT IM | Exports findings log and sends summary of testing activity to all involved in Study Configuration External UAT session | Following each Study Configuration External UAT session |
| 6.3.23 | DCT IM | Reviews findings log and confirms findings categorization; assigns HP ALM and JIRA entries to Study Hub development Tier 4 team for issue resolution | Following each Study Configuration External UAT session |
| 6.3.24 | Study Hub Super User | Communicates with Study Hub Product Manager, Study Hub Super User and Study Hub Development Team, estimates for defect resolution and coordinates with DCT IM for retests, if necessary. If retesting is needed after defect resolution, testing scenarios are redone and screen shots captured in HP ALM as evidence of pass / fail of defect resolution. | Following each Study Configuration External UAT session |
| 6.3.25 | DCT IM | Plans triage meeting with Study Hub Super User team, Study Hub Development Team and Study Hub Product Manager to confirm timelines for defect and enhancement resolution. All defects and enhancements are managed in HP ALM. | After all Study Configuration External UAT sessions are complete |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.26 | DCT IM | Shares Study Hub Study Configuration External UAT report of testing process with all applicable team members (DCTL, PL and Sponsor), including plans for resolution of all findings (if required) | After all Study Configuration External UAT sessions are complete |
| 6.3.27 | DCT IM | Confirms with DCTL no further testing is necessary prior to preparation of Study Hub Study Configuration External UAT report | After all Study Configuration External UAT sessions are complete |
| 6.3.28 | DCT IM | Prepares Study Hub Study Configuration External UAT report and shares with Sponsor and study team members with task for review and feedback | 1-2 business days after all Study Configuration External UAT sessions are complete |
| 6.3.29 | DCT IM | Updates Study Hub Configuration Plan and Traceability Matrix if needed | 1-2 business days after all Study Configuration Internal UAT sessions are complete |
| 6.3.30 | DCT IM | Shares Study Hub Study Configuration External UAT report with all Sponsor and study team members with task for review and approval, via DocuSign for signature | 1-2 business days after completion of final Study Configuration External UAT report |
| 6.3.31 | DCT IM | Files Study Hub Study Configuration External UAT report in the project-specific Study Configuration External UAT folder in ELVIS and shares signed final Study Configuration External UAT report with DCTL | Once final Study Configuration External UAT report is fully signed |
| 6.3.32 | DCTL | Files Study Hub Study Configuration External UAT report in TMF | Once final Study Configuration External UAT report is fully signed |
| 6.3.33 | DCTL | Submits completed Study Hub Configuration Checklist to the Study Hub Super User Team using an IQVIA Support Portal ticket | Once final Study Configuration External UAT report is fully signed |
| 6.3.34 | Study Hub Super User | Configures Study Hub production environment according to the study specific Study Hub Configuration Checklist | After review of Study Hub Configuration Checklist with DCTL |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.35 | Study Hub Super User | Files Study Hub Configuration Checklist in the project-specific Study Hub Configuration Checklist folder in ELVIS accessible by Study Hub Super User Team to update as needed throughout lifecycle of project | Prior to notifying DCTL configuration is complete |
| 6.3.36 | Study Hub Super User Team | Configuration of Study Hub production environment is reviewed by a second Study Hub Super User to ensure adherence to the Study Hub Configuration Checklist submitted, documented in the configuration request IQVIA Support Portal ticket. Note: Quality check of Study Hub configuration encompasses all functionality required for the study, including but not limited to study geographies, study visits, eDiaries, custom reports and integration parameters. | Prior to notifying DCTL configuration is complete |
| 6.3.37 | Study Hub Super User | Schedules meeting with DCTL, DCT IM, DCT IT IM, Study Hub Admin and Project Managers (If applicable) from associated integrated vendors / systems to provide guided walk-through of configuration in the production environment | Prior to notifying DCTL configuration is complete |
| 6.3.38 | Study Hub Super User | Documents Baseline Study Configuration Walkthrough Form applicable to the study during the meeting 6.3.38 and seeks approvals from meeting participants | Prior to notifying DCTL configuration is complete |
| 6.3.39 | Study Hub Super User | Confirms completion of Study Hub project-specific configuration with DCTL and DCT IM by closing IQVIA Support Portal ticket | At completion of Study Hub production environment configuration |
| 6.3.40 | DCTL | Communicates go-live of Study Hub configuration in production environment with Sponsor and critical study team members, including Project Managers from associated integrated vendors / systems | Upon confirmation that Study Hub production environment configuration is completed |
| 6.3.41 | DCTL | Files Baseline Study Configuration Walkthrough Form report in TMF | At completion of Study Hub production environment configuration |

7.0	SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_DM0424 | Integrating Data Across Systems |
| 7.2 CS_WI_CSM0036 | Centralized UAT Process |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| External References |  |
| 7.3 Study Hub Configuration Checklist | Study Hub Configuration Checklist |
| 7.4 Study Configuration External UAT Script Template | Study Configuration External UAT Script Template |
| 7.5 Study Hub Study Configuration External UAT Report Template | Study Configuration External UAT Report Template |
| 7.6 Study Hub Configuration Plan | Study Hub Configuration Plan |
| 7.7 DCT Platform Implementation Schedule | DCT Platform Implementation Schedule |
| 7.8 Baseline Study Configuration Walkthrough Form | Baseline Study Configuration Walkthrough Form |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CRO_WI_VT0022 | Study Hub Configuration and Testing | 2 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Role added: Data Strategy Lead / Data Team Lead | 3.0 | Action added in section 6.1 assigned to this user. |
| Action added: completion of Study Implementaiton Plan for Implementation Manager | 6.1.1 | Improvements to Study Hub configuration process |
| Action updated: internal implementation kickoff meeting | 6.1.2 | Improvements to Study Hub configuration process |
| Action updated: Study Hub Conifguration Plan now completed before configution checklist | 6.1.3 | Improvements to Study Hub configuration process |
| Action added: External Study Hub configuration kickoff meeting | 6.1.4 | Improvements to Study Hub configuration process |

| Ownership change: Study Hub Configuration Checklist now completed by Implementation Manager | 6.1.7 | Improvements to Study Hub configuration process |
| --- | --- | --- |
| Action added: data flow mapping | 6.1.10 | Improvements to Study Hub configuration process |
| New role introduced: Study Hub Admin | 6.3 | Improvements to Study Hub configuration process |
| Role added: Data Strategy Lead / Data Team Lead | 3.0 | Action added in section 6.1 assigned to this user. |

- APPENDICES

Not Applicable

Page 14 of 14

Copyright © 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Salter, Patricia (q731460) Title:

Date: Monday, 30 August 2021, 07:59 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================