|  | IQVIATM Work Instruction Study Hub Project Closure and Decommissioning |
| --- | --- |
|  | Document Number and Revision: CS_WI_DCT0008 Revision 2 |
| Document Owner: Asif Aman | Author(s): Bradley Cress |

# PURPOSE

The purpose of this document is to provide the recommended process for extracting data collected for any Decentralized Clinical Trial (DCT) utilizing IQVIA’s Study Hub platform during site or project close-out.

# SCOPE

  - This Work Instruction (WI) applies to any DCT capturing data in IQVIA’s Study Hub platform where there is a request to extract site or Sponsor level data due to site or project close out.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| DCT Lead (DCTL) | 6.1, 6.2, 6.3 |
| Study Hub IT Support | 6.2. 6.3 |
| QBOX IT Admin | 6.2, 6.3 |
| MuleSoft System Admin | 6.2, 6.3 |
| Study Hub Support Tier 3 Team | 6.2, 6.3 |
| Study Hub Super User (SHSU) | 6.3 |

# DEFINITIONS

DCT: Any trial that leverages technology and specialized services to engage participants in the community and facilitate patient-centric care, including remote pre-screening, telemedicine visits, at-home treatment, or mobile research nurses and staff. This approach aims to the bring patient voice into the trial, reduce the burden on sites and patients, and increase representative participation by expanding traditional site boundaries to deliver a more personalized trial experience.

DCT Lead: Oversight of DCT tech implementation and ongoing DCT tech activities, oversight of the DCT Site Ops team and related deliverables. The DCTL is considered an Operational Team Lead on the project.

Salesforce: Vendor providing cloud-based services on which the IQVIA’s DCT Technology Platform is built.

Study Hub: IQVIA’s DCT Technology Platform used to interact with participants and sites on a DCT project.

Page 1 of 9

Copyright © 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Study Hub SuperUser (SHSU): Study administrators managing Study Hub project setup, configuration, maintenance, closure access management based on an updated Study Hub Protocol Setup Checklist or ARMG ARF, as well as providing end-user support.

MuleSoft: Middleware software for system integrations and data deletion.

QBOX: A web-based solution to receive/send files from/to external Sponsors.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Project-Specific Documents

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | DCTL | Works with the Sponsor and Project Leader to review the Master Service Agreement (MSA) and Work Order and ensure the project- specific Data Protection Impact Assessment (DPIA) and DCT Operations Plan (DCTOP) are completed to capture the requirements for close-out activities. Refer to CS_WI_DCT0003 DCT Data Protection Impact Assessment Process and the DCT Operations Plan Template. Note: If the MSA provides for, or Global Privacy team determines that IQVIA exerts, IQVIA data controllership over some of the data being handled in close out, rather than just data processing of the data, contacts DCT Regulatory and Privacy to determine the appropriate Data Retention and Management Plan for that data. To determine if IQVIA retains or exerts controllership over data, contacts DCTRegulatoryandDPCompliance@iqvia.com for Study Hub data, and PrivacyOfficer@IQVIA.com for data not held in Study Hub. | At project setup |

  - Extraction of Site Data Collected in Study Hub

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | DCTL or delegate | - In coordination with the Clinical Lead (CL) and Monitor, ensures sites completed the following actions, in collaboration with the Site Coordinator or DCT Study Coordinator (if assigned and delegated to do so by the Delegation of Authority Log), and unless directed otherwise by the Sponsor: - All site participants are in a final status (e.g., Does Not Qualify, Dropped, or Completed) | Prior to data extraction |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Monitoring Visits are in completed status, if being captured within Study Hub - All ongoing/open activities/action items or tasks related to the project are finalized at the site - Updates the site(s) status in Study Hub to “Closed;” “Dropped;” “Not Interested;” “Not Selected;” “Prematurely Closed,” or “Rejected for Site Selection Visit”. |  |
| 6.2.2 | DCTL or delegate | Based on the project specific DCTOP requests all site level access is removed from Study Hub using directions provided in CS_WI_DCT0005 Study Hub User Account Management. | Per DCTOP |
| 6.2.3 | DCTL or Delegate | Submits an IQVIA Support Portal ticket to request a report of all open tickets related to the sites included in the data extract. | Per DCTOP |
| 6.2.4 | Study Hub IT Support | Provides an extract of any open tickets to the DCTL/delegate to ensure all data changes associated with any open tickets are complete prior to the data extract. | Following request to extract the data |
| 6.2.5 | DCTL or delegate | Confirms the open tickets have been actioned and closed. | Following review of the extract |
| 6.2.6 | DCTL or delegate | Requests extraction of site data collected in Study Hub by submitting an IQVIA Support Portal ticket. If request is for a specific site – this information should be detailed in the ticket. | Per DCTOP |
| 6.2.7 | SHSU | Assigns the ticket to extract the data to the Mulesoft System Admin. | Per DCTOP |
| 6.2.8 | DCTL or delegate | Submits an IQVIA Support Portal ticket requesting setup of the QBOX account, as follows:. - Short description: QBOX Account – Site Data - Please select what group this ticket is for: Information Technology - System/Application about which you are making your request: QBOX - Is this request Hardware related: No - Please give us the details of your IT request, and click the Submit button when finished: indicate Protocol Number, Site Number, user names and email addresses to which the data should be sent to and add a comment to assign the ticket to support group QBOX Clinops -OPB. | At the same time as performing step 6.2.3 |
| 6.2.9 | QBOX IT Admin | - Creates the requested site on QBOX. - Provides accounts for the requested users to QBOX, including the MuleSoft Admin team. | Per DCTOP |
| 6.2.10 | MuleSoft System Admin and Study Hub Support | - Follows the relevant Mulesoft system manual.for guidelines on data extract and the DCTOP for guidance on project specific Quality Control (QC) activities. - Extracts all directly identifiable project data for that site(s) and uploads it to a secure internal server. | Per DCTOP |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  | Tier 3 Team | - Completes the project level data extraction for a second time, comparing and confirming the final file size matches between both resulting extracts. - Confirms the number of site folders matches the expected number of sites, based on a separate query for sites that contains project data. - Confirms the total number of participant .xlsm files matches the expected number of participants, based on a separate query for total number of participants in the project. - Spot checks participants to verify if they belong to the given project and verify fields (randomly selected in each QC step) are available in the participant case extract as documented in the DCTOP. - Spot checks the project level excel file to confirm the expected data points/columns are included, based on the "Table of Contents" that was developed, as documented in the DCTOP. - Moves one version of the data extract to QBOX and deletes the duplicate extract used for QC purposes. Note: The directly identifiable data should be segregated by site so it can be delivered to each site separately. - Notifies the DCTL of completion of the task and addresses any feedback raised by the DCTL as part of the DCTL QC checks |  |
| 6.2.11 | DCTL or delegate | - Reviews extracted data - Confirms the number of site folders matches the expected number of sites, based on a separate query for sites that contains project data. - Confirms the total number of participant .xlsm files matches the expected number of participants, based on a separate query for total number of participants in the project. - Spot checks participant case files to confirm the expected data points/columns are included, based on the “Table of Contents” that was developed as documented in the DCTOP. - Spot checks the project level excel file to confirm the expected data points/columns are included, based on the "Table of Contents" that was developed, as documented in the DCTOP. - Contacts the MuleSoft System Admin if any of the above steps identify an error. - Contacts the site to inform them of the availability of the data in QBOX. - Sends the site the CS_FM_DCT0012 ‘Study Hub Data Transfer Completion – Investigator Acknowledgment’ form, | Once data is moved to QBOX |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | requesting confirmation of completion not exceeding 7 calendar days. - If the CS_FM_DCT0012 Study Hub Data Transfer Completion - Investigator Acknowledgment’ form is not received within 7 calendar days, sends a minimum of one follow-up email and makes a minimum of one phone call to the site to remind them to complete and send in the form. Includes the Principal Investigator, CL and Monitor in all emails and reminders sent to the site. - If the CS_FM_DCT0012 ‘Study Hub Data Transfer Completion - Investigator Acknowledgment’ form is not received within 7 calendar days, waits until confirmation is received from the site that they are ready to download the data resubmits a request the Mulesoft team to upload the data to QBOX again. - If the site does not confirm that they are ready to download the data, follows up with the site as per the decommissioning plan described in the DCTOP. |  |
| 6.2.12 | DCTL or delegate | Collects the CS_FM_DCT0012 ‘Study Hub Data Transfer Completion - Investigator Acknowledgment’ form from the site(s) and files it in the Trial Master File (TMF). | Per DCTOP |

  - Extraction of Sponsor Data Collected in Study Hub

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | DCTL or delegate | Based on the project-specific DCTOP, requests user access removal from Study Hub using directions provided in CS_WI_DCT0005. | Per DCTOP |
| 6.3.2 | SHSU | Removes users’ Study Hub access from the project and deactivates user’s Study Hub account if not assigned to any other project, as outlined in CS_WI_DCT0005. | Per DCTOP |
| 6.3.3 | DCTL or delegate | Submits an IQVIA Support Portal ticket requesting the status of theproject is updated to ‘Completed’, ‘Discontinued’, ‘Closed Follow- up/In Analysis’ in Study Hub. | Once the user access has been confirmed actioned |
| 6.3.4 | SHSU | Changes the project level status. | Per DCTOP |
| 6.3.15 | DCTL or Delegate | Submits an IQVIA Support Portal ticket to request a report of all open tickets related to the project. | Per DCTOP |
| 6.3.16 | Study Hub IT Support | Provides an extract of any open tickets to the DCTL/delegate to ensure all data changes associated with any open tickets are complete prior to data extract. | Following receipt of ticket |
| 6.3.17 | DCTL or delegate | Confirms the open tickets have been actioned and closed. | Following review of extract |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.5 | DCTL or delegate | Requests extraction of specific data collected in Study Hub by submitting an IQVIA Support Portal ticket. | After Study Hub access has been removed |
| 6.3.6 | SHSU | Forwards the ticket to the Mulesoft System Admin. | Per DCTOP |
| 6.3.7 | DCTL or delegate | Submits an IQVIA Support Portal ticket requesting setup of the QBOX account, as follows:. - Short description: QBOX Account – Sponsor Data (non PII/PHI) - Please select what group this ticket is for: Information Technology - System/Application about which you are making your request: QBOX - Is this request Hardware related: No - Please give us the details of your IT request, and click the Submit button when finished: indicate the Protocol Number, user names and email addresses to which the data should be sent to and add a comment to assign the ticket to support group QBOX Clinops -OPB. | At the same time as performing step 6.3.4 |
| 6.3.8 | QBOX IT Admin | - Creates the requested site on QBOX. - Provides accounts for the requested users to QBOX, including the MuleSoft Admin team | Per DCTOP |
| 6.3.9 | MuleSoft System Admin and Study Hub Support Tier 3 Team | - Follows the relevant Mulesoft system manual for guideline on data extract and DCTOP for guidance on project specific QC activities - Extracts pseudonymized project data and uploads it to a secure internal server. - Completes the project level data extraction for a second time, comparing and confirming the final file size matches between both resulting extracts. - Confirms the number of site folders matches the expected number of sites, based on a separate query for sites that contains project data. - Confirms the total number of participant .xlsm files matches the expected number of participants, based on a separate query for total number of participants in the project. - Spot checks participants to verify if they belong to the given project and verify fields (randomly selected in each QC step) are available in the participant case extract as documented in the DCTOP. - Spot checks participant case files to confirm the expected data points/columns are included, based on the “Table of Contents” that was developed as documented in the DCTOP. | Per DCTOP |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Spot checks the project level excel file to confirm the expected data points/columns are included, based on the "Table of Contents" that was developed as documented in the DCTOP - Spot checks to see if data other than participant information has been extracted. - Moves one version of the data extract to QBOX and deletes the duplicate extract used for QC purposes. - Notifies the DCTL of completion of the task and addresses any feedback raised by the DCTL as part of the DCTL QC checks |  |
| 6.3.10 | DCTL or delegate | - Reviews extracted data - Confirms the number of site folders matches the expected number of sites, based on a separate query for sites that contains project data. - Confirms the total number of participant .xlsm files matches the expected number of participants, based on a separate query for total number of participants in the project. - Spot checks participant case files to confirm the expected data points/columns are included, based on the “Table of Contents” that was developed as documented in the DCTOP. - Spot checks the project level excel file to confirm the expected data points/columns are included, based on the "Table of Contents" that was developed as documented in the DCTOP. - Contacts the MuleSoft System Admin if any of the above steps identify an error - Confirms that data was provided and accessible to the Sponsor. - Sends the Sponsor the CS_FM_DCT0013 ‘Study Hub Data Transfer Completion – Sponsor Acknowledgment’ form. | Per DCTOP |
| 6.3.11 | DCTL or delegate | Collects the CS_FM_DCT0013 ‘Study Hub Data Transfer Completion - Sponsor Acknowledgment’ form and files it in the Trial Master File (TMF). | Per DCTOP |
| 6.3.12 | DCTL or delegate | Stores a copy of the written correspondence/confirmation in the TMF. | Once written confirmation received from Sponsor |

  - Deletion of Study Hub Data

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.13 | DCTL or delegate | Emails DCT Operations Head to receive approval to to delete the project-specific data, including confirmation that the data is correct | Once written confirmation received from Sponsor |
| 6.3.14 | DCT Operation s Head | Sends an approval email to the DCTL or delegate to confirm that the project specific data can be deleted. | Once email is received by DCTL or delegate |
| 6.3.14 | DCTL or delegate | Sets a flag in Study Hub in the “Basic Study Information” section for the specific project to “Study data is ready to be deleted”. | Once written confirmation received from DCT Operations Head |
| 6.3.15 | DCTL or delegate | Submits an IQVIA Support Portal ticket requesting specific project data to be deleted. | Once written confirmation received from DCT Operations Head |
| 6.3.18 | MuleSoft System Admin | Deletes the project-specific data from the Study Hub production environment according to the relevant Study Hub MuleSoft Integrations Manual. Note: the user account will not be deleted from the Salesforce platform but will be updated to a non-recognizable format. Note: data will be held in backup for 90 days and then will be deleted from the backup. IQVIA will not retain any data after the 90- day period. | Once ticket received |
| 6.3.19 | MuleSoft System Admin | Confirms to the DCTL/delegate that the data deletion has been successfully completed. | Once ticket has been completed |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_DCT0003 | DCT Data Protection Impact Assessment Process |
| 7.2 CS_WI_DCT0005 | Study Hub User Account Management |
| 7.3 CS_WI_DCT0009 | DCT Operations Plan Template |
| 7.4 CS_FM_DCT0012 | Study Hub Data Transfer Completion - Investigator Acknowledgment |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.5 CS_FM_DCT0013 | Study Hub Data Transfer Completion - Sponsor Acknowledgment |
| External References |  |
| 7.6 | Mulesoft system manuals |
| 7.7 | IQVIA Study Hub System Manual |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| CS_WI_DCT0008 | Study Hub Project Closure and Decommissioning | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added steps on deletion of project- specific data | 6.3 | New information |
| Added reference to the Mulesoft system manuals | 6.2, 6.3 | New information |
| Added clarification on confirming closure of tickets and forwarding to Mulesoft System Admin | 6.2, 6.3 | New information |
| Added reference to the IQVIA Study Hub System Manuals | 6.3 | New information |
| Converted Study Hub Data Transfer Completion Forms to SOP templates | 7.0 | Standardization of forms |

- APPENDICES

Not Applicable

Page 9 of 9

Copyright © 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Aman, Asif (q754786) Title:

Date: Friday, 02 September 2022, 08:13 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Salter, Patricia (q731460) Title:

Date: Friday, 09 September 2022, 04:33 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================