|  | IQVIATM Operating Procedure Preparation of Medical Writing Deliverables |
| --- | --- |
|  | Document Number and Revision: CS_OP_MW0203 Revision 7 |
| Document Owner: Suzie Hendriques | Author(s): Corinne Willmott, Suzie Hendriques |

# PURPOSE

The purpose of this Operating Procedure (OP) is to describe the process and define responsibilities of various departments within IQVIA in the preparation of Medical Writing deliverables, regardless of document type.

# SCOPE

  - This OP applies globally to all projects for which Global Medical Writing is contracted to prepare documents.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this OP:

| Role | Sections |
| --- | --- |
| Disclosure Specialist (DS) | 6.1, 6.2, 6.3, 6.4, 6.6 |
| Document Publisher (DP) | 6.5 |
| Lead Medical Writer (MW) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6 |
| Line Manager of Lead MW or DS | 6.1 |
| Medical Writing Quality Control (QC) Reviewer | 6.2 |
| Project Leader (PL) | 6.1, 6.2, 6.6 |
| Project Management Analyst (PMA) | 6.1 |
| Project Team Member (PTM) | 6.2, 6.3 |
| Quality Assurance (QA) Lead | 6.2 |
| Senior Medical Writing Reviewer | 6.2 |

## Notes:

- The PL responsibilities may be undertaken by a member of the Project Leadership group, a Clinical Project Manager from the Early Clinical Development group, or, in the case of a stand-alone project, the Lead MW/DS, their Line Manager, or other functional lead.

- PTMs may be requested to contribute and/or perform document review as applicable to the document type and scope of work (SoW) and may include the PL, Statistical Team Lead, Therapeutic Medical Advisor, Pharmacokinetic (PK) Scientist, or other functions, as appropriate.

Page 1 of 12

Copyright © 2011, 2014, 2015, 2017, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

# DEFINITIONS

Outline: If included in the SoW, the outline (also referred to as model/shell report for a clinical study report [CSR]) is prepared for document types that present clinical data, prior to the final results becoming available. The outline is based on the relevant template(s) and final source documents (e.g., Clinical Study Protocol, statistical analysis plan [SAP]) and includes all non-data driven elements. Placeholders are included for the end-of-text tables, listings, and figures (TLFs) to be discussed in each section, and for any proposed in-text tables or figures. No results or discussion of data are included.

Draft 1 Version: For document types that report clinical data, the Draft 1 version incorporates the results based on final end-of-text TLFs. Writing from draft TLFs is usually out of scope, requiring additional Medical Writing budget. The Draft 1 version also incorporates the Customer’s comments on the outline (if applicable and included in SoW) plus any comments provided during internal team review and QC, as applicable. For documents not reporting clinical study results (e.g., Clinical Study Protocol), the Draft 1 version is the first version that is delivered to the Customer.

Draft 2 Version: The Draft 2 version incorporates the Customer’s comments on the Draft 1 version.

Final Version: The Final version incorporates the Customer’s comments on the Draft 2 version, plus any additional QC comments following final QC.

Published Version: If included in the SoW, the published version is produced following completion of full publishing, in which all components of a deliverable are converted to PDF, compiled, and hyperlinks built between components, or partial publishing where submission-ready components are created for full publishing by the Customer or third party. Note: this task is a technical document formatting task and is not related to publishing in a scientific or medical journal of a manuscript based on the trial.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

## Project Setup and Management

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | PL | Verifies that the Customer has made a written commitment to award the work and that appropriate budget for all contributing functions is confirmed before work starts. | Project Award |
| 6.1.2 | Line Manager of Lead MW or DS | Assigns the Medical Writing project to the Lead MW or DS with the assistance of the Medical Writing Customer Relationship Manager, when applicable. | Project Award |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.3 | PL | Verifies that the budget for Medical Writing is loaded correctly and, for projects using Estimate at Completion (EAC), seeks input from Lead MW or DS into establishing initial baseline and phasing of hours. Refer to CS_WI_PL0026, Project Finance (non-EAC) or CS_WI_PL0069, Project Finance Using Estimate at Completion, as applicable. | After Project Award |
| 6.1.4 | Lead MW or DS | - Provides support to Business Development, if requested. - Obtains copies of project–related documents: contract, SoW, previous change orders, budget, timelines, and team contact list from the PL, and retains for information. - Reviews the Medical Writing services to be provided in the SoW and budget loaded, verifying that the assumptions are correct, and confirms details with the Customer, as applicable. - For projects using EAC, provides input into establishing initial baseline and phasing of hours, ensuring that operational reality is reflected. Refer to CS_WI_PL0069, Project Finance Using Estimate at Completion. - Confirms the Customer primary contact for Medical Writing. - Requests access to applicable project filing areas (refer to CS_WI_MW0233, Management and Filing of Medical Writing Documentation). - Requests source documents (e.g., Clinical Study Protocol and SAP) and Medical Writing Microsoft Word templates from other IQVIA departments or the Customer, as appropriate. Other documents may also be requested as deemed necessary (e.g., example documents, style guide). - Confirms any regulatory guidance documents to be followed with the Customer or internal IQVIA team. - If in scope, informs the Narrative Writing group of the requirement for narratives. - If in scope, informs Document Publishing group of the requirement for publishing. - If in scope, informs Clinical Trial Disclosure group of the requirement for clinical trial results posting. - Schedules and requests resource for QC reviews; refer to CS_OP_MW005, Quality Control (QC) Review of Medical Writing Deliverables. - May serve as the Program Lead (when there are multiple Medical Writing projects within the same clinical development program) or the Customer-specific Representative/Relationship Manager (if identified). | After Project Award |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - When additional MWs are involved in the project, informs MWs about the project and provides the writing conventions (e.g., Customer or IQVIA style guide). |  |
| 6.1.5 | PL | - Includes Lead MW and/or DS in discussions on project timelines. - Provides the SoW and budget, timelines, and team contact list, and keeps the Lead MW and/or DS informed of any changes to these documents. - Requests and secures PTMs for review/input to deliverable (e.g., Medical Services, Biostatistics, Q2 Solutions, PK). - Obtains agreement from Customer for any required meetings relating to Medical Writing deliverables, either online, via teleconference, or face--to-face, as applicable. Note: These tasks are performed per standard project management processes in accordance with CS_WI_PL0018, Project Scope and Customer Contract Management, CS_WI_PL0029, Project Management, Communications and Reporting, and CS_WI_PL0060, Project Resource Management. | Project Setup and Conduct |
| 6.1.6 | PMA | Grants or facilitates granting of access for Lead MW and/or DS to the appropriate project filing areas. | Project Setup |
| 6.1.7 | Lead MW or DS | - Performs ongoing review of Medical Writing budget, informs PL about any out of scope request from the Customer, and keeps Medical Writing team members informed on any changes to the timelines or the SoW. - For projects using EAC, performs monthly review of project hours and works with PL and PMA to identify updates needed to forecasting, including providing input to re-baselining, and identifies outofscope hours. Refer to CS_WI_PL0069, Project Finance Using Estimate at Completion. - Maintains version control of the document(s) (see Section 6.4). - Maintains filing according to CS_WI_MW0233, Management and Filing of Medical Writing Documentation, to ensure that documents are accessible and retrievable in a timely manner. - Attends internal and Customer project team meetings as defined in the SoW and budget. - If appropriate, documents any change from the standard Medical Writing process using CS_FM_MW0224, Global Medical Writing File Note. | Project Conduct |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.8 | Line Manager of Lead MW or DS | - Provides support to the Lead MW or DS throughout the project as needed. - May serve as the Senior Medical Writing Reviewer or assist the Lead MW in assigning an appropriate Senior Medical Writing Reviewer (refer to CS_WI_MW0221, Senior Medical Writing Review of Medical Writing Deliverables). | Project Conduct |
| 6.1.9 | PL | - Processes change order(s) for out of scope requests (refer to CS_WI_PL0018, Project Scope and Customer Contract Management). - If applicable, schedules meetings with Customer in relation to Medical Writing deliverables. | Project Conduct |

  - Document Preparation by Lead MW or DS

In general, the Lead MW or DS will prepare the versions of documents defined in Section 4.0 and deliver according to the SoW and the mutually agreed timelines established at the start of the project.

Versions will not be revised and resent to the Customer, e.g., if an error is found in the Draft 1 version, this will be corrected in the Draft 2 version; a corrected Draft 1 version will not be sent. Exceptions are any errors in the Final version, which will be corrected and a revised Final version delivered.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | Lead MW or DS | Prepares each version of the Medical Writing deliverable per the SoW and according to the process outlined for the applicable document type as follows: - Clinical Study Protocol or Protocol Amendment: refer to CS_WI_MW006, Producing a Clinical Study Protocol or CS_WI_MW0236, Producing a Clinical Study Protocol Amendment - Investigator Brochure: refer to CS_WI_MW010, Preparation of Investigators Brochure - CSR (including safety reports, interim reports, addenda, errata, and other results-focused documents): refer to CS_WI_MW001, Producing a Clinical Study Report (Integrated Clinical / Statistical Report) - Patient Narratives: refer to CS_WI_MW0220, Preparation of Clinical Study Report Narratives - CSR Appendices: refer to CS_WI_MW0235, Compilation of Clinical Study Report (CSR) Appendices | Project Conduct |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Clinical Trial Results Posting: refer to CS_WI_MW0222, Producing a Clinical Trial Results Posting for Submission to Public Registries - Redacted Clinical Documents: refer to CS_WI_MW0219, Redaction of Clinical Documents for Public Disclosure Note: For document types not listed above, preparation of deliverables should follow the principles described in this OP. |  |
| 6.2.2 | Lead MW or DS | If applicable, requests the sections of the deliverable that are prepared by other PTMs for incorporation | Project Conduct |
| 6.2.3 | Senior Medical Writing Reviewer | Performs Senior Medical Writing review in accordance with CS_WI_MW0221, Senior Medical Writing Review of Medical Writing Deliverables. | Usually concurrently with QC review of Draft 1 |
| 6.2.4 | PTM | - Reviews document if requested by the Lead MW or DS, in accordance with the Work Instruction (WI) applicable to the document type (see Section 6.2.1). - Returns comments to the Lead MW or DS. - Signs CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables electronically or via wet-ink signature. | During internal review |
| 6.2.5 | Medical Writing QC Reviewer | Performs QC review of the document according to CS_OP_MW005, Quality Control (QC) Review of Medical Writing Deliverables. Required for Draft 1 and Final versions at a minimum. | Project Conduct |
| 6.2.6 | Lead MW or DS | - Verifies that all reviewers document that the review was performed by signing CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables electronically or via wet-ink signature. - Updates master version of the deliverable, as appropriate, to address the comments. Where review/QC findings relate to sections of the document drafted by another PTM, the Lead MW will consult the appropriate PTM when reviewing and addressing review/QC findings. Documents any review comment that has not been incorporated with the rationale. - Signs form CS_FM_MW007, as detailed above, to document that all comments have been reviewed and addressed as appropriate. | Project Conduct, following internal/QC review |
| 6.2.7 | Lead MW or DS | Reminds the Customer of the agreements in the SoW, or as documented elsewhere, regarding how their review comments should be provided (e.g., consolidated and adjudicated by the Customer, via the Customer’s electronic document management system [EDMS]). | Prior to Customer review |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: Provision of unconsolidated or unadjudicated comments by the Customer may be out of scope and require additional Medical Writing budget. |  |
| 6.2.8 | Lead MW or DS | Sends all scheduled deliverables to the Customer securely according to agreed format and timelines and in accordance with CS_WI_MW0201, Sending Medical Writing Deliverables to Customers Securely. | After completion of required internal reviews |
| 6.2.9 | QA Lead | If in scope, reviews document (refer to CS_OP_QA003, Audit Management; CS_TP_QA0314, Clinical Study Report Audit Workbook or CS_TP_QA0315, Clinical Study Protocol and Case Report Form Audit Workbook) and provides audit findings and/or audit report. Note: The QA Lead is not required to approve or sign off on the Medical Writing deliverable. | Usually concurrently with the last Customer review |
| 6.2.10 | Lead MW or DS | - Reviews and responds to audit findings (refer to CS_OP_QA003, Audit Management), implementing changes to the master version of the audited document as appropriate. - For any audit finding relating to document content not addressed by a change to the document, includes the rationale in the response. Note: Where audit findings relate to sections of the document drafted by another PTM, the Lead MW will consult the appropriate PTM when reviewing and addressing audit findings. | After receipt of audit findings/report |
| 6.2.11 | Lead MW or DS | Issues an email to the Customer stating that if no comments are returned within 5 business days then the document will be considered final. If no response has been received after 5 business days, the final contracted version will be considered complete. Notes: - If submitting the final version for electronic approval directly within a Customer’s EDMS, no email is required. - For dual registry results posting review, approval should be provided within 6 business days | Upon issue of final contracted version to Customer |
| 6.2.12 | PL | Identifies and contacts the Centralized Monitoring Lead (CML), or delegate assigned to project, to perform the following: - Obtain the Coordinating Investigator/Principal Investigator signature (plus any additional signatures required by Customer templates) on the final document, as applicable. - Forward the scanned signature page to the Lead MW for inclusion in the final document. | After final delivery to Customer |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Process the hard-copy original signature page according to platform-specific processes [refer to CS_WI_TMF0001, Trial Master File (TMF) - IQVIA eTMF (Wingspan), CS_WI_TMF0004, Trial Master File (TMF) - ELVIS DIA eTMF; or CS_WI_TMF0006, Trial Master File (TMF) - ELVIS pre-DIA eTMF], as applicable. - For electronic signatures, obtains the electronically signed document and provides to the Lead MW, as applicable. |  |

## Comments Resolution Meetings

The purpose of the Comments Resolution Meeting is to discuss important, conflicting, or ambiguous review comments returned by the Customer. The goal is to reach agreement on how to address these comments. Typically, the Lead MW or DS leads the meeting and the Customer/internal team members provide input during the meeting. Minutes are not prepared; however, the changes agreed may be documented using the Microsoft Word track changes feature and/or by annotating the review comments.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | Lead MW or DS | Schedules a Comments Resolution Meeting, as needed. | Following Customer review |
| 6.3.2 | Lead MW or DS | - Reviews the Customer comments and flags those requiring further discussion. - May share the annotated document with the Customer and PTMs (as applicable) to allow the team time to consider their input. | Prior to the Comments Resolution Meeting |
| 6.3.3 | PTM | Attends meeting to provide function-specific input, as applicable. | During the Comments Resolution Meeting |
| 6.3.4 | Lead MW or DS | Documents changes and team decisions using a suitable method (e.g., Microsoft Word track changes functionality), as applicable. | During the Comments Resolution Meeting |

## Maintaining Version Control of Documents

Version control is the management of changes to documents. In Medical Writing, version control is achieved by maintaining a master file of the document throughout the document preparation process (until the last version is delivered according to the SoW) and preventing other IQVIA functions or the Customer from making changes to the master file. In general, it should be assumed that the master file is being continuously edited, and incrementally different versions

(copies of the master file) are generated and released only when the document is sent out for Customer review, or when the last version is delivered.

The master file is never replaced by any files returned by reviewers, unless the Customer specifically requests so. In such cases, the Customer is responsible for any changes in the returned file that are not clearly marked or identified, and thus cannot be verified or confirmed by IQVIA.

When multiple copies of the same document are being worked on by more than one MW at the same time, sections of the document completed by other writers are carried over into the master file “owned” by the Lead MW. If multiple MWs have to work in parallel on preparing a document, it is recommended that the master document is shared using suitable company-approved software.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | Lead MW or DS | - Names the versions of a document according to CS_WI_RM0284, General and Trial Master File (TMF)- Specific Document Quality – Good Documentation Practices, Customer requirements, and/or the EDMS. - If not working in EDMS, chooses a file name that best describes the status of the document (e.g., Draft 1 version to Customer, Draft 2 version to Customer, and Final version to Customer). When working in EDMS, the file name should not include the status of the document since the same file will change over time. | During document preparation |

## Publishing of Documents

If included in the SoW, a published version of the deliverable will be prepared as described in Section 4.0.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | Lead MW | Provides all content final documents to Document Publishing for further processing, if applicable per SoW. | Following Customer confirmation that content is final and ready for publishing |
| 6.5.2 | DP | Publishes the document and delivers the final published version in line with Customer requirements/expectations and according to CS_WI_RA0292, Publishing – Producing Clinical and Submission Publishing Deliverables. | Following document approval |

## Completion of the Medical Writing Scope for Each Deliverable

A Lead MW or DS is assigned for each Medical Writing deliverable, or group of related Medical Writing deliverables, being prepared in the same timeframe.

Therefore, projects with multiple Medical Writing deliverables may have a different Lead MW at different stages of the project, and there may be no Lead MW assigned or active between deliverables. A Lead MW is responsible only for the tasks relating to their assigned deliverable(s) in accordance with the SoW.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | Lead MW or DS | Completes all activities related to filing of applicable documents and emails for the assigned deliverable(s), according to CS_WI_MW0233, Management and Filing of Medical Writing Documentation. | Upon completion of the Medical Writing scope for specific deliverable(s) |
| 6.6.2 | Lead MW or DS | Requests customer feedback for the deliverable(s) according to the current IQVIA customer survey process. | Upon completion of the Medical Writing scope for specific deliverable(s) |
| 6.6.3 | PL | Obtains the “official” Final version of document(s) from the Customer or the appropriate functions (e.g., Regulatory if IQVIA submitted the document to the agencies) if needed for any purpose (e.g., for inclusion in the Trial Master File). Note: Once the last version of the document is delivered per Medical Writing SoW, the Lead MW or DS is not responsible for tracking, maintaining, or obtaining copies of any further (published or unpublished) versions of the document that are prepared outside of IQVIA Medical Writing. Customers may make additional changes, further process, or perform final publishing of the last deliverable provided by the Lead MW or DS. | Close, after issue of the final version to the Customer |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_FM_MW0224 | Global Medical Writing File Note |
| 7.2 CS_WI_PL0018 | Project Scope and Customer Contract Management |
| 7.3 CS_WI_MW0221 | Senior Medical Writing Review of Medical Writing Deliverables |
| 7.4 CS_WI_MW0201 | Sending Medical Writing Deliverables to Customers Securely |
| 7.5 CS_OP_MW005 | Quality Control (QC) Review of Medical Writing Deliverables |
| 7.6 CS_WI_MW001 | Producing a Clinical Study Report (Integrated Clinical / Statistical Report) |
| 7.7 CS_WI_MW006 | Producing a Clinical Study Protocol |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.8 CS_WI_MW0236 | Producing a Clinical Study Protocol Amendment |
| 7.9 CS_WI_MW010 | Preparation of Investigators Brochure |
| 7.10 CS_WI_MW0220 | Preparation of Clinical Study Report Narratives |
| 7.11 CS_FM_MW007 | Internal Signature Page for Medical Writing Deliverables |
| 7.12 CS_OP_QA003 | Audit Management |
| 7.13 CS_TP_QA0314 | Clinical Study Report Audit Workbook |
| 7.14 CS_TP_QA0315 | Clinical Study Protocol and Case Report Form Audit Workbook |
| 7.15 CS_WI_RM0284 | General and Trial Master File (TMF)-Specific Document Quality – Good Documentation Practices |
| 7.16 CS_WI_MW0219 | Redaction of Clinical Documents for Public Disclosure |
| 7.17 CS_WI_MW0222 | Producing a Clinical Trial Results Posting for Submission to Public Registries |
| 7.18 CS_WI_MW0235 | Compilation of Clinical Study Report (CSR) Appendices |
| 7.19 CS_WI_MW0233 | Management and Filing of Medical Writing Documentation |
| 7.20 CS_WI_RA0292 | Publishing - Producing Clinical and Submission Publishing Deliverables |
| 7.21 CS_WI_PL0026 | Project Finance (non-EAC) |
| 7.22 CS_WI_PL0029 | Project Management, Communications and Reporting |
| 7.23 CS_WI_PL0069 | Project Finance Using Estimate at Completion |
| 7.24 CS_WI_TMF0001 | Trial Master File (TMF) - IQVIA eTMF (Wingspan) |
| 7.25 CS_WI_TMF0004 | Trial Master File (TMF) - ELVIS DIA eTMF |
| 7.26 CS_WI_TMF0006 | Trial Master File (TMF) - ELVIS pre-DIA eTMF |
| 7.27 CS_WI_PL0060 | Project Resource Management |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_OP_MW0203 | Preparation of Medical Writing Deliverables | 6 |

- MODIFICATION FROM PREVIOUS REVISION - TO BE DONE

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Minor formatting and abbreviations updated, and SOP titles updated | Throughout | For clarity |

| Added text to clarify that for dual registry results posting review, approval should be within 6 business days | 6.2 | To clarify process for dual registry results posting review |
| --- | --- | --- |
| Removed CL from step to obtain coordinating investigator signature | 6.2 | CML is responsible for close out activities, not CL |
| Added text to allow for electronic signatures by Coordinating Investigator | 6.2 | To describe process if Coordinating Investigator signs a document electronically |
| Updated text to allow for any electronic signature, removed reference to electronic approval workflow | 6.2 | To clarify current process for electronic signatures |

- APPENDICES

Not Applicable

Page 12 of 12

Copyright © 2011, 2014, 2015, 2017, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

UserName: Ginzler, Maria (q602835) Title:

Date: Wednesday, 29 June 2022, 07:31 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Corley, Helen (q730385) Title:

Date: Wednesday, 29 June 2022, 07:55 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Willmott, Corinne (q778849) Title:

Date: Wednesday, 29 June 2022, 08:03 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Wednesday, 29 June 2022, 08:04 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ferrari, Antonio (q844337) Title:

Date: Wednesday, 29 June 2022, 08:40 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Eason, Carrie (q605126) Title:

Date: Wednesday, 29 June 2022, 10:58 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Wednesday, 29 June 2022, 11:51 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Janse van Rensburg, Rene (q714326) Title:

Date: Thursday, 30 June 2022, 10:17 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Weilert, Doris (q406557) Title:

Date: Thursday, 30 June 2022, 11:19 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================