|  | IQVIATM Work Instruction Medical Input into Quality and Safety for Awarded Projects |
| --- | --- |
|  | Document Number and Revision: CS_WI_MS0210 Revision 7 |
| Document Owner: Antonio Ferrari | Author(s): Antonio Ferrari, Rosa Piccirillo |

# PURPOSE

The purpose of this Work Instruction (WI) is to define the processes for Therapeutic Medical Advisor (TMA) input into overall project quality and safety with respect to key study objectives, study data quality, and subject safety (i.e., critical data and processes). Additionally, this WI outlines the responsibilities of TMAs in assisting the project team with quality and safety issues during the lifecycle of the study.

# SCOPE

  - This WI is applicable to all awarded studies which incorporate Medical Services where TMA input is provided to meetings/discussions for project risk management and handling Protocol deviations.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Clinical Lead (CL) | 6.3, 6.4 |
| Global Therapeutic Medical Advisor (Global TMA) | 6.2, 6.4 |
| Project Leader (PL) | 6.1, 6.2, 6.3 |
| Therapeutic Medical Advisor (TMA) | 6.1, 6.3, 6.4 |
| Medical Strategy Lead (MSL) | 6.1 |

# DEFINITIONS

Refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services

Medical Monitoring: Medical monitoring is defined as the provision of contracted medical support by Medical Services to Investigator sites and the project team including, at a minimum, Protocol clarification and provision of safety and any other advice on the Investigational Product (IP) or study-related procedures.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Medical Input into Project Quality and Safety

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | MSL | Consults with Regional TMAs to provide feedback on Project Quality and Safety | Prior to recruitment |
| 6.1.2 |  | Records medical input in CS_TP_PL0092, Protocol Derisking Tool – Internal Use | Prior to recruitment |
| 6.1.3 |  | Provides medical input and completed form to and discusses with PL and project team as per CS_WI_PL0023, Project Lifecycle Planning and CS_WI_PL0025, Project Risk, Issues and Lessons Learned Management | During PL-led Internal Planning Meeting, internal portion of Kick-off Meeting and subsequent discussions/ meetings, as needed |
| 6.1.4 | TMA | Reviews, at a minimum, the Protocol and Investigator Brochure (IB) or the Summary of Product Characteristics (SmPC), or Patient Information Leaflet (PIL) as applicable and the Statistical Analysis Plan (SAP) if available, as these documents will be extensively referenced within the medical review | Upon providing medical input |
| 6.1.5 |  | Identifies key medical risks to data quality and subject safety, and also advises internal teams (Data Management, Medical Safety Surveillance (MSS), etc.) on strategies to mitigate these risks by following Steps 6.1.7-6.1.13 and documents the requested information and review in CS_TP_PL0092, Protocol Derisking Tool – Internal Use |  |
| 6.1.6 |  | Undertakes a detailed analysis of the primary and co-primary objective(s) and variable(s) and attendant risks to study quality |  |
| 6.1.7 |  | Lists study data critical to the primary and main secondary objective |  |
| 6.1.8 |  | Gives consideration to risk mitigation for each critical data component |  |
| 6.1.9 |  | Lists inclusion/exclusion criteria deemed to be critical to the study primary objective and subject evaluability, and gives |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | consideration to risks and mitigation plans for each inclusion/exclusion criterion listed |  |
| 6.1.10 |  | Identifies and lists key factors in study compliance and conduct following randomization, critical to subject evaluability, and gives consideration to potential risks and the risk mitigation plan for each key factor listed |  |
| 6.1.11 |  | Identifies key inclusion/exclusion criteria critical to subject safety, and considers and documents potential risks and mitigation plans for each critical criterion |  |
| 6.1.12 |  | Identifies key facets of study conduct and site and patient compliance following randomization, critical to safety, and considers and documents potential risks and mitigation plans for each critical criterion |  |
| 6.1.13 |  | Reviews the IB and lists possible safety signals from pre- clinical and clinical data, giving consideration to risk mitigation strategies for each listed potential safety signal Note: IB review for identification of potential safety signals should be taken in conjunction with the Sponsor and is a mandatory component of medical input into project quality and safety. |  |
| 6.1.14 | PL/ designee | Enters medical input into project quality and safety risks (i.e. critical data and processes) in IQVIA Resource and Portofolio Management system: Project and Portfolio Management tool (QRPM: PPM) Risks, along with all other identified project risks Note: The risks identified by the TMA are reviewed with the Sponsor during the kick-off meetings (KOM) and subsequent meetings throughout the project (CS_WI_MS0213, Medical Monitoring Plan Creation and Review). | Upon completeion of medical review activities |

  - Review of Subject Safety Information during the Study

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | Global | Provides oversight of the medical data review in accordance | Project conduct; first patient in (FPI) through database lock (DBL) |
|  | TMA | with CS_TP_MS003 Medical Monitoring Plan |  |
| 6.2.2 | PL | Requests that the Sponsor provides the updated IB (for |  |
|  |  | Phases 1 through 3b studies) as well as the updated SmPC, |  |
|  |  | PIL or IB, as applicable for Phase 4 studies and distributes |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | the documents to update the TMA, Medical Safety Advisor (MSA), Medical Data Reviewer (MDR) and Medical Safety Surveillance (MSS) are updated on the latest safety information on the IP |  |
| 6.2.3 | Global TMA | Communicates to the PL and relevant project team members/Sponsor the safety information and any potential emergent safety signals iteratively |  |
| 6.2.4 | PL/ designee | Records safety information risks and any potential emergent safety signals in QRPM: PPM Risks (non-RBM projects) or Risk Mitigation Workbench (RMW – RBM projects) |  |
| 6.2.5 | Global TMA | Confirms, usually by email or minutes of a Sponsor teleconference, that review of cumulative Serious Adverse Event (SAE) listings and other emergent safety information has taken place, and if any further actions are recommended |  |

  - Protocol Deviation Review

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | TMA | Reviews the Protocol, IB, and SAP (if available) and provides to the CL/ PL a list of key potential Protocol deviations impacting subject eligibility, evaluability, safety, and the primary objective | During start up |
| 6.3.2 | TMA, PL, and applicable project team member | Discuss procedures, including escalation and corrective action plans, for the identified key Protocol deviations | During the conduct of the study |
| 6.3.3 | CL | Provides the Protocol deviation log to the TMA | During the study conduct, at least once a month or at frequency defined for the project during the active recruitment phase of studies |
| 6.3.4 | TMA | Reviews the Protocol deviation log to assess and categorize the level of the deviation (critical, major or minor) |  |
| 6.3.5 | TMA | Provides documentation of the review of cumulative Protocol deviation listings by email as per the Protocol Deviation Management Plan (PDMP) | Upon completion of review of the Protocol deviation log |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: Refer to CS_WI_PL0038 Handling of Protocol Deviations. |  |
| 6.3.6 | TMA | Provides advice to the study team on a corrective action plan to prevent recurrence of potential deviations critical to eligibility, safety, evaluability, and the primary objective | As an integral part of the review |
| 6.3.7 | TMA | Assesses if Protocol amendments may be required and, if so, provides advice to the Sponsor to draft an amendment | Upon identification of the need for a Protocol deviation |

  - Handle of 24/7 Medical Emergency Coverage

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | TMA | Handles 24/7 emergency medical enquiries as documented in CS_WI_MS0203 Medical Advisor 24/7 Medical Emergency Coverage | During the conduct of the study if study contracted for 24/7 medical emergency coverage |
| 6.4.2 | CL/ Global TMA | Discusses urgent contact procedures with the Sponsor, for studies that IQVIA is not providing 24/7 medical emergency coverage, clearly documents these discussions in meeting minutes and describes the process in the Clinical Operations Plan (COP) or in the Integrated Project Management Plan: Project Communication Plan | In studies for which IQVIA is not providing 24/7 coverage |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_TP_MS003 | Medical Monitoring Plan |
| 7.2 CS_WI_MS0203 | Medical Advisor 24/7 Medical Emergency Coverage |
| 7.3 CS_TP_PL0092 | Protocol Derisking Tool - Internal Use |
| 7.4 CS_WI_PL0023 | Project Lifecycle Planning |
| 7.5 CS_WI_PL0025 | Project Risk, Issues and Lessons Learned Management |
| 7.6 CS_WI_PL0038 | Handling of Protocol Deviations |
| 7.7 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.8 CS_WI_MS0213 | Medical Monitoring Plan Creation and Review |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_MS0210 | Medical Input into Quality and Safety for Awarded Projects | 6 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| CS_FM_MS0212 to CS_TP_PL0092 | 6.1.2 and 6.1.5 | New tool created and it should be used when TMA performs medical input into quality and safety for the study |
| Update role section to PL/ designee | 6.2.4 and 6.1.14 | To clarify who perform the step |
| Supporting documentation update | 7.0 | List of supporting documents were updated |

- APPENDICES

Not Applicable

Page 6 of 6

Copyright © 2011, 2014, 2016, 2018, 2020, 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

UserName: Neilson, Irene (q731875) Title:

Date: Wednesday, 09 June 2021, 09:19 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Wednesday, 09 June 2021, 09:54 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Kemp, Jaco (q608126) Title:

Date: Wednesday, 09 June 2021, 10:06 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Piccirillo, Rosa (q792913) Title:

Date: Wednesday, 09 June 2021, 01:01 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Thursday, 10 June 2021, 01:20 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ferrari, Antonio (q844337) Title:

Date: Thursday, 10 June 2021, 05:07 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================