|  | IQVIATM Work Instruction Medical Monitoring Plan Creation and Review |
| --- | --- |
|  | Document Number and Revision: CS_WI_MS0213 Revision 8 |
| Document Owner: Antonio Ferrari | Author(s): Jabeen Menzies, Emiliano Calatayud |

# PURPOSE

  - To describe the process for creating (including approving) the Medical Monitoring Plan (MMP) and reviewing/revising the MMP as needed for a contracted IQVIA clinical trial.

# SCOPE

  - This Work Instruction (WI) applies globally to:

    - Medical and Scientific Services

    - Research and Development Solutions (RDS) groups including Early Clinical Development (ECD)

    - Project Leadership

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Global Therapeutic Medical Advisor (GTMA) | 6.1, 6.3, 6.4, 6.5 |
| Medical Surveillance Specialist (MSS) | 6.1, 6.2 |
| Clinical Scientist (CS) | 6.1, 6.2, 6.4, 6.5 |
| Medical Safety Advisor (MSA) | 6.1, 6.2, 6.4, 6.5 |
| Medical Data Reviewer (MDR) | 6.1, 6.2, 6.4, 6.5 |
| Project Leader (PL) | 6.4, 6.5 |
| Medical Strategy Lead (MSL) | 6.1 |
| Central Monitor (CM) | 6.1 |

# DEFINITIONS

Medical Monitoring Plan (MMP): The MMP outlines the role of the Therapeutic Medical Advisor (TMA) in ensuring safety of the patient in a clinical trial while adhering to the scope of work. It also outlines the communication among internal stakeholders as well as with the Customer.

# MATERIAL AND EQUIPMENT

Not Applicable

Page 1 of 7

# PROCEDURE

  - Creation and revision of the MMP

The MMP is always negotiated with the Customer and some Customers may mandate the use of their own template. Any substantial change requested by the Customer must be assessed. In the case of Customer-mandated templates, it is imperative to check that all the components of the IQVIA MMP are included in the template and compatible. If needed, the components of the IQVIA MMP must be requested to be included in the Customer’s template either as amendments or as an addendum.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | GTMA with CS support | Convenes an “Internal Medical Kick-off Meeting (imKOM)”, including all internal stakeholders listed below: - MSL - CS (if assigned) - MDR - MSS - MSA - CM for Data Trial Execution (DTE) studies - Regional TMAs if assigned If all team members are not appointed in time, at least regular teleconferences (TCs) should be scheduled to discuss medical scope of work (SOW) among the team, under GTMA responsibility, guidance and oversight. Main objective of this meeting is: - Thorough understanding of the SOW included in the award budget. - The meeting is held under the leadership of the assigned GTMA with the participation of MSL (for the completion of the hand over knowledge from the proposal stage) and the representatives of the service lines either budgeted at the time of the meeting or called upon by the decision of the assigned GTMA if he/she assesses there is a need to propose including these service lines to a Customer. GTMA will consult with their LM if other service lines need to be invited to imKOM where services are not budgeted at that moment. - If the appointed functional line members are not available, a suitable and empowered back-up will be appointed to represent the service in the preparation for a project delivery. - The meeting will be recorded and minutes will be taken. The outcome of the meeting will be summarized in action points. | Before External KOM |
| 6.1.2 | MDR | Provides input into the Medical Data Review Plan (Appendix A of the MMP- CS_TP_MS003 Medical Monitoring Plan). | At Internal Medical KOM |
| 6.1.3 | MSS | Provides input into the Medical Safety Surveillance Laboratory Report Review Guidelines (Appendix B) and Medical Surveillance ECG Report Review Guidelines (Appendix C) of the MMP using | At Internal Medical KOM |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | information from the Protocol and the laboratory manual or laboratory flow chart. |  |
| 6.1.4 | MSA | Provides input into the Serious Adverse Events (SAEs), Analysis Of Similar Events (AOSEs), and aggregate data review (appendix A of the MMP template) from information from the Protocol and the Investigator Brochure (IB)/ Summary of product characteristic (SmPC). | Before External KOM |
| 6.1.5 | CM | Provides input into the MMP for centralized monitoring aspects of the study if applicable – (A separate Subject Level Data Review (SLDR) plan may also be created). |  |
| 6.1.6 | GTMA with CS support | Shares meeting minutes among the team. | After the Internal KOM |
| 6.1.7 |  | Distribute the information regarding the medical scope or work agreed and finalized to Regional TMA(s), MDR, MSS, Central monitor, CS and MSA. | After the External KOM |
| 6.1.8 | GTMA with CS support and input from the internal stakeholders | Uses CS_TP_MS003 Medical Monitoring Plan to draft the project- specific Medical Monitoring Plan (MMP) to reflect the contracted services any Protocol specific details. Note: No prospective protocol deviations are allowed to inclusion/exclusion criteria. All medical questions and answers will be included in the Questions & Answers log (FAQ) with the help of an assistant; their precedent will be followed on similar questions. | Before first subject screened Ongoing from study start-up |
| 6.1.9 | GTMA, MDR and MSS with CS support | Assesses with the Customer medical counterpart the potential for reviewers to be unblinded and documents the outcome of the assessment in the MMP by selecting the applicable scenario: - No potential to un-blind a reviewer. - There is potential for the following data to un-blind a reviewer. [Specify data points. Include the appropriate rationale listed below]: - There will not be the need for an unblinded MDR and/or MSS. The MMP is crafted so that if data review or lab monitoring is contracted, data that has the potential to un- blind is not reviewed if there is no impact on subject safety or reviewed in such a manner (i.e. individually or in aggregate) as to not lead to inadvertent unblinding - There will be the need for an unblinded MDR and/or MSS for the following data. [Specify data points.] Note: Please refer to CS_WI_DM0423 (Managing Unblinded Data) regarding managing unblinded data in discussions with the Customer medic. | Before first subject screened |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.10 | GTMA, MDR and MSS with CS support | Approves the revised MMP. | Before first subject screened |

  - Prepare laboratory and/or ECG report review, Medical Data Review sections of the MMP

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | MSS with CS support | Completes the Medical Safety Surveillance Laboratory Report Review Guidelines (Appendix B). | Before first subject screened |
| 6.2.2 |  | Completes the Medical Surveillance ECG Report Review Guidelines (Appendix C). |  |
| 6.2.3 | MSA & MDR | Completes the Medical Data Review Plan (Appendix A). |  |

  - Review of the MMP

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | GTMA | If laboratory report and/or ECG review are contracted, reviews Appendix B and Appendix C, as edited by the MSS or designee if laboratory report and/or ECG review are contracted. | Before finalisation of MMP |
| 6.3.2 |  | Reviews edits made by the MSA for individual subject safety review (individual case safety review in safety database (ICSR), SAEs) and other activities related to signal detection Safety Trend Analysis Report (STAR)), regulatory reports (DSUR) to Medical Data Review Plan (Appendix A), verifying scope matches contract if MSA services are contracted. | Before finalisation of MMP |
| 6.3.3 |  | Reviews edits made by the MDR on the program to Appendix A, verifying scope matches contract if MDR services are contracted. | Before finalisation of MMP |

  - Approval of the MMP

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | GTMA | Confirms review by all contributors to the MMP (e.g. MDR, MSA | Before finalisation |
|  | with CS | and MSS). | of document |
|  | support |  |  |
| 6.4.2 |  | Sends to the PL for review, with the purpose of assessing |  |
|  |  | whether the MMP is consistent with the contract and Quintiles |  |
|  |  | pricing model (QIP). |  |
| 6.4.3 |  | Reviews the MMP with the Customer medical representative. | After all internal |
|  |  |  | input has been |
|  |  |  | obtained, but |
|  |  |  | before FPI and |
|  |  |  | finalisation of MMP |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.4 | GTMA with CS support | Obtains final approval from the MDR, MSS and MSA of the MMP based on contracted scope. | After finalization of the MMP, but before first subject screened |
| 6.4.5 |  | Forwards the finalized MMP to the CS (if contracted), Administrative Assistant (AA) (If assigned), PL or Project Management Analyst (PMA) to initiate the electronic signature of approval from the GTMA, RTMAs, MDR, MSS, MSA representatives. | Before first subject screened |
| 6.4.6 | GTMA | Approves the MMP on behalf of IQVIA after approval from internal stake-holders obtained. Note: The preferred method for approval of documents is by use of e- Signature, refer to CS_WI_RM0284 General and Trial Master File (TMF)-Specific Document Quality – Good Documentation Practices. Note: If laboratory and/or ECG review guidelines are being used, these are integral components of the MMP and approval should not be given until these are completed. | After finalization of the MMP, but before first subject screened |
| 6.4.7 | GTMA with CS support | Forwards the approved MMP to the Customer according to the agreed communication plan for Customer’s approval. | After all internal approvals have been received, but before first subject screened |
| 6.4.8 | GTMA with CS support/ PL | Forwards the approved MMP to the AA (if assigned), PMA or PL for filing in the Trial Master File (TMF) (paper or electronic as per SOW), informing PL. | After all approval signatures have been obtained, but before first subject screened. |
| 6.4.9 | GTMA with CS support | Forwards copy (when Paper TMF) or link (when eTMF) to the approved MMP to the MSS, MSA, MDR for sharing with their respective teams. |  |
| 6.4.10 | GTMA with CS support | Updates the medical tasks, redistributes/posts and notifies the PL of any budget adjustments required if the SOW changes during the conduct of the study or if there are major changes in the SOW. Note: The version number of the MMP should be increased and should be approved. (see Appendix D of the MMP template) MMP versioning should be a sequential number representing the latest version, starting with Version 1.0. Subsequent final versions for major updates are indicated as 2. 0, 3.0, etc. For minor changes, a sequential “dot version” may be used, such as 1.1, 1.2, 1.3 (refer to instructions in Appendix D of the MMP template). | Project conduct |

  - Protocol amendments and other substantial changes impacting project conduct.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | GTMA/ PL | Assesses the impact of changes on the current MMP when notified of any changes that may directly impact the conduct of the trial, including amendments to the Protocol and the SOW. | Project conduct |
| 6.5.2 | GTMA with CS support | Modifies the MMP within 4 weeks of receiving an amended final Protocol. | If required changes are substantial as indicated by the Customer |
| 6.5.3 |  | Updates the MMP for minor changes as needed. | During the course of the trial |
|  |  | Note: Minor changes to the MMP do not require approval |  |
|  |  | For minor changes, a sequential “dot version” may be used, such as 1.1, 1.2, 1.3 (refer to instructions in Appendix D of the MMP template). |  |
| 6.5.4 |  | Approves the revised MMP on behalf of IQVIA after approval from internal stakeholders obtained. | After all updates have been made and within 6 weeks of receiving a final amended Protocol |
| 6.5.5 | GTMA with CS support | Submits the revised MMP to the Customer for approval | If required changes are substantial as indicated by the Customer |
| 6.5.6 | GTMA with CS support | Forwards the revised and approved MMP to the AA (if assigned), PL or PMA for filing in the TMF (paper or electronic as per SOW) | After approval of the MMP, as applicable |
| 6.5.7 | GTMA with CS support | Forwards copy of or link to the revised and approved MMP to the MSS, MDR, and MSA for sharing with their respective teams | After approval of the MMP |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_RM0284 | General and Trial Master File (TMF)-Specific Document Quality – Good Documentation Practices |
| 7.2 CS_TP_MS003 | Medical Monitoring Plan |
| 7.3 CS_WI_DM0423 | Managing Unblinded Data |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_MS0213 | Medical Monitoring Plan Creation and Review | 7 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Roles and Responsibilities updated | 3.0 | Subject Level Data Reviewer replaced with Central Monitor |
| Supporting documentation updated | 7.0 | Some of listed documents become obsolete |

- APPENDICES

Not Applicable

Page 7 of 7

Copyright © 2011, 2014, 2016, 2018, 2019, 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Neilson, Irene (q731875) Title: Sr Clin Plan Analyst

Date: Friday, 12 February 2021, 08:08 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Calatayud, Emiliano (q703375) Title: Sr Dir, Medical

Date: Friday, 12 February 2021, 09:13 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ferrari, Antonio (q844337) Title: Sr Dir, Medical

Date: Sunday, 14 February 2021, 05:09 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Laxenaire, Julie (q766314) Title: Clin Resourcing Mgr

Date: Monday, 15 February 2021, 06:56 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Kennedy, Jillian (q600133) Title: Dir, Quality Mgmt

Date: Monday, 15 February 2021, 07:42 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================