## Instructions
1.0 Instructions
1. This template consists of two checklists each with its own use.
2. Each checklist can be modified to meet the needs of the project or region, i.e., documents/items can be added, changed or marked "not applicable" as needed.
3. Transfer of information on Core and Country documents is completed in one step. It can be initiated and completed before transfer of information on site documents as soon as all applicable approvals for the particular country are available but best practice is to be combined with initiation of transfer of the first site within the country. Transfer should occur prior to first SIV in the country and it may occur via e-mail or via formal meeting. However, in case of complex projects, projects with multiple country vendors it is advisable transfer to be done via formal meeting. One transfer per country is required.
4. Transfer of information on site documents is completed in two steps. The first step should be completed in advance of the SIV. The Monitor is provided with an overview of the key areas of the site from the perspective of site information, site documents and Site Ready to Enroll (SRtE ) activities. The second step - signing and dating the site transfer checklist -should be completed after all SRtE activities have been completed. Resolution date(s) for all action items related to SRtE should be added in comment section. Best practice for initiating transfer of information of Site documents is as early as Essential Document Pack for particular site is approved. Transfer of information on Investigator site documents may occur via e-mail(s) or via formal meeting(s). A separate site transfer checklist is required for each site.
5. It is required to attach reports, add links or documents at the time of transfer . The comment field can be used for this purpose as well as it can be used for any additional infrmation that is not part of the attached reports/links/documents, in order to document action items, resolution dates, etc.
6. Signatures can be either electronic or wet signature. Electronic signatures are preferable, when possible and should be applied using the appropriate TMF platform or validated eSignature solution.
7. Filing should be completed according to the appropriate Trial Master File.
LRSU - Core and Country Transfer Checklist
LRSU must use this checklist for the transfer of information on Core and Country Documents, as described in section 6.5 of CS_WI_RSU0068.
Review the following completion guidelines and complete the corresponding columns on the LRSU - Country Transfer tab
FIELD TITLE | GUIDELINES
Country Targets and Planned SSU Completion Dates (PCDs) | Include report providing details over targets for site open and PCDs within the country. For example, export from Site Activation Delivery Summary of Site Activation Study Toolkit, export from Start Up Oversight Status Report from Clinical Analytics or report/export from Trial Management System that provides same level of information.
Confirmation of tracking in Trial Management System (includes but is not limited to all critical fields including submission and approval dates) | Include report from Trial Management System providing details over tracking of critical fields on country level (e.g. dates of submissions, approvals, etc.). For example export from Country& Site Summary of Site Activation Study Toolkit, or report/export from Trial Management System that provides same level of information. Also include Critical Field compliance report and provide information over % of compliance on country level.
Confirmation of TMF filing status of approved Core & Country documents that are to be included in the CS_TP_RSU0050 Essential Documents Pack - Review Checklist (EDP-RC) (e.g., Protocol, IB, ICFs, RA/EC approvals, etc.) | Include TMF report (s) containing links to the actual documents, their versions and providing information over % of compliance. For example for projects using IQVIA eTMF (Wingspan) provide Completeness report and Study Item export (full data) for Core & Country documents. For other TMF platforms, report(s) need to include same level of information. If there are documents which are not yet filed list them all providing information on the version and attach actual documents. As minimum reports need to provide filing status of approved (submitted and approved by relevant authorities ( IRB/EC/RA)) Core & Country documents that are to be included in the EDP-RC but it is acceptable report to provide filing status of all Core & Country documents.
Open or forthcoming country related action items (e.g., new protocol amendments, new ICF development, new contract/budget amendments, follow-up items, etc.) | List any open or forthcoming country related action items. If no such action items document it is N/A
Country specific items Monitor needs to be aware of (includes but is not limited to): 1. Sponsor Concerns 2. Escalations 3. Country specific vendors 4. Country specific risks and issues | Provide details over applicability and status for all of items listed in Column A as per guidance provided in the checklist. Add any other country specific item that according to LRSU is critical for Monitor awareness. For every item need to be clear if applicable or not and if yes details and actions need to be provided.
Other Study Specific Information/Documents | Include any other study specific information and/or specific documents not included above.
LRSU - Site Transfer Checklist
LRSU must use this checklist for the transfer of Information on Investigator Site Documents, as described in section 6.6 of CS_WI_RSU0068.
Review the following completion guidelines and complete the corresponding columns on the LRSU - Site Transfer tab
FIELD TITLE | GUIDELINES
Confirmation of site-level tracking in Trial Management System (includes but is not limited to all critical fields including submission and approval dates) | Include report from Trial Management System providing details over site level tracking of critical fields (e.g. dates of submissions, approvals, etc.). For example export from Country&Site Summary of Site Activation Study Toolkit, or report/export from Trial Management System that provides same level of information.
Confirmation of TMF filing status of all site level documents included in the approved CS_TP_RSU0050 Essential Documents Pack - Review Checklist (EDP-RC). | Include TMF report (s) containing links to the actual documents, their versions and providing information over % of compliance. For example for projects using IQVIA eTMF (Wingspan) provide Completeness report and Study Item export (full data) for Site documents. For other TMF platforms, report(s) need to include same level of information. If there are documents which are not yet filed Include copy of approved EDP-RC ( link is also acceptable). As minimum reports need to provide filing status of site level documents included in the approved EDP-RC but it is acceptable report to provide filing status of all Site documents.
Open Actions related to completion of Site Ready to Enroll activities | Provide export from SRtE checklist. List any open action at the time of initial meeting and add date of resolution at the time of signing the transfer checklist
Site contact details | Include link to Site Ready to Enroll Site Contact Form or attach the completed form
Site-specific items Monitor to be aware of (includes but is not limited to): 1. Open actions related to "approved with action " items on EDP-RC 2. QA status not satisfactory (i.e. QA Status other than Reviewed) 3. Details over payment schedule and division of payment 4. Any site specific local vendor and associated Ancillary agreements 5. Site-specific risks and issues | Provide details over applicability and status for all of items listed in Column A as per guidance provided in the checklist. Add any other site-specific item that according to LRSU is critical for Monitor awareness. For every item need to be clear if applibale or not and if yes details and actions need to be provided.
Other Site-Specific Information/Documents | Include any other site-specific information and/or specific documents not included above.

## LRSU-Core and Country Transfer
LRSU - Monitor: Core and Country Transfer
Sponsor Name: | Project Code:
Protocol Number: | EU Clinical Trial/EudraCT Number (if applicable):
Country: | Meeting Date (if transfer via email, note date email sent):
Monitor(s) Name(s):
Documents/Information shared during transfer | Comments (Include action(s) required if applicable)
Country Targets and Planned SSU Completion Dates (PCDs) | Include relevant report providing details over targets for site open and PCDs within the country
Confirmation of tracking in Trial Management System (includes but is not limited to all critical fields including submission and approval dates) | 1. Include relevant report frorm Trial Management System providing details over tracking of critical fields ( e.g. dates of submissions, approvals, etc.) 2.Include Critical field compliance report and provide information over % of compliance on country level
Confirmation of TMF filing status of approved Core & Country documents that are to be included in the CS_TP_RSU0050 Essential Documents Pack - Review Checklist (EDP-RC) (e.g. Protocol, IB, ICFs, RA/EC approvals, etc.) | 1. Include relevant TMF report (s) containing links to the actual documents, their versions and providing information over % of compliance. 2. If there are documents which are not yet filed list them all providing information on the version and attach actual documents
Open or forthcoming country related action items (e.g.,new protocol amendments, new ICF development, new contract/budget amendments, follow-up items, etc.) | List any open or forthcoming country related action items. If no such action items document it is N/A
Country specific items Monitor needs to be aware of (includes but is not limited to): 1. Sponsor Concerns 2. Escalations 3. Country specific vendors 4. Country specific risks and issues Add any other country specific item that might contain critical information for Monitor | Provide details over applicability and status for any of items listed in Column A 1. Sponsor Concerns: Y/N If Y - list all 2. Escalations: Y/N If Y - list details and actions taken 4. Country specific vendor(s): Y/N If Y provide details for the vendor and provide link to executed Ancillary Agreement(s) or attach executed Ancillary Agreement(s) 5. Country specific risk and issues: Y/N If Y - provide details and list all Other: If applicable provide details as necessary if not applicable document it is N/A
Other Study Specific Information/Documents Please specify below and add rows as required.
Signatures
LRSU Representative Name and Title (Please Print) | Date (dd/Mmm/yyyy)* | Signature*
*Date and Signature may be completed via eSignature

## LRSU - Site Transfer
LRSU - Monitor: Site Transfer
Sponsor Name: | Project Code:
Protocol Number: | EU Clinical Trial/ EudraCT Number (if applicable):
Country: | Site Number:
Pre - SIV Meeting Date: (if transfer via email, note date email sent) | PI Name:
Monitor Name:
Documents/Information shared during transfer | Comments Include action(s) required if applicable
Confirmation of site-level tracking in Trial Management System (includes but is not limited to all critical fields including submission and approval dates) | Include relevant report from Trial Management System providing details over site-level tracking of criticial fields ( e.g. dates of submissions, approvals, etc.)
Confirmation of TMF filing status of all site level documents included in the approved CS_TP_RSU0050 Essential Documents Pack - Review Checklist (EDP-RC). | 1. Include relevant TMF report (s) containing links to the actual documents, their versions and providing information over % of compliance 2. Include copy of approved EDP-RC ( link is also acceptable) if there are documents which are not yet filed.
Open Actions related to completion of Site Ready to Enroll activities | 1.Provide export from SRtE checklist 2. List any open action at the time of initial meeting and add date of resolution at the time of signing the transfer checklist
Site contact details | Include link to Site Ready to Enroll Site Contact Form or attach the completed form
Site-specific items Monitor to be aware of (includes but is not limited to): 1. Open actions related to "approved with action " items on EDP-RC 2. QA status not satisfactory (i.e. QA Status other than Reviewed) 3. Details over payment schedule and division of payment 4. Any site specific local vendor and associated Ancillary agreements 5. Site specific risks and issues Add any other site-specific item that might contain critical information for Monitor | Provide details over applicability and status for any of items listed in Column A 1. Open actions from EDP-RC : Y/N If Y - list all 2. QA Status ( as per EDP-RC ) not satisfactory: Y/N If Y - list details and actions taken 3. Details over payment schedule and division of payment: provide necessary details and provide link to executed CTA(s) or attach executed CTA(s) 4. Site specific vendor(s): Y/N If Y provide details for the vendor and provide link to executed Anxillary Agreement(s) or attach executed Ancillary Agreement(s) 5. Site specific risk and issues: Y/N If Y - provide details and list all Other: If applicable provide details as necessary if not applicable document it is N/A
Other Site -Specific Information/Documents Please specify below and add rows as required.
Signatories:
LRSU Representative Name and Title (Please Print) | Date (dd/Mmm/yyyy)* | Signature*
*Date and Signature may be completed via eSignature. Checklist is to be signed and dated only after all SRtE activities have been completed for the site