|  | IQVIATM Operating Procedure Site Activation |
| --- | --- |
|  | Document Number and Revision: CS_OP_RSU0060 Revision 6 |
| Document Owner: Laurie Flintom | Author(s): Paige Niemczyk, Zubin Thacker, Adam Cribbs, Mary Beatty, Jessica Gant |

# PURPOSE

To define the Investigator Site Activation process.

# SCOPE

  - This operating procedure (OP) applies to IQVIA Research and Development Operations (R&DO) personnel supporting the Investigator Site Activation process.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this OP:

| Role | Sections |
| --- | --- |
| Clinical Lead (CL) | 6.1, 6.3, 6.6 |
| Contract Budget and Solutions Lead (CBSL) | 6.1, 6.4 |
| Global Site Identification Lead (GSID Lead) | 6.1, 6.2, 6.3 |
| Site Analytics Lead (SA Lead) | 6.1, 6.2 |
| Local Contract Negotiator | 6.1, 6.4 |
| Local Regulatory Start-up Representative (LRSU Rep) | 6.1, 6.3, 6.4, 6.5, 6.6 |
| Local Site Identification Representative (LSID Rep) | 6.1, 6.2, 6.3 |
| Operational Team Lead (OTL) | 6.1 |
| Regulatory Advisor (RAd) | 6.1, 6.5 |
| Site Activation Manager (SAM) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6 |

## Notes applicable to this OP and its Associated Work Instructions (WIs):

- Within this OP and its related WIs, steps are intended to be performed by individuals fulfilling the roles specified in Section 3.0 Roles and Responsibilities and in the Who columns within the subsections of section 6.0 Procedures. However, responsibility for a step(s) can be delegated to an individual who is not fulfilling that specific role as long as that delegate is qualified by education, training, and/or experience to perform the step

- Records of who fulfills each role should be maintained (e.g., in project team contact lists, organization charts, etc.)

- A single individual may fulfill multiple roles, except where it is indicated that a step needs to be performed by an independent person (e.g., in the case of independent quality control)

- Any required records associated with a step need to identify the individual(s) who performed the step, regardless of whether the step was delegated (e.g., author of operational plan)

Page 1 of 21

Copyright © 2019 -- 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

- Centralized RSU (cRSU) may be involved in performing and/or coordinating certain activities described in this SOP and its associated work instructions that are not shown as assigned for cRSU. Please refer to CS_OP_RSU0061, Centralized RSU Scope of Activities

- For projects where no SAM is assigned, the CL performs the tasks assigned to the SAM

# DEFINITIONS

Refer QG_OD_SMT0018, Glossary of Terms – Clinical Services for definitions.

Site Ready to Enroll (SRtE) Activities: All activities required by the Sponsor and study Protocol for an Investigator site to be approved for Site Activation and ready to enroll subjects.

Site Activation: Milestone indicating the site is ready to enroll subjects. Pre-requisites for Site Activation include: Investigator site’s Essential Document Pack (EDP) is approved, Investigator site has been approved for Investigational Product (IP) release, Investigator site staff is fully trained to follow Protocol procedures, the SIV has occurred, and all site ready to enroll activities have been completed.”

Site Activation Management Plan (SAMP): Planning document that details specific activities covered in Site Activation, including but not limited to: project/country/site strategy, Investigator site identification and selection strategy, project specific roles and responsibilities, project specific parameters, Site Activation Negotiation Tactics, templates (including location of templates), regulatory and ethics submission strategy, SRtE requirements and project document tracking requirements for applicable systems.

Trial Management System: When referencing “Trial Management System” throughout this OP, this infers tracking directly into CTMS or other IQVIA trial management systems.

CTIS (Clinical Trials Information System): A dedicated EU Portal and database for submitting information and management of clinical trial business processes throughout lifecycle for studies conducted under EU CTR.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

The process steps in this procedure must be followed to verify the consistency and reliability of the IQVIA Site Activation process. Sections 6.2 through 6.6 are applicable when IQVIA is contracted to perform the respective Site Activation phase(s).

Before beginning Site Activation activities, ensure that an executed contract between IQVIA and Sponsor is in place as per “Policy for Requirement of Comprehensive Agreement Prior To Site Activation_Final” (refer to Section 7.33 in this OP).

As per applicable local regulations, scanned or electronic signatures from an Investigator site and IQVIA are acceptable when IQVIA is the contracting party or when the Sponsor (as the contracting party) has approved the use of scanned or electronic signatures.

In addition, each role mentioned in this OP is responsible to:

- Ensure tracking, status reporting, risk/issue identification and mitigation of activities to support Site Activation in applicable systems.

- File individual documents or pertinent correspondence in the Trial Master File (TMF) as they are finalized as per Step 6.1.8.

Note: All activities and aligned steps are dependent on available resources.

## Strategic Planning and Project Oversight

Strategic planning is a key element of the Site Activation process that supports the identification and inclusion of required resources, tasks, deliverables, and milestones required for the project.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | GSID Lead | Confirms Site Identification and Selection process - Confirms the participating countries and number of Investigator sites with the Project Leader (PL) - Schedules the Knowledge Transfer Call (KTC) attended by PL, Therapeutic Strategy Lead, SA Lead, Feasibility Analytics Lead (if applicable), Analytic Strategy Lead, Decentralized Clinical Trial Lead (DCTL) Therapeutic Medical Advisor (TMA) or Medical Strategy Lead (MSL), Operational Deployment Lead, Global Strategy Manager, CL and SAM, if assigned. | Project Setup |
| 6.1.2 | SAM/CL | Verifies Allocation of Site Activation Resources Verifies that all Site Activation resources required for the project are assigned based upon the Scope of Work (SOW). | Throughout Site Activation process |
| 6.1.3 | SAM | Develops Site Activation Management Plan (SAMP), Site Ready to Enroll (SRtE) requirments and Table of Regulatory Responsibilities (TRR) - Partners with project team members to define Site Activation requirements, templates and guidelines based on Sponsor, project specifics, and scope of work (SOW). - Identifies and confirms, with input from CL, PL/Project Vendor Manager (PVM), CML and Data Team Lead (DTL) the critical path to Site Activation. Confirms with CL and PL/PVM that the project specific Clinical Operations Plan (COP) and Vendor Management Plan (VMP)includes detailed execution to support the plan and triggers . | Following approved project strategy and prior to Stage Gate Review 2 |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Creates the project specific CS_TP_RSU0013, Site Activation Management Plan (SAMP), SRtE checklist requirements, and CS_TP_RSU0023, Table of Regulatory Responsibilities (TRR). - Documents in the SAMP any decisions regarding submission strategy, such as those relating to use of country level or harmonized approaches under the European Union (EU) Clinical Trial Regulation (CTR). - Defines in the SAMP the Customer expectations for document redaction or deferral of publication in relation to clinical trial transparency obligations in countries or regions where clinical trial documents are made publicly available (e.g. in relation to clinical trial application sperformed under the requirments of the EU CTR). Note: The first version of the TRR must be approved before the first submission that IQVIA performs outside the United States (US). Refer to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications for more detail on requirements (e.g., for regions like the US where a TORO is used instead of the TRR) and timing of TRR finalization. |  |
| 6.1.4 | SAM | Customizes required templates necessary to execute Site Activation activities. | Following approved project strategy and throughout Site Activation process |
| 6.1.5 | OTLs | Ensures applicable plans detail day-to-day execution of the SAMP as appropriate. |  |
| 6.1.6 |  | Ensures tracking, status reporting, risk/issue identification and mitigation of activities to support Site Activation in applicable Trial Management systems. | Throughout Site Activation process |
| 6.1.7 | SAM | Directs Site Activation per plan and Status Reporting of Milestones - Monitors execution of the SAMP and reports progress toward agreed Site Activation milestones. - Maintains ongoing risk/issue identification and mitigation. |  |
| 6.1.8 | All Roles in section 3.0 | Files Individual Documents or Relevant Correspondence in the TMF as they are Finalized Working Document: Any document not yet finalized as defined below needs to be appropriately identified as a working document as described in the SAMP or other project instruction. Final Document: A document is considered final when: - The document has been received at IQVIA, reviewed internally, and meets the required criteria, and | Throughout Site Activation process and the Project Lifecycle |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - The document has been reviewed and approved by the sponsor, if required, and - The document has been reviewed and meets criteria to submit to the Regulatory Authorities (RA), Independent Ethic committees (IEC), Institutional Review Board (IRB), if required. Final versions of documents are identified by a whole number (e.g. Version 1.0, 2.0) as described in CS_WI_RM0284, General and Trial Master File (TMF)-Specific Document Quality - Good Documentation Practices. When a final document is subsequently revised, the revision is then considered a “Working Document” until finalized as defined above. Note: Once the document is considered final this is the date that is used to drive the TMF Wingspan timeliness metric, the final document date is the date used in TMF for filling. The final document must be in the TMF placeholder within 30 days of the final document date. Manages all documents, throughout the Site Activation process and project lifecycle, as described in CS_WI_RM0284. Files all final project documents and relevant email correspondence in “real time” as they are finalized according to the definitions above and the following as applicable: - TMF platform-specific OP and WIs in the TMF folder in eSOP: - CS_OP_TMF0007 Trial Master File (TMF) - CS_WI_TMF0001, Trial Master File (TMF) - IQVIA eTMF (Wingspan) - CS_WI_TMF0002, Trial Master File (TMF) - Customer eTMF - CS_WI_TMF0003, Trial Master File (TMF) - Paper TMF - CS_WI_TMF0004, Trial Master File (TMF) - ELVIS DIA eTMF - CS_WI_TMF0005, Trial Master File (TMF) - Single-service Projects - CS_WI_TMF0006, Trial Master File (TMF) - ELVIS pre- DIA eTMF - Or Sponsor equivalent filing plan/tool. |  |

## Site Identification

This section of the OP describes the Site Identification process. Refer to CS_WI_RSU0065 Site Identification and Selection for full details.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | GSID Lead | Confirms Site Identification and Selection process Confirms and/or updates the pre-award strategy during the KTC, with support of KTC checklist. Ensures the project team understands the country strategy and site/Investigator profiling. | Following Project Award |
| 6.2.2 | SA Lead | Generates Tiered Site List Creates Tiered Site List based on the Investigator site identification strategy including Sponsor mandated Investigator sites. | Post Award, following KTC |
| 6.2.3 | GSID Lead | Confirms Qualifying Sites for Optimized Site ID and Selection Confirms qualifying top tiered (Tier 1 & HP + Tier Prime) Sites enabled by CORE Powered Site Investigator data. | Following Tiered Site List |
| 6.2.4 |  | Prepares and Conducts Site ID Vetting Instructions Meeting (VIM) Prepares VIM along with input from SA Lead to provide instructions to all LSID Reps with information required to vet Tiered Site List against all key strategy components. |  |
| 6.2.5 | LSID Rep | Performs Local Vetting of Potential Sites Receives Tiered Site List and refines the listing based on local intelligence and vetting guidelines, identifying the Investigators and sites to be included in the final Vetted Site List. |  |
| 6.2.6 | GSID Lead | Authorizes Final Vetted Site List Documents authorization of the final Vetted Site List using the appropriate Trial Management System, obtaining internal stakeholder review. | Following Vetted Tiered Site List |
| 6.2.7 |  | Conducts Site ID Vetting results and Study Expectations Meeting (SEM) Conducts the SEM with SAM. GSID Lead will focus on Investigator site strategy, Investigator site profile and tiering methodology with all assigned LSID Reps. SAM will focus on Sponsor specific processes, documents, templates, and escalation requirements. | Following Vetted Tiered Site List, prior to site list distribution to Sponsor |
| 6.2.8 | SAM | Sponsor authorization of Final Vetted Site List Sends to Sponsor for authorization if required. | Following Vetted Tiered Site List |
| 6.2.9 | LSID Rep | Promotes Vetted Sites to the Selection Phase Promotes Investigators to the Protocol Country list in applicable Trial Management System. | Following Final Vetted Site List |

## Site Selection

This section of the OP describes the Site Selection process. Refer to CS_WI_RSU0065, Site Identification and Selection for full details.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | SAM | Confirms Confidentiality Requirements - Confirms Confidentiality Disclosure Agreement (CDA) requirements in consultation with Sponsor. If executed CDAs are not in place, confirms the appropriate CDA template and fallback language (if applicable) to be used. - If a CDA is not required or is already executed (e.g. Master CDA), proceed to next step. | Following Project Award |
| 6.3.2 | GSID Lead | Creates Site Selection Questionnaire (SSQ) - Creates project-specific CS_TP_RSU0063, Site Selection Questionnaire, and annotated SSQ. - Consults with CL to ensure relevant questions about clinical supplies and equipment needed at the Investigator sites are included in the SSQ as per CS_WI_SM0027, Provision of Clinical Project Supplies and Equipment to Investigator Sites. - Finalizes SSQ documents and provides to the SAM and LSID Reps. Note: PL is responsible for obtaining Sponsor approval of the SSQ if required, prior to distribution to the SAM and LSID Reps. | Following Site ID Strategy |
| 6.3.3 | SAM | Creates the Project Specific Selection, Non-Selection and Back-up Letters Templates Creates the project specific letter templates using CS_TP_RSU0004, Site Selection and Non-Selection Letter, in collaboration with CL. Distributes the letter templates to LRSU Rep. Note: CL to provide Investigator site specific details required for letter if needed. | Following Project Award |
| 6.3.4 | LSID Rep | Contacts Sites for Selection - Approaches promoted Investigator sites to confirm their interest in participating in the study, in line with confidentiality requirements. - Distributes the SSQ to the Investigator sites for verification and completion. | Following Final Tiered Site List |
| 6.3.5 |  | Evaluates Site Responses - Obtains completed SSQ and evaluates Investigator site responses based on the requirements contained in the annotated SSQ, contacting Investigator sites for clarification as needed. | Throughout Site Selection |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Approves or rejects the Investigator site as a potential candidate. If Site Selection Visit (SSV) is not applicable (e.g. a tier 1 site as part of the Optimized Site Identification and Selection Process) proceed to Step 6.3.7. Track as required in Trial Management System |  |
| 6.3.6 | CL | Verifies Site Selection Visit (SSV) Completion Verifies that SSV and the SSV Report have been completed in accordance with CS_WI_SM0005, Monitoring Visits. | Following Monitor Resource Request |
| 6.3.7 |  | Evaluates Sites for Final Selection - Determines, based on Monitor recommendation after SSV, if the Investigator site qualifies for inclusion in the study. - Updates the site’s status accordingly within the Trial Management System to whether the site is “Selected”, “Not Selected”, or will serve as a “Back-up” site. | Throughout Site Selection |
| 6.3.8 | LSID Rep | Hands over sites to LRSU Rep Provides all relevant documents (e.g., SSQ and CDA) and site information to the LRSU Rep, as applicable. |  |
| 6.3.9 | LRSU Rep | Notifies Sites of Selection, Non-Selection, or Back-up Status - Notifies the Investigator site using the project specific letter template. For selected Investigator sites also obtains key Investigator site details using CS_TP_RSU0082, Site Ready to Enroll Site Contact Form. - Tracks Planned SSU Completion Date (PCD) and Planned Site Ready to Enroll Date in Trial Management System. | Throughout Site Selection |

## Clinical Trial Agreements and Site Contracting

This section of the OP describes the process related to Clinical Trial Agreements (CTA) and Site Contracting required for Site Activation. Refer to CS_WI_RSU0066, Clinical Trial Agreement and Budget.

In accordance with International Council for Harmonization of Technical Requirements for Pharmaceuticals for Human Use – Good Clinical Practice (ICH- GCP) (refer to Section 7.35 in this OP), Investigators must be provided with the Protocol and Investigator’s Brochure (IB) before signing a CTA to conduct the study.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | CBSL | Develops Global CTA Template Develops, negotiates, and finalizes global CTA templates, associated ancillary templates, and negotiation parameters in accordance with IQVIA and Sponsor-agreed CTA guidelines. | Following Project Award |
| 6.4.2 |  | Develops Country CTA Templates |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Utilizing the global CTA templates, develops, negotiates and finalizes Country CTA templates and associated ancillary templates in accordance with IQVIA and Sponsor-agreed CTA guidelines. - For those countries that commonly utilize Investigator site specific or government mandated templates, guidance of CTA guidelines for inclusion will be provided. |  |
| 6.4.3 | CBSL | Determines Accountability for Budget Calculations If IQVIA is scoped to perform Protocol pricing, proceed to Step 6.4.4. If the Sponsor is preparing Protocol pricing, proceed to Step 6.4.5 | Following Project Award |
| 6.4.4 |  | Develops Protocol Pricing Budget and Payment Schedule (if in scope for IQVIA) Develops, negotiates and finalizes the Protocol pricing budget template and parameters according to: - Appendix C: Policy on Compensation to Healthcare Professionals for Clinical Research Services - CS_WI_SM0028, Investigator Payments - PL and TMA’s interpretation of the Protocol, procedures and complexity - Sponsor’s investigator budget strategy - GrantPlan data up to the 90th percentile for Fair Market Value (FMV) compliance |  |
| 6.4.5 |  | Sponsor Provided Protocol Pricing Budget: Obtains Master Budget and Payment Schedule from Sponsor Obtains final Protocol pricing budget and payment schedule for all participating countries and negotiation parameters from the Sponsor | Following Final Protocol |
| 6.4.6 | LRSU Rep | Translate Final Country CTA and Ancillary Templates and Budget and Payment Schedule (as required) Translates documents, as required, in accordance with CS_WI_RSU0032, Translation of Documents. | Following Final CTA Country Templates, Budget, and Payment Schedule |
| 6.4.7 | CBSL | Conducts Training for Project Specific CTA Budget and Payment Schedule Templates. Negotiation Parameters and Sponsor Contracting Strategy and Processes. Prepares training materials and conducts training on project specific CTA, budget and payment schedule templates, negotiation parameters and Sponsor contracting strategy, processes, and expectations. |  |
| 6.4.8 | Local Contract Negotiator | Negotiates CTA and Budget with Sites Negotiates CTA terms and conditions, applicable ancillary agreements, budget, and payment schedule with the relevant |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Investigator site contacts, according to the CTA Training, project- specific guidance, and negotiation parameters. |  |
| 6.4.9 | Local Contract Negotiator | Executes CTA and Budget - Generates Global Contracting QC Form or applicable Sponsor QC Form. - Generates the appropriate number of final versions (or utilizes electronic signature software, as applicable) of the CTA, routes to all parties for signature, receives executed contracts and verifies no additional changes have been made and all applicable signatures and dates are present. | Following Approved by all parties the Investigator site- specific CTA and Budget |
| 6.4.10 | CBSL, LRSU Rep, Local Contract Negotiator | Manages Contract Amendments Produces the updated and executed CTA amendment documents by re-tracing steps 6.4.2 through 6.4.10 as applicable, if an amendment to the current executed CTA is requested. | As requested throughout the lifetime of the project |

## Regulatory and Ethics Committee Submission

This section of the OP describes the process related to the initial RA/IEC/IRB submissions and any additional submissions (e.g. radiation committees, biobanks, etc.) relevant for Site Activation requirements, if IQVIA is contracted on behalf of a Sponsor. Refer to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | SAM | Gathers Regulatory Intelligence and Submission Documents Requirements Consults with RAd and LRSU Rep, collates Regulatory intelligence and develops core and country specific submission document requirements based on Protocol, SOW and TRR. Note: - Any contracted RA/IEC/IRB and/or Competent Authority (e.g. radiation committees, biobanks, etc.) submissions should be clearly documented in the SOW and the TRR. - The RAd will collate Regulatory Intelligence and develop document requirements for submissions in the EU under the EU CTR. | Following country list finalization |
| 6.5.2 |  | Defines the Essential Documents; Finalizes the SAMP and Essential Documents Pack – Requirements Form (EDP-RF) - Defines the Essential Documents for the project and finalizes the SAMP and EDP-RF including any applicable Quality Control (QC). Includes the Essential Documents elements and submission requirements in the SAMP. Also Refer to CS_WI_RSU0021, Essential Documents Pack, and CS_WI_RSU0022, Collection of Financial Disclosure Information from Investigator Sites |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Shares finalized CS_FM_RSU0047, Essential Documents Pack – Requirements Form (EDP-RF) and SAMP with LRSU Rep. |  |
| 6.5.3 | SAM/LRSU Rep/ML | US FDA Investigational New Drug (IND) Investigator Information Package Coordinates submission to Sponsor/delegate of US FDA IND Investigator Information Package for all applicable Investigator sites in countries subject to IND Regulations. | Startup and Conduct, when study is under a US FDA IND |
| 6.5.4 | SAM | Obtains CT Application Dossier Documents Obtains required documents for the Core CT application dossier that are being provided by the Sponsor/delegate. Tracks and files documents in appropriate Trial Management System. | During Startup or upon amendment |
| 6.5.5 | RAd | Delegation Letters Prepares and finalizes Delegation Letters for all countries per SOW in collaboration with SAM, PL and LRSU Rep. Provides instructions for finalization to Sponsor and ensures finalized Delegation Letters are forwarded to appropriate LRSU Rep per country. | During start-up after country finalization |
| 6.5.6 |  | EU Clinical Trial Number and EU Clinical Trial Application System - Requests the number required for initiation of an EU CT Application (or works with Sponsor, per SOW). - Establishes appropriate access to the EU CTIS where required, for studies being conducted under EU CTR. - Oversees provision of project specific access to other IQVIA users who require access, per project scope. | While draft Core CT application is being prepared |
| 6.5.7 |  | Finalizes Core CT Application Dossier - Finalizes Core CT application dossier. - Reviews IP labels, master Informed Consent Form (ICF) and subject recruitment material as applicable per SOW. (Refer to CS_WI_RSU0019, Investigational Product Label Review; CS_WI_RSU0033, Creation and Review of the Informed Consent Form; and CS_TP_RSU0034, Regulatory Review Checklist for Subject Recruitment Material) - Performs a review of core CTA dossier including any technical reviews of individual documents per SOW according to applicable processes/WIs. - Obtains a completed QC review of the dossier with the assigned SAM reviewer and/or Sponsor level approval as applicable. | Following Draft IP Labels, ICFs and Recruitment Material |
| 6.5.8 |  | Compiles the EU-specific Part I Dossier Compiles the Part I dossier in accordance with the core CT dossier and submits the Part I dossier via EU CTIS, where required for clinical trials being conducted under EU CTR in the EU. | Following Final Core CT Application Dossier |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.9 |  | Monitors Submission Status, Facilitates Responses - Routinely monitors submission status, facilitates responses to requests for information and corrections requested by the EU Member State (MS) authorities within the CTIS in consultation with SAM, PL, and Sponsor. - Documents communications and informs relevant stakeholders of the outcome of review procedure including provision of required responses/documents in response to conditional approvals. - Files any documents and correspondence into relevant areas of TMF and updates applicable tracking systems of the approval or rejection including completing any required follow-up actions. | Throughout Activation Process |
| 6.5.10 | SAM/RAd | Files Core documents into the TMF as per Step 6.1.8 | Documents are considered final |
| 6.5.11 | LRSU Rep | Compiles the Country/Site CT Application - Compiles the country/site CT application dossier for submission to RA/IEC/IRB in accordance with Core CT Application Dossier, local Regulatory requirements, and project specific SAMP. - Performs activities associated with the preparation and submission of the Part II dossier, within the CTIS (for studies being conducted under EU CTR in the EU) Note: - The RAd will support LRSU Rep in the compilation of the country- level Part II clinical trial application in the EU under the EU CTR. - SAM is responsible for the compilation and submission of the required documentation in North American when a Central Institutional Review Board (IRB) is used for the project. | Following Approved Core CT Application Dossier |
| 6.5.12 |  | Translates documents as applicable in accordance with CS_WI_RSU0032. | During compilation of Country / Site CT Application Dossier |
| 6.5.13 |  | Ensures a QC Review of the CT Application Dossier - Ensures a QC review of the CT application dossier is conducted by an independent LRSU Rep reviewer to verify accuracy and completeness. Any deviations should be recorded in accordance with country specific WIs. - Obtains Sponsor-level approval of the dossier, if required per Sponsor specifications(in consultation with SAM). | Prior to the submission of the Country / Site CT Application Dossier |
| 6.5.14 |  | Submits Country/Site CT Application Dossier - Submits country/site CT application dossier. Verifies that all local submission fees are paid and submits Country/Site CT Application Dossier to the relevant RA/IEC/IRB for approval. If sites are required to submit documents to the EC directly, provides the | After QC of Country / Site CT Application Dossier |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | relevant documents to Investigator site representatives for submission. - If Sponsor mandates the distribution of controlled regulatory documents and the documents are not tracked in the Trial Management system, refer to CS_TP_SM0071, Clinical Study Document Tracking Log. Note: SAM is responsible for the compilation and submission of the required documentation in North American when a Central IRB is used for the project. |  |
| 6.5.15 | LRSU Rep | Monitors Submission Status, Facilitates Responses - Routinely monitors submission status, facilitates responses to requests for information and corrections requested by the RA/IEC/IRB in consultation with SAM, RAd, PL and Sponsor. - If the trial involves countries where the EU CTR is applicable, monitors Request for Information (RFI) receipts for Part II dossier, prepares responses and uploads documents to CTIS, completes the response submission in CTIS. - Documents communications and informs relevant stakeholders of the outcome of review procedure including provision of required responses/documents in response to conditional approvals. - Files documents and correspondence into relevant areas of TMF and updates applicable tracking systems of the approval or rejection including completing any required follow-up actions. | Throughout Activation Process |
| 6.5.16 |  | Files Country and Site documents into the TMF as per Step 6.1.8 | Documents are considered final |

## Site Activation Approval and Transfer

The section of the OP describes the process of Site Ready to Enroll Execution and Oversight required for Site Activation. Refer to CS_WI_RSU0068 Site Ready to Enroll Execution and Oversight.

Site Activation is dependent on the completion of the requirements outlined in the SAMP.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | SAM | - Monitors execution and timelines of the SAMP and progress to agreed Site Activation Milestones. - Verifies the completion of EDP and additional SRtE criteria captured in the project-specific SRtE Checklist. | Throughout Site Activation |
| 6.6.2 | LRSU Rep | Confirms the completion of SRtE requirements per criteria outlined in the SAMP, after CML completes initial triggers for automated system accesses, Investigator site training, and equipment shipment |  |
| 6.6.3 | SAM | Obtains confirmation from LRSU Rep and Centralized Monitoring Lead (CML) that all activities per the SRtE requirements are completed. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.4 |  | - Completes and signs the CS_FM_RSU0048, Site Activation Approval Form (SAAF). - Notifies the CL and Monitor in writing when the Investigator site is approved for IP Release, SIV and/or Site Activation. Sends the signed SAAF to the CL and Monitor. Ensures all signed versions of the SAAF are filed in the TMF. - Enters “SIV Approval Date” and “Authorization for Site Activation” in applicable Trial Management System at the time of SAAF signature for approved activities as described in Trial Management System Guidance Documents. | After all Site Activation requirements have been met |
| 6.6.5 | CL | - Activates Investigator site and informs SAM that Investigator site has been activated. - Confirms site status of “Enrollment Open” is tracked in applicable Trial Management System by Monitor/CML as described in Trial Management System Guidance Documents. | After the SAAF is signed |
| 6.6.6 | LRSU Rep | Tracks SRtE date in applicable Trial Management System as described in Trial Management System Guidance Documents | After confirmation from SAM that Site Activation has occurred |
| 6.6.7 |  | Completes Site Information Transfer from RSU to Clinical Teams - Completes Transfer of Information on Site Documents by signing LRSU – Site Transfer tab in CS_TP_RSU0040, RSU Country and Site Transfer Checklist and files in the TMF. - Enters the date of the transfer in applicable Trial Management System. | Upon completion of SRtE activities |
| 6.6.8 | SAM | - Runs the Trial Management System report to confirm that the transfer process is complete. - Confirms TMF filing of the signed LRSU – Site Transfer tab from the Transfer Checklist. Note: If the transfer process is not completed as required, or if the signed LRSU-Site Transfer tab from the Transfer Checklist is not filed in the TMF within the required timelines (refer to CS_OP_TMF0007 Trial Master File (TMF) and its associated WIs) follows up with LRSU Rep until completion of the transfer process and filing has occurred. If needed, escalates to the LRSU Rep’s Line Manager. |  |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| 7.2 CS_OP_RSU0061 | Centralized RSU Scope of Activities |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.3 CS_TP_RSU0013 | Site Activation Management Plan |
| 7.4 CS_TP_RSU0023 | Table of Regulatory Responsibilities |
| 7.5 CS_WI_RSU0067 | Project Lifecycle Clinical Trial Applications |
| 7.6 CS_WI_RM0284 | General and Trial Master File (TMF)-Specific Document Quality - Good Documentation Practices |
| 7.7 CS_OP_TMF0007 | Trial Master File (TMF) |
| 7.8 CS_WI_TMF0001 | Trial Master File (TMF) - IQVIA eTMF (Wingspan) |
| 7.9 CS_WI_TMF0002 | Trial Master File (TMF) - Customer eTMF |
| 7.10 CS_WI_TMF0003 | Trial Master File (TMF) - Paper TMF |
| 7.11 CS_WI_TMF0004 | Trial Master File (TMF) - ELVIS DIA eTMF |
| 7.12 CS_WI_TMF0005 | Trial Master File (TMF) - Single-service Projects |
| 7.13 CS_WI_TMF0006 | Trial Master File (TMF) - ELVIS pre-DIA eTMF |
| 7.14 CS_WI_RSU0065 | Site Identification and Selection |
| 7.15 CS_TP_RSU0063 | Site Selection Questionnaire |
| 7.16 CS_WI_SM0027 | Provision of Clinical Project Supplies and Equipment to Investigator Sites |
| 7.17 CS_TP_RSU0004 | Site Selection and Non-Selection Letter |
| 7.18 CS_WI_SM0005 | Monitoring Visits |
| 7.19 CS_TP_RSU0082 | Site Ready to Enroll Site Contact Form |
| 7.20 CS_WI_RSU0066 | Clinical Trial Agreement and Budget |
| 7.21 CS_WI_SM0028 | Investigator Payments |
| 7.22 CS_WI_RSU0032 | Translation of Documents |
| 7.23 CS_WI_RSU0021 | Essential Documents Pack |
| 7.24 CS_WI_RSU0022 | Collection of Financial Disclosure Information from Investigator Sites |
| 7.25 CS_FM_RSU0047 | Essential Documents Pack - Requirements Form |
| 7.26 CS_WI_RSU0019 | Investigational Product Label Review |
| 7.27 CS_WI_RSU0033 | Creation and Review of the Informed Consent Form |
| 7.28 CS_TP_RSU0034 | Regulatory Review Checklist for Subject Recruitment Material |
| 7.29 CS_TP_SM0071 | Clinical Study Document Tracking Log |
| 7.30 CS_WI_RSU0068 | Site Ready to Enroll Execution and Oversight |
| 7.31 CS_FM_RSU0048 | Site Activation Approval Form |
| 7.32 CS_TP_RSU0040 | RSU Country and Site Transfer Checklist |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.33 QCP_CP_BE0013 | IQVIA Corporate Policy Healthcare Professionals and Government Officials |
| External References |  |
| 7.34 IQVIA Comprehensive Agreement Policy | Policy for Requirement of Comprehensive Agreement Prior To Site Activation_Final |
| 7.35 IQVIA Site Overage Policy | Guidance to ensure that target number of sites are initiated by including 15% overage during Site ID. |
| 7.36 ICH-GCP: E6 R2 | International Council for Harmonization of Technical Requirements for Pharmaceutical for Human Use (ICH), E6: Good Clinical Practice (GCP) |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_OP_RSU0060 | Site Activation | 5 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added bullets to rows with multiple steps | Throughout | Consistency with formatting in other SOP documents |
| Added OTL, removed PL | 3.0 | Change in “who” columns within document |
| Updated SRtE Activities definition | 4.0 | Updated to match the definition used in the SRtE WI |
| Updated Site Activation definition | 4.0 | Provide clarity |
| Added CTIS definition | 4.0 | New system that will be used with introduction of the EU CTR |
| Removed PL step | Old 6.1.1 | Removed first step as it was a duplication from another SOP, and unnecessary to this document |
| Updated GSID Lead step | New 6.1.1 | Updated the GSID Lead step to include some text from the removed PL |
| Updated text to clarify SAM activities, added reference to SRtE activities, updated roles in the notes (e.g. PIM to PVM), moved “action words” to the beginning of sentences in the | 6.1.3 | Provide clarity, update to current role terms, information on new EU CTR requirements and consistency with formatting in other SOPs |

| Notes. Added text related to redaction of documents under EU CTR |  |  |
| --- | --- | --- |
| PL replaced by GSID Lead; text updated to accurately reflect the GSID Lead responsibility | 6.2.1 | The PL’s role in confirming Site ID strategy is covered in other documents. |
| Changed SAM to GSID Lead for confirming qualifying sites | 6.2.3 | Clarify process |
| Inserted two steps regarding authorization of final vetted site list and the Study Expectations Meeting | New 6.2.6 and 6.2.7 | Clarify process |
| Changed GSID Lead to SAM | Old 6.2.5, new 6.2.8 | SAM is responsible for communicating with Sponsor |
| Added “if applicable” for fallback language and “Master” to explain “mCDA” | 6.3.1 | Clarify process |
| GSID Lead provides SSQ directly to LSID Rep instead of only to SAM | 6.3.2 | Simplify process |
| Added example | 6.3.4 | Clarify process |
| Added “project specific letter template”, updated SM0073 to RSU0082, and added instruction for what needs to be tracked in the Trial Management System | 6.3.8 | Clarify process and correct SOP reference |
| Added note: “The Rad will collate Regulatory Intelligence and develop document requirements for submissions in the EU under the EU CTR”. | 6.5.1 | Change to process due to EU CTR |
| Updated “when” to remove SAMP | 6.5.1 | The SAMP is not finalized until the next step |
| Corrected SAM responsibilities and deleted the steps in 6.5.3 and 6.5.4 | 6.5.2 | Clarify process, remove some duplication, and shorten SOP |
| Changed text to show that the “submission” is to the Sponsor/delegate and NOT to the US FDA | 6.5.3 | Clarify responsibility |
| Updated text to reflect EU CTR changes | 6.5.6 | Change to process due to EU CTR |

| Added title to step | 6.5.7 | Clarify process |
| --- | --- | --- |
| Updated text due to EU CTR changes | 6.5.8, 6.5.9 | Change to process due to EU CTR |
| Removed SAM from “who”, added changes due to EU CTR, added notes to clarify RAd support of LRSU Rep and SAM’s responsibility in North America | 6.5.11 and 6.5.14 | Clarify responsibility |
| Modified text to move “action” words first | 6.5.13 | Consistency with formatting in other SOP documents |
| Added EU CTR text | 6.5.15 | Change to process due to EU CTR |
| Changed “Handover” to “Transfer” | Throughout 6.6 | Process change |
| Inserted new row to clarify LRSU Rep responsibilities | 6.6.2 | Process change |
| Removed “CL” from “who” column as they are no longer responsible for this step | 6.6.3 | Process change |
| Removed “Ready to Enroll date and that” from text | 6.6.5 | Process change |
| Inserted LRSU Rep responsibilities to track SRtE date | 6.6.6 | Process change |
| Changes to text regarding filing and what date is entered into the Trial Management System, updated “when” column | 6.6.7 | Provide clarity |
| Removed Appendix B and changed Appendix C to “Appendix B” | 10.0 | Appendix B is already found in CS_WI_RSU0067 and does not need to be repeated here. |

- APPENDICES

  - Appendix A: Sharing information from Site Lists with the Sponsor

  - Appendix B: Policy on Compensation to Healthcare Professionals for Clinical Research Services

Appendix A: Sharing Information from Site Lists with the Sponsor

    - Pre-award: Limited information may be shared with the Sponsor after approval from Site Analytics Leadership. The amount shared is limited because it represents components of a proposed strategy which could be used by a competitor if the project is not awarded to IQVIA.

    - Project Award: The following information may be shared with a Sponsor from a Vetted Site List:

      - Country / Site name / Investigator last name / Investigator first name / Email address / State / City / Address / patient volume (only as high/medium/low) / confirmation that Investigator/site participated in previous trial with the same Sponsor, but without any reference to rankings. It must not be presented in a ranked-list format (following data privacy guidelines)

      - Weight added to each data attribute for the site strategy, for example. 20% on partner status, 25% on delivery tier etc.

      - Other information may be shared with the Sponsor with Site Analytics Leadership approval and guidance (for example: certain aggregated data, following data privacy guidelines)

    - Additional clarification:

      - We should not share information from an unvetted site list (as we always want to ensure local knowledge of Investigator/sites is applied before sharing a list with Sponsor).

      - The above information must not be shared with a 3rd party or other CRO without Site Analytics Leadership approval because it represents proprietary information or key components

    - The following information must never be shared with anyone outside of IQVIA as it represents either proprietary intellectual property or would hinder adherence to data privacy guidelines:

      - Any site performance data or information (enrolment factors, timelines, etc.)

      - Individual site of Investigator quality of performance tiers (for example, Dr. Smith: Delivery Tier 3, Quality Tier 4)

      - Algorithms or formulas behind the site tiering models. This includes the formulas we use to normalise data across countries as well as how the individual quality and delivery tiers are calculated

## Appendix B: Policy on Compensation to Healthcare Professionals for Clinical Research Services

This policy sets forth IQVIA’s standards with respect to compensation of health care professionals (HCPs) and/or their health care institutions for conducting clinical research.

Compensation to HCPs and/or their health care institutions must be reasonable in amount and tied to specific services provided by the HCPs and/or their health care institutions for which there is a legitimate business need.

Any compensation to HCPs and/or their institutions for conducting clinical trials must be set forth explicitly in an agreement which specifies the clinical trial services which are the basis for payment. Any exceptions must be approved by the Global Legal Department.

The amount of compensation should be based on fair market value (FMV) determinations. The FMV determination should be made using benchmark data on compensation recently paid for similar clinical studies sponsored by the pharmaceutical/biotechnology industry in the country where the research is conducted (such as data from GrantPlan®, Grants Manager® or other similar databases). The rate of compensation may vary depending on the specific facts and circumstances of the particular study and research site. In determining FMV compensation, and in applying the benchmark data, factors such as the following should be considered in order to determine fair budgets:

    - Complexity of the required services or procedures;

    - Anticipated recruitment challenges;

    - Time commitment required by the HCP or HCP/Institution staff;

    - Experience, reputation, and qualifications of the HCP or institution;

    - Inflation factors;

    - Demand for the particular HCP’s or institution’s services;

    - Location of the HCP or institution;

    - Institution infrastructure needed to execute the services; and

    - Published institution rates and fees.

When enrollment or retention in a trial is particularly challenging, reasonable additional payment may be made to compensate the HCP or institution for time and effort spent on extra work to enroll qualified research participants. For example, payment may be provided for additional study coordinator or other resource needed to perform chart reviews or to conduct patient outreach, or for additional expenses such as advertising costs.

Additional fees for achievement of subject enrollment goals within a specified time must be reviewed and approved by the Fair Market Value (FMV) Legal Liaison as set forth in Site Fee Committee – Responsibilities, below.

## Prohibited Payments

Compensation to HCPs and/or their institutions shall not: Be tied to the outcome of clinical studies;

Be in the form of Sponsor company stock or stock options; or

Be for the referral of patients (whether by the provision of patient lists or otherwise). For the avoidance of doubt, payments can be made for work performed (such as medical chart reviews) to identify potential patients.

This policy does not relieve HCPs of their financial disclosure and other responsibilities with respect to actual or potential conflicts of interest.

## Site Fee Committee – Responsibilities

When IQVIA is scoped with building the clinical site budgets, IQVIA’s documented processes for building clinical site budgets will be followed. Where, according to IQVIA’s documented processes, FMV Legal Liaison review is required, the FMV Legal Liaison is authorized to approve budgets with appropriate support up to the GrantPlan 100th percentile.

Proposed budgets that are unresolved within the authority of the FMV Legal Liaison will be presented by the FMV Legal Liaison to the Site Fee Committee (SFC). The SFC will have representation from the Global Legal Department (Legal), the Ethics and Compliance Office (ECO), and the Chief Medical and Scientific Office (CMSO). The SFC will establish a standing meeting or operate via e-mail correspondence, as appropriate to support operational requirements in a timely manner. The SFC is empowered to establish additional clinical site budget or payment matters that require escalation to the SFC. Decisions by the SFC will be final with no further internal escalation.

## Related Policies

Refer to QCP_CP_BE0013, Healthcare Professionals and Government Officials.

Page 21 of 21

Copyright © 2019 -- 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Neilson, Irene (q731875) Title:

Date: Thursday, 28 October 2021, 04:37 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Thursday, 28 October 2021, 06:55 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Beatty, Mary (q100217) Title:

Date: Thursday, 28 October 2021, 12:49 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================