INSTRUCTIONS

(Delete these instructions before finalizing this document)

The Site Activation Management Plan (SAMP) template is intended to facilitate the start-up project planning process as well as to ensure robust planning and execution of required activities to be completed in parallel to Essential Documents Pack (EDP) elements, leading to Site Activation. The main purpose of the SAMP is to inform the internal team and should only be reviewed by the Sponsor if requested.

The Site Activation Manager (SAM) or designee is responsible for developing the SAMP, but it may include documents or information developed/obtained by other project team members or third parties. When creating this plan, do not reiterate detailed project information that is already captured in other project documents (e.g., Clinical Operations Plan (COP), Vendor Management Plan (VMP), Communication Plan, etc.) or in Standard Operating Procedures (SOPs) and Work Instructions (WIs) (collectively referred to as “SOPs”), instead the relevant project document or SOP should be referenced. However, author can consider to include short high-level summary of the referred document.

Include Protocol/Sponsor identifiers in the Header to make this template project-specific. This template has been generated based on IQVIA SOPs referenced within it. If roles and responsibilities differ from the ones stated in the SOP, the text in the subsection(s) referencing the SOP should be modified to reflect the project specific responsibilities for each role.

**If we will be using Sponsor’s SOP(s) for any Start-up activities, describe the Sponsor’s process in the appropriate subsection below (or add additional subsections if required) and provide a copy of the Sponsor SOP to all relevant team members. **

For projects where IQVIA SOPs will be used, the project must use current IQVIA SOPs as of their effective dates, unless otherwise stated. If there are exceptions for certain studies to remain under superseded SOPs, the SAMP must be updated to explain which process the team is to follow and why there is a need to follow the superseded SOP.

If a certain section of this plan is not yet completed or not applicable, the section can be designated with a relevant comment “Pending”, “In preparation” or “Not applicable” added in the title of the section. Subsection headings of the SAMP must not be deleted; however, if a subsection is designated not applicable, the text within the sub-section may be deleted. Additional subsections may be added as needed, but it is strongly recommended that this plan be kept at a manageable length.

For proper naming and dating of this document, follow CS_WI_RM0284, General and Trial Master File (TMF)-Specific Document Quality - Good Documentation Practices. Ensure version control is maintained in all subsequent versions of this plan. The header must list the version number and effective version date.

Note: For projects using IQVIA ELECTRONIC CONSENT (e-CONSENT) there is an annotated e-Consent SAMP template available (located on the e-Consent SharePoint).

Once the SAMP is ready for final signature:

- Delete all red text -- red text is instructional only and must be deleted prior to signing.

- Convert any blue font to black for items that are filled in based on instructions (e.g., SAM name in the signature blocks).

- Review document for formatting -- correct as needed.

- Update the Table of Contents (instructions are found on that page of this template).

- It is recommended to PDF this document.

- Signatures can be either electronic or wet signature. Electronic signatures are preferable, when possible and should be applied using the appropriate TMF platform or validated eSignature solution.

Each signed version of the SAMP must be uploaded in eTraining for applicable Site Activation project team members to read and acknowledge (this must include LRSU teams). CL and PL, when reviewing the SAMP, should determine if the SAMP should be required eTraining for any other team members, such as the CML and CMA.

The SAMP must be signed prior to Stage Gate Review (SGR) 2.

***REMEMBER: All signed versions of the SAMP must be filed in the Trial Master File (TMF)***

Site Activation Management Plan (SAMP)

Version Approval

Delete these instructions before signing the document.

In table below, change blue font to black and remove brackets [ ] once names and titles have been entered. There is no requirement for the sponsor to sign the SAMP. If the sponsor requests to sign the SAMP, additional signature lines will need to be added to the signature block.

Roles designated in this plan will be project-specific, and dependent on the project’s resourcing. In some cases, tasks may be delegated to other team members in instances where a specific role is not resourced. Signatures below should be adjusted accordingly.

Signatures can be either electronic or wet signature. Electronic signatures are preferable, when possible and should be applied using the appropriate TMF platform or validated eSignature solution. eSignatures, if used, will appear in appended page(s).

| Document Author |  |
| --- | --- |
| [SAM Name, Title], Site Activation Manager, IQVIA | Date (ddMmmyyyy) |
| Document Reviewers |  |
| [RAd Name, Title], Regulatory Advisor, IQVIA | Date (ddMmmyyyy) |
| [CL Name, Title], Clinical Lead, IQVIA | Date (ddMmmyyyy) |
| [PL Name, Title], Project Leader, IQVIA | Date (ddMmmyyyy) |

# Revision History

Changes to the Project Affecting the SAMP

INSTRUCTIONS (do not delete these instructions):

The SAMP should be reviewed and updated as appropriate throughout Startup and Lifecycle Maintenance as changes in scope or processes occur( i.e. protocol amendment(s), Key Team Member (KTM) transition). If updates are deemed necessary, the SAMP must be approved (following the same process as review and approval of the initial version). In the table below, list a summary of the changes, sections referenced and reasons for the change.

Each updated version of the SAMP must be uploaded separately in eTraining, for applicable project team members to read and acknowledge.  All signed version of the SAMP must be filed in the TMF.

The Table of Contents must be reviewed/adjusted each time the SAMP updates are completed.

Updates due to an SOP change:

- The SAMP must be reviewed each time an SOP is updated that will impact the Site Activation process to ensure documentation of project processes remains current.

- The SAMP must reflect the current SOPs in use during the Start-up and Lifecycle Maintenance phase of the project. If SOPs are added, revised or made obsolete, the SAMP must be updated accordingly.

- For projects where IQVIA SOPs will be used, the project must use current IQVIA SOPs as of their effective dates, unless otherwise stated. If there are exceptions for certain studies to remain under superseded SOPs, the SAMP must explain which process the team is to follow and why there is a need to follow the superseded SOP. The same SOP version must be used across all countries within the same project.

| Summary of Change | Section Reference | Reason for Change |
| --- | --- | --- |

{Instructions: The Table of Contents (TOC) for the project should be customized in accordance with the scope of the project. To update the TOC: Right click on the table; select “update field,” and select either “update entire table” (if you’ve added additional sections) or “update page numbers” if you have not added sections, but only adapted text in existing sections. Only items identified with the proper heading styles will appear in the Table of Contents. Delete these instructions before finalizing document}

TABLE OF CONTENTS

Revision History	2

1.0	Purpose	5

2.0	Project Set-up and Planning	5

3.0	Site Identification and Selection	6

4.0	Site Contracting	9

5.0	Informed Consent Form (ICF) Development/Review/Approval	11

6.0	Regulatory Authority/Independent Ethics Committee/Institutional Review Board (RA/IEC/IRB) Submissions & Approvals	13

6.1	European Union Clinical Trial Regulation (EU CTR)	14

6.2	Responding to RA/IEC/IRB questions	16

6.3	EU CTR RACI between SAM and RAd	17

6.4	North America Central IRB Submission	18

6.5	Adding additional countries (during start-up or conduct)	18

6.6	Amendments to the CT Application (during start-up or conduct)	19

6.7	Reporting of Updates during a trial, such as Study Status Reports, Urgent Safety Measures (USM), Serious Breaches (SB) and Temporary Halts (TH)	19

7.0	Delegation Letter	21

8.0	US FDA IND Investigator Information Package	21

9.0	Project Insurance	22

10.0	IP Label Creation and Review	22

11.0	Import/Export Licenses	23

12.0	Site Ready to Enroll Activities	25

12.1	Overview of SRtE Activities	25

12.2	SRtE Roles & Responsibilities:	27

12.3	Identification and Documentation of Site Ready to Enroll Activities	28

12.4	SRtE Site Contact Form (CS_TP_RSU0082, Site Ready to Enroll Site Contact Form)	28

12.5	Systems Access, Equipment and other Supplies	29

12.6	Other Investigator and Site Staff Training:	32

12.7	Execution and Oversight of Site Ready to Enroll Activities:	33

12.8	RSU Country Level Meetings:	34

12.9	Internal team meetings (at minimum weekly):	35

12.10	Internal/External Team Meetings and Status Review	35

12.11	RSU Country and Site Transfer:	35

12.12	Site Activation:	36

13.0	Essential Document Pack Collection & IP Release Process	36

14.0	Investigator’s Site File	37

15.0	Handover and Transition Activities during a Clinical Study	38

16.0	Reporting	38

17.0	Project Team Training	38

18.0	Translation	40

19.0	Out of Scope work	41

Appendix A	Critical Path Planning	42

General Notes:

- When “Trial Management System” is referenced throughout this template, this infers tracking directly into CTMS or other IQVIA trial management systems.

- Centralized RSU (cRSU) may be involved in performing and/or coordinating certain activities described in this plan that are not shown as assigned for cRSU. Refer to CS_OP_RSU0061, Centralized RSU Scope of Activities for the activities that may be performed by the Centralized Regulatory Start-up (cRSU).

Note: Activities not covered in CS_OP_RSU0061 but performed by cRSU Rep for specific country or process need to be documented in the respective section of this plan (unless already documented in a Local Clinical Monitoring Work Instruction).

- Global Site Activation Analyst (GSAA) may fulfill some of the Site Activation Manger(SAM)/Maintenance Lead (ML) responsibilities outlined in this plan.

- Tasks and responsibilities of Monitor/Clinical Trial Assistant (CTA) are outlined in the project-specific Clinical Operations Plan (COP) as Monitor/CTA are not expected to read and acknowledge the SAMP.

# Purpose

- The purpose of this Site Activation Management Plan (SAMP) is to outline project or program specific references and expectations regarding the management of the {Insert Program/Protocol Name} during the Site Activation and Lifecycle Maintenance Phase based on defined scope.

- Roles and responsibilities of these activities are covered in IQVIA SOPs, WIs and the Expanded SRtE RACI unless otherwise noted as a deviation or in a project/program specific WI.

- SAMs have a defined Issue Management Framework that describes the project issue management framework and provides guidance on how we should view issue management at IQVIA: Link to Issue Management Framework

# Project Set-up and Planning

Resource planning/request, Financial planning, Systems, Document repository, timelines

- The SAM requests assignment of applicable resources within Global Site Activation (GSA) from each region participating in the project.

- The SAM will confirm templates and workspaces are set-up for the project (e.g., Trial Management System, and RSU folders on shared drives or Sharepoint). The SAM will also confirm documents for which RSU is responsible are filed by the RSU team as appropriate in the Trial Master File (TMF) according to CS_OP_TMF0007, Trial Master File (TMF) and its associated WIs.

- The SAM in collaboration with the Project Leader (PL), Clinical Lead (CL), Regulatory Advisor (RAd) and Local Regulatory and Start-Up Representatives (LRSU Rep) develops start-up and Site Activation timelines. There must be an agreed upon internal alignment and discussion with the Sponsor.

# Site Identification and Selection

### Initial Site List, CDA and SSQ distribution and collection, and final site selection. Refer to CS_WI_RSU0065, Site Identification and Selection

{Iinclude any information the SOP indicates will be documented in the SAMP. Update the text below as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}.

Confidential Disclosure Agreement (CDA) and Site Selection Questionnaire (SSQ) process:

{Update the text as needed depending on whether a CDA is required for this project. Per the SOP, the SAM must document the following, including confirmation on where the related documents are located

- Whose CDA template will be used (IQVIA or Sponsor)

- If CDA negotiation fallback is available

- If Master CDAs are accepted by Sponsor and if any Master CDAs already exist between the Sponsor and specific sites – the list of sites must be obtained from the Sponsor in writing and filed in the TMF

- If CDA and SSQ can be sent together or if the CDA must be signed before the SSQ can be sent.

- If the Original CDA is to be collected and/or sent to Sponsor

- If an alternate strategy will be used to accelerate Site ID and Selection, e.g. Optimized Site ID and Selection, SSQ prior to CDA, etc.

- Timeline and escalation expectations for these activities

The text provided in the example assumes a CDA is required and that we will use IQVIA templates, Master CDAs, etc. Update as appropriate, add or delete text as needed.

Example:

- Confidential Disclosure Agreement (CDA) is required for each site

- IQVIA CDA Template & Fallback Document will be used and is located at the link within the table below

- Master CDAs are acceptable: List here

- CDA & SSQ may be sent to sites together

- Note alternate Site ID/Selection acceleration strategy if applicable

| Document | Status | Link to Study Specific Template | Reference Document {delete column if not needed} |
| --- | --- | --- | --- |
| CDA Template | IQVIA/Sponsor |  |  |
| Fallback Document | Available Y/N |  |  |
| Master CDAs | Accepted Y/N |  |  |
| Original CDAs | Y/N |  |  |
| CDA/SSQ Sent Together | Y/N |  |  |
| Site ID Kick-off Meeting (KOM) Worksheet |  |  | CS_TP_RSU0008 |

SSQ Review and SSV process:

- Local Site Identification Representative (LSID Rep) reviews and evaluates completed SSQ using annotated SSQ as a guide, within {1-2} working days of receipt and may escalate specific questions based on annotated SSQ, to {SAM/CL}

- {SAM/CL} reviews only specific escalated questions and provides response to LSID Rep within {1-2} working days of receipt

- LSID Rep approves or rejects site for Site Selection Visit (SSV) within {1} working day of all clarifications from site or response from {SAM/CL} escalation receipt

- LSID Rep Updates status in applicable Trial Management System according to whether an SSV is required.

- For Optimized sites that meet the pre-agreed selection criteria, mark ‘Selected’

- For non-Optimized sites that meet the pre-agreed selection criteria, mark “Approved for SSV”

- For rejected sites that do not meet the pre-agreed selection criteria, select “Rejected for SSV”

  - For sites requiring SSV, designates SSV requirement “on-site”, “remote”, or “waived” based on the criteria outlined in CS_WI_SM0005, Monitoring Visits If approved for SSV, Local SID Rep enters SSV type (on-site or telephone) into Trial Management System using criteria found in CS_WI_SM0005, Monitoring Visits or other supplemental study instructions, if applicable, based on the Site ID and Selection strategy

- LSID Rep is responsible for ensuring that the completed CDAs and SSQs are filed in the TMF

- SAM is responsible to ensure that SSQ review and escalation timelines are included in the Site ID KOM slides (CS_TP_RSU0008)

| Document | Link to Study Specific Template | Reference Document |
| --- | --- | --- |
| SSQ Template |  | CS_TP_RSU0063 |
| Annotated SSQ |  |  |

- CL is responsible for ensuring timely Monitor resourcing is in place

- Monitor is responsible for conducting the SSV and providing the SSV Report to CL for review according to the Clinical Operation Plan (COP) but the finalization of the SSV Report, is not rate-limiting for site selection

- Monitor makes selection recommendation to CL within {1-2} working days post SSV

- {Note: upon agreement and finalization of timelines for completion of Monitor`s task, SAM needs to ensure that same information is provided to the CL, so it is included in the project specific COP}CL, in consultation with project team, is responsible for final selection decision or back-up designation, updates site status in the Trial Management System to “Selected”, “Not Selected” or “Back Up”, and notifies SAM.

- CL makes selection decision based on recommendation and updates site status to ‘Selected’/’Not Selected’/’Back-Up’ within {Note: Default should be 1-2 working days unless specific process is to be followed e.g., the need to wait for additional SSVs to happen before a decision can be made. Adjust as necessary on a study basis} {1-2} working days post Monitor`s recommendation.

- The CL ensures site status is updated in CTMS and notifies SAM

- SAM informs LRSU Rep and LSID Rep of new site(s) selected within {1} working day of confirmation by CL

- LSID Rep provides all relevant documents and site information to the LRSU Rep, as applicable.

- LRSU Rep sends the Site Selection, Back-Up, or Non-Selection Letter to the site along with the Site Ready to Enroll Contact Form (CS_TP_ RSU0082) within {2-3} working days of confirmation by SAM

- SAM is responsible for ensuring all sites are informed of their SSV outcome

- LRSU Rep is responsible for ensuring letters distributed to all contacted sites are filed in the TMF

| Document | Link to Study Specific Templates | Reference Document |
| --- | --- | --- |
| Site Selection, Back-Up, and Non-Selection Letters |  | CS_TP_RSU0004 |

Deviations from CS_WI_RSU0065, Site Identification and Selection:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.}

- Activities that cRSU Rep may be performing that are not assigned to cRSU Rep in the SOP

- Activities assigned to cRSU Rep (or any other role) in the SOP that are performed by another role (e.g., LRSU Rep)

- If LSID Rep is not responsible for approving/rejecting the sites for SSV, update the process accordingly as in example below. {VERY IMPORTANT: the response timelines for each step must be included and can only be modified if sponsor is the reviewer/approver or for special circumstances but can never exceed 5 working days unless strong justification is provided and documented}

- Local Site Identification Representative (LSID Rep) reviews and evaluates completed SSQ using annotated SSQ as a guide within {1} working day of receipt.

- LSID Rep submits the SSQ to {CL/SAM/Sponsor} for review and approval

- {SAM/CL/Sponsor} reviews the SSQ and confirms site approval/rejection for SSV within {1} working day of receipt

  - LSID Rep updates site status in CTMS to Approved/Rejected for SSV within {1} working day of receipt.

- If IQVIA is not responsible for “SSQ review and SSV process”, describe who is responsible and how it will be managed, including response timelines for every step as included above for standard process.

# Site Contracting

### Site Contract Templates, Site Contract and budget negotiations Refer to CS_WI_RSU0066, Clinical Trial Agreement and Budget

{Per the SOP, document which Contract template(s) will be used – IQVIA’s or Sponsor’s – the text below assumes IQVIA templates are used. Update as appropriate – add or delete text as needed.

Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}

Setup:

- Contract and Budget Solutions Lead (CBSL), in combination with the Sponsor, will finalize study budget and payment terms and distribute to SAM

- SAM and CBSL make country-specific Clinical Trial Agreement (CTA) and Budget adaptations as applicable

- IQVIA study expectations, process, and timelines are included in the contract negotiator training

- SAM will work with CBSL to ensure contract negotiator training aligns with study strategy and timelines

- CBSL determines if Power of Attorney for signatures is required and if so, works with the Sponsor to develop the document.

Contract:

- LRSU Rep will negotiate contract with the Investigator Sites

- SAM will contact Sponsor for approval of site CTA requested changes not in Fallback language

- Sponsor CTA review turnaround time is X working days

Budget:

- LRSU Rep will negotiate budget with the Investigator Sites

- SAM will contact Sponsor for approval of site budget if more than Sponsor approved limits

- Sponsor Budget review turnaround time is X working days.

Finalization:

- LRSU Rep will finalize the CTA and Budget once agreed by site and Sponsor

- All party signatures are required for the document to be fully executed

| Document | Status | Link to Study Specific Templates | Reference Document {delete column if not needed} |
| --- | --- | --- | --- |
| CTA Template | IQVIA/Sponsor/Hybrid |  |  |
| Fallback Document | Available Y/N |  |  |
| Budget Template | IQVIA |  |  |
| Payment Terms | IQVIA |  |  |
| Contract and Budget Negotiation Training | Available Y/N |  |  |

CTA Amendments:

- In case of request for CTA Amendment (e.g., from Sponsor, Monitor, LRSU Rep, PL, CL) SAM and CBSL are to be contacted. CBSL is to prepare and provide the appropriate Global Amendment Template(s) Country Budget Template, and budget negotiation parameters, for applicable countries. SAM, with input from PL, CBSL, Sponsor completes the Country CTA Amendment Template(s) and updates the instructions and budget negotiation parameters, as appropriate and provides them to LRSU Rep in applicable countries. LRSU Rep negotiates the amendment changes to the Investigator Site CTA with the appropriate site(s) following the same negotiation/escalation/finalization process as for initial CTA.

- If the CTA Amendment request is received after the Site Activation phase of the project when SAM is no longer allocated, the responsibilities of SAM are assumed by ML.

- For specific details on the local CTA Amendment process for applicable countries, the Local Clinical Monitoring WIs should be referenced.

Deviations from CS_WI_RSU0066, Clinical Trial Agreement and Budget:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.}

- Activities that cRSU Rep may be performing that are not assigned to cRSU Rep in the SOP

- Activities assigned to cRSU Rep (or any other role) in the SOP that are performed by another role (e.g., LRSU Rep)

- If IQVIA is not responsible for contracts, describe who is responsible and how it will be managed. (Be sure to include information on whether an executed contract is required for EDP approval. A fully executed contract is always required for IP release.)

# Informed Consent Form (ICF) Development/Review/Approval

To ensure the development, review, adaptation and approval of the ICF is complete. Refer to CS_WI_RSU0033, Creation and Review of the Informed Consent Form

{ Per the SOP, the following items must be listed in the SAMP:

- Iinclude any information the SOP indicates will be documented in the SAMP.

- Which ICF templates are used (IQVIA or Sponsor’s).

- If an ICF booklet will be used or an electronic consent will be used, describe how that will be reviewed and managed.

- If number and type of ICFs is not documented on the project EDPRF, document that information here.

- If the Sponsor has some additional process (a special review process or needs to review the entire ICF), document that information here.

- Remember, the ICF KOM is to be recorded and added to eTraining.

- The ICF Lead owns the oversight of the ICF development process. For this project, the role will be filled by the designated ICF Lead {if no designated ICF Lead is allocated on the project replace with appropriate role( RAd, SAM or other role) that will assume the functions of the ICF Lead}. {If Japan is involved, include this statement – ‘The CPM in Japan will be the ICF Lead for Japan.} The SAM { RAd, or the designated ICF Lead } is the primary contact with the Sponsor for ICF information.

The text below assumes IQVIA templates are used. Update as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members

- {Include the following text if IQVIA will write the Study Master ICF(s)} The ICF documents required for the project will be developed using IQVIA templates {Sponsor provided templates}. Study Master ICF(s) are created only upon finalization of the Protocol. The Country adaptations begin only upon finalization of the Study Master ICF(s) and signature of the Study Master ICF Checklist(s). For this study the IQVIA Compensation for Injury (CFI) text {Sponsor Compensation for Injury} will be used. The Sponsor and ICF Lead have agreed on the legal text requirements for each country and any changes from IQVIA standard will be communicated to the affected countries.

- {Alternatively, if the Sponsor is providing the Study Master ICF(s) include this text instead} The Sponsor is responsible for providing the Study Master ICF(s) for this project. The ICF Lead will perform a review against the final protocol, the ICF Checklist and other source documents as needed (e.g., the Investigator’s Brochure). Once the Study Master ICF(s) have been reviewed and approved by both IQVIA and Sponsor, the ICF Kick of Meeting (KOM) will be held to inform cRSU and LRSU Reps of the requirements for this study ICF. This meeting will be recorded and posted to eTraining to ensure all staff that require the information have access to it. After the ICF KOM, the Country Master ICFs can be created for each country participating in the project. {if the Sponsor provides both the Study Master ICF and all Country Masters, they will need to be reviewed and approved internally, the process for this should be agreed with the ICF Lead and documented here, and the next paragraph can be deleted}

- The cRSU Rep is responsible for adapting the Study Master ICF for most countries. (Any countries included in the project that will have the Country Master ICF created by the LRSU Rep are listed below). The cRSU Rep will provide the LRSU Rep in each country with the adapted Country Master ICF. LRSU Rep will review and approve the Country Master ICF prior to including it in any required country submissions to the RA/IEC/IRB.

{For single-country projects; projects conducted in one or two countries only, or multinational projects where there is a supplemental ICF required only for one country, a Country Master ICF(s) can be created without first creating a Study Master ICF. Other scenarios are appropriate, depending on the individual needs of a project (e.g., US Country Master ICF can be created initially, then used as a substitute for the Study Master ICF from which to create the Country Master ICF(s) for other participating countries), but these scenarios must be documented in the SAMP}.

- ICF Amendments will be managed in a similar fashion to the initial project ICFs as stated in the SOP.

Deviations from CS_WI_RSU0033, Creation and Review of the Informed Consent Form:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.}

- Activities that cRSU may be performing that are not assigned to cRSU in the SOP

- Activities assigned to cRSU (or any other role) in the SOP that are performed by another role (e.g., LRSU Rep) – in particular, you must list any countries for which LRSU Rep is performing the adaptation to create the Country Master ICF, as this is a cRSU responsibility.

- Use of a draft protocol to start ICF creation, or creation of a Country Master ICF from a draft Study Master ICF, or use of a Country Master ICF as the Study Master ICF

# Regulatory Authority/Independent Ethics Committee/Institutional Review Board (RA/IEC/IRB) Submissions & Approvals

The Clinical Trial Application package compilation, review and submission and coordination of responses to RA/IEC/IRB questions. Refer to: CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications

{Per the SOP, the following items must be listed in the SAMP:

- Iinclude any information the SOP indicates will be documented in the SAMP.

- If there is no RAd involved in the project, document that the SAM will perform the role of the RAd in the project.

- Document decisions regarding submission strategy, such as those relating to use of country level or harmonized approaches to the European Union (EU) Clinical Trial Regulation (CTR)

- Document Customer expectations for document redaction or deferral of publication, in relation to clinical trial transparency obligations in countries or regions where clinical trial documents are made publicly available (e.g., in relation to clinical trial applications performed under the requirements of the EU CTR).

- If IQVIA is responsible to create a Questions & Answers (Q&A) log to document RA/IEC/IRB questions and their answers. If so, provide the link to the log.

- Include the agreed upon timelines for compilation and/or responses to questions

- If we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}

- In the event that IQVIA is not performing the full scope of Start-up, this section must include information on the project responsibilities associated with Regulatory and Ethics Committee (EC) approvals, especially where the Roles & Responsibilities (R&R) are allocated to different groups outside of IQVIA. Include any part of this activity that is assigned to others outside IQVIA (Sponsor, Vendor, other CRO). This must include who is responsible for determining “Regulatory Green Light” and that IQVIA will perform a Due Diligence to confirm Regulatory Green Light is completed as per the R&R within the contract. It should be clearly documented within the SAMP who is responsible for completing the green light/site activation and any other relevant activities for the project; and that copies of the approvals are to be provided to IQVIA for confirmation of full country and site approvals and confirmed as complete by the Project Lead (PL) or SAM.

- The first version of the Table of Regulatory Responsibilities (TRR) must be approved before the first submission that IQVIA performs outside the US. The TRR identifies the regulatory responsibilities for a clinical project for all countries EXCEPT the United States (US). Each approved version of the TRR is made available to the LRSU Rep(s) for awareness of the agreed project specific processes in place.

- For projects conducted under a US Investigational New Drug application (IND), a Transfer of Regulatory Obligations (TORO) will be prepared as part of the finalization of the project work order. Refer to CS_WI_RSU0009, Transfer of Regulatory Obligations.  There is no requirement for the TORO to be in place before project work can begin.

- {If required by the Scope of Work (SoW), provide details for which documents the RAd will perform a technical review or content review to support the trial and Investigational Product . Edit the following text to match scope of work} The RAd will perform a technical review on the following documents: Protocol, Investigator Brochure (IB), Investigational Medicinal Product Dossier (IMPD), Informed Consent Form (ICF), patient recruitment document, and the Investigational Product (IP) Label and completes the appropriate checklists.

- When the documents are deemed acceptable, the RAd compiles and performs a QC check of all component parts of the Core Clinical Trial Application (CT Application) dossier. The SAM will perform a second review and acknowledges the QC by e-signature in the Trial Management System.

- Country specific CT Application submissions will be managed and performed by LRSU Reps. The Country CT Application will be based on the Core CT Application compiled by the RAd with any country specific requirements added by the LRSU Rep. A second LRSU Rep will review the CT Application before it is submitted to the RA/IEC/IRB. A QC must be performed prior to any RA/IEC/IRB submission using CS_TP_RSU0024, Global QC Checklist for Clinical Trial Submission Documents and/or CS_TP_RSU0025, Country QC Checklist for Clinical Trial Submission Documents (or other Local QC Checklist).

European Union Clinical Trial Regulation (EU CTR)

{remove text and mark this section as “not applicable” if there are no countries from the European Union. If applicable, any Sponsor-specific requirements, processes or expectations that deviate from the processes for redaction described here, in CS_WI_RSU0067, and/or in the IQVIA principles for redaction must be documented within this SAMP}

- For clinical trials conducted under the EU CTR, the RAd identifies any personal protected data (PPD) within the core clinical trial documents that is considered acceptable to redact, per IQVIA principles for redaction of clinical trial documents, applicable regulatory requirements and/or guidelines (e.g. European Medicines Agency guidance on transparency relating to clinical trials) and considering any Sponsor-specific agreement described in this plan. Prepares the draft redacted clinical document(s) in an appropriate version of applicable software (e.g. Adobe Acrobat Professional) using a ‘Mark for Redaction’ tool ensuring that all information to be redacted is still visible. {If needed edit following sentence upon discussion and confirmation from Sponsor} Sponsor review should be completed for each redaction performed on a core clinical trial document. Full redaction should then be applied, following confirmation of acceptability of the planned redaction.

- The RAd must also inform the Sponsor of the option for redaction of commercially confidential information (CCI) that is included within core clinical trial documents, and which also may be redacted in-line with EMA guidance on transparency relating to clinical trials. If the Sponsor requires additional information they should be provided with a copy of the applicable guidance and IQVIA policy relating to redaction of CCI. While IQVIA can advise on information/data that may be redactable, the identification of CCI within clinical trial documentation remains the responsibility of the Sponsor at all times. Following identification of CCI by the Sponsor, the RAd shall redact by the same process described above.

- The redacted and non-redacted versions of all documents must be retained for submission in the clinical trial application/amendment and filed in the TMF.

{In situations where the Sponsor may retain responsibility for Part I submission scope in the EU under EU CTR - adapt as appropriate}

- For clinical trials performed under EU CTR, the RAd establishes appropriate access to the EU Clinical Trial Information System (CTIS) and oversees provision of access to other IQVIA users who require access, per clinical trial submission scope. Utilizing the information within the Core QC Checklist, the RAd prepares a Part I-specific QC checklist, describing all final documents uploaded and planned for the submission. The RAd is also responsible to submit Part I CT Application Dossier. The RAd routinely monitors submission status and tracks the status of Part I submission and facilitates, in consultation with the SAM, PL and Sponsor, the resolution and submission of responses to questions or corrections requested by the Reporting Member State (rMS). In parallel to the Part I dossier preparation the RAd is also required to coordinate Part II, country-level submission planning, to ensure preparation for submissions are performed efficiently, and submissions can proceed in parallel or sequentially, as planned.

- Country specific CT Application submissions will be managed and performed by LRSU Reps and will follow the standard review and QC process as for any RA/IEC/IRB submission, including use of the appropriate QC Checklists as detailed in CS_WI_RSU0067.

- {remove sentence if not applicable, and adapt per study scope, if necessary} For clinical trials performed under EU CTR the LRSU Rep uploads documents to the CTIS to compile the Part II dossier in CTIS.

- For a clinical trial conducted under the EU CTR the LRSU Rep, with the support of the RAd, identifies any PPD within the country and site-level documents that is considered acceptable to redact, per applicable regulatory requirements and/or guidelines (e.g. European Medicines Agency guidance on transparency relating to clinical trials) and considering any Sponsor-specific agreement described in this plan. The LRSU Rep prepares redacted and non-redacted versions of the applicable documents in an appropriate version of applicable software (e.g. Adobe Acrobat Professional) using a ‘Mark for Redaction’ tool. The requirement for Sponsor review of redacted and non-redacted versions of country and site-level documents must be established study-by-study, unless already documented in an account level agreement or manual.

- For this trial, the Sponsor {does or does not} require that they review the redacted and non-redacted versions of the country and site-level documents before they are submitted. {Note if this information is already captured in an account level agreement or manual, indicate where the Sponsor requirements are captured and provide a link to the document.}

- The redacted and non-redacted versions of all documents must be retained and filed in the TMF.

Responding to RA/IEC/IRB questions

- If questions are received from the RA/IEC/IRB, the LRSU Rep provides the SAM/RAd (for EU CTR countries) with a full translation of the questions within the timelines outlined in this plan. The SAM/RAd (for EU CTR countries) will coordinate the preparation of answers with the appropriate team members {If required per the SoW add – and will enter RA/IEC/IRB questions into a Questions & Answers (Q&A) log for the Sponsor and project team on a continuing basis}

{Instruction: Due to tight timelines for responding to questions under EU CTR separate text is proposed to be used for countries falling/not falling under EU CTR in order to allow different timelines to be agreed and used. Depending on list of participating countries this specific section might not be applicable and is to be deleted. It is also acceptable both sections to be combined if it is agreed on project level same timelines to be used but responsibilities for specific countries need to be clearly stated}

{Suggested text for Countries not falling under EU CTR:}

- LRSU Rep will provide RA/IEC/IRB questions to SAM within X working days of receipt.

- SAM will collate response in addressing RA/IEC/IRB questions with input from relevant parties (for example, PL/CL, RAd, Medical Advisor, Sponsor) within X working days. The SAM will work directly with the local country teams to ensure RA/IEC/IRB questions are responded to within X working days of the receipt of the answers or within the timeline provided by the Authority.

- The SAM will advise all parties involved if the response time needs to be amended to meet a meeting date of the RA/IEC/IRB.

- If possible, the SAM will advise all parties of potential dates when we may receive questions from the RA/IEC/IRB.

{Suggested text for Countries falling under EU CTR:}

- For questions relating to Part II documentation, the LRSU Rep will provide questions received from EU Member States (MS) to RAd within 1 working days of receipt.

- RAd will collate responses necessary to address the MS questions with input from relevant parties (for example, LRSU, PL/CL, SAM, Medical Advisor, Sponsor) within 7 working days or 10 calendar days of initial receipt of the questions, whichever is shorter.

- For questions relating to Part II documentation, the RAd will work directly with the local country teams to ensure MS questions are responded to within 2 working days of the receipt of the answers or within 12 calendar days of receipt of the questions from the MS. For questions relating to Part I documentation, the RAd will ensure the response is submitted within 12 calendar days of the receipt of the questions.

- The RAd will advise all parties involved if the response time needs to be amended for any reason.

- RAd must notify in advance all parties of potential dates when we may receive questions from the RA/IEC/IRB.

EU CTR RACI between SAM and RAd

{remove paragraph and associated table if not applicable}

High-level overview of division of responsibilities between SAM and RAd for projects involving countries falling under EU CTR

{Instructions: Use the table below to provide clear split of tasks during submission and approval activities. List of tasks is exemplary and not comprehensive and can be amended and updated as needed. Project details and certain partnership accounts may impact the task distribution. Change example font color to black before finalizing.}

| Task | Role performing task for EU CTR countries | Role performing task for non-EU CTR countries |
| --- | --- | --- |
| Regulatory Intelligence on Submission Document Requirements | RAd | SAM |
| Submission strategy | RAd | SAM |
| Execution, control, and oversight of submission strategy | RAd | SAM |
| Oversight of preparation of Country Application Dossier including request for documents from external parties (e.g., Sponsor, third-party central vendor, etc.) | RAd | SAM |
| Management and oversight of responses to questions received from the Member States/RA/IEC/IRBs | RAd | SAM |
| Status reporting of submission and approval activities to internal and external stakeholders | RAd | SAM |
| Oversight of tracking and filing process of documents and milestones related to submission and approval activities | RAd | SAM |
| Identification of risk and issues related to submission and approval activities and their escalation and management | RAd | SAM |

North America Central IRB Submission

{Only include if North America is involved in the project. If North America is not included or there are no Central IRBs, delete the following text and state “not applicable” for this section.  Each project and Central IRB in NA is slightly different, but in general the following information will be needed for the initial submission, update as needed}:

- {name of Central IRB} will be the Central IRB for this project. The following information will be needed for the initial submission: Protocol, IB, Country ICF Template, Patient Materials, Advertising and/or Recruitment Materials, Questionnaires, Indemnification Agreement between Sponsor and the Central IRB, and IRB Project Application Form. {Include any Central IRB processes that may be followed (e.g., submission via the Central IRB’s website).}

Adding additional countries (during start-up or conduct)

  - The SAM will update the SAMP and TRR as needed.

- SAM/ RAd (for EU CTR countries) will collect the country specific requirements and work with Sponsor to obtain documents and establish timelines. Submission and approval activities will follow the same process as for initial submissions as described in paragraphs above and according to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications.

Amendments to the CT Application (during start-up or conduct)

(refer to CS_WI_SM0020, Management of Revised Clinical Study Documents)

- Upon receipt of information from the Sponsor or project team of any upcoming global amendments to the study documents, the SAM/ML will request the Sponsor’s determination of substantial or non-substantial amendment. The RAd prepares CS_FM_RSU0054, Assessment of Substantiality and sends to the Sponsor for review and approval.

- The Sponsor is responsible for determining whether an amendment is substantial or non-substantial. The RAd and SAM/ML can provide guidance on classification if requested, but the final decision must come from the Sponsor. The RAd and SAM/ML communicate with the Sponsor if there is disagreement about the Sponsor’s classification and provide a reference to the appropriate legislation to support the rationale.

- SAM/ML/RAd ((for EU CTR countries) will coordinate RA/EC/IRB submission activities and receipt of RA/EC/IRB approvals or acknowledgements. These activities will follow the same process as for initial submissions as described in paragraphs above and according to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications.

- Refer to Section 19.0, Out of Scope Work, for guidance related to out-of-scope changes.

Reporting of Updates during a trial, such as Study Status Reports, Urgent Safety Measures (USM), Serious Breaches (SB) and Temporary Halts (TH)

- Authorities in many countries/regions require updates such as the following to be reported – for example:

- Updates on study status (i.e. milestones such as first visit of first participant, end of recruitment, etc.)

- Notification of incidents and measures taken which meet the definition of USM, SB, TH and other changes in risk/benefit profile of a trial

- Annual Reports on progress of the trial

- End of Trial and early End of Trial

- As standard, the responsibility for making such reports to RA/EC/IRB will follow the responsibilities described in prior sections relating to Initial Clinical Trial Applications (i.e. if IQVIA LRSU Reps are responsible for communicating with RA/EC/IRB in relation to the initial CTA the same responsibilities will apply for communication/reports made to the same authorities/committees during the conduct of the clinical trial. Any variation from these roles and responsibilities will be defined in this SAMP, and recorded within the Table of Regulatory Responsibilities.

- If the Sponsor or Data Safety Monitoring Board (DSMB) decides that the project requires a temporary halt and/or re-start, the PL/RAd (for EU CTR countries) oversee the coordination of submission to RA/IEC/IRB by the LRSU Rep.

- Serious Breach identification, assessment and reporting is conducted per the process described in CS_OP_QA0358, unless otherwise agreed with the Sponsor, and documented in a Quality Assurance Agreement.

- Urgent Safety Measures and Temporary Halt notifications must be made immediately and within timelines mandated per country specific Regulations. For EU CTR and European Economic Area (EEA) countries, the submissions to RA/IEC/IRB must follow within 15 days from when the trial is temporarily halted. For all other regions/countries, the LRSU Rep must be consulted regarding the locally-legislated timeframe for the submission. This information is also available in RID. Once the Urgent Safety Measure is confirmed, PL informs Lifecycle safety that the submission was made so that there is no duplication of submission.

- Lifecycle Safety Regulatory Reporting (LS RR) may on occasion be requested to be involved in the submissions of urgent safety measures however, coordination and oversight of such submissions remains a PL/RAd (for EU CTR countries) responsibility. LRSU Rep uses the Core QC checklist to prepare a Country QC checklist to ensure all required documents are included in the submission and prepares all necessary documentation required for RA/IEC/IRB submission (including consideration for any redaction (as described in the process for initial submission/approval of this plan) that may be necessary). During conduct of the study, the RAd should be consulted regarding submission strategy {this should be documented in the COP}.

Deviations from CS_WI_RSU0067 – Project Lifecycle Clinical Trial Applications:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.}

- Any activities that cRSU may be performing that are not assigned to cRSU Rep in the SOP will need to be documented here (for example, core CT Application, delegation letters, and any local RSU tasks that are being completed by cRSU Rep instead of LRSU Rep).

- If no start-up meeting is held (communication will occur by email instead).

Note: Any deviations related to Delegation Letters should be listed in the section below rather than in this deviation section.

# Delegation Letter

Prepare Delegation Letters. Refer to CS_WI_RSU0067 – Project Lifecycle Clinical Trial Applications

{If the Sponsor has a specific process or if they have their own Delegation Letter Template, describe it in this section. If Sponsor templates are to be used, it may be necessary to send to certain local offices for review of compliance with local requirements (e.g., Russia). IQVIA Legal will need to review the DL if changes made by the Sponsor contradict IQVIA contract. If so, describe here.

Note: In US and Canada a delegation letter is not required. Sites may request a “delegation letter”, but what they need is an “Authorization Letter” which states IQVIA is authorized to sign on Sponsor’s behalf. An example of such a letter can be obtained from the US Contract Negotiation Line Manager.}

- The SAM, with support from the RAd, will explain the Delegation Letter (DL) process and general requirements at the KOM to help facilitate and expedite preparation before project start-up.

- The RAd prepares and provides to the SAM all country/region-specific Delegation Letters in accordance with the Delegation Letter Checklist (found in the Regulatory Intelligence Database (RID)) and collaborates with the SAM and the LRSU Rep (where applicable) on the final text as well as any instructions for signatures. The RAd sends the final Delegation Letter to Sponsor for signature, and distributes the final, signed Delegation Letters to the appropriate LRSU Rep(s).

# US FDA IND Investigator Information Package

When the US FDA IND Investigator Information Package is part of the RSU process for a specific project Refer to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications

{This information applies to all studies conducted under a US IND. Mark this section “Not Applicable” only if the project is not a US IND. The timelines for submitting the IND Investigator Information Package must be discussed with the Sponsor while completing the EDP-RF. Note that documents are not final until after EDP approval, so in general, time will be stated as the number of days after EDP approval. }

- An IND Investigator Information Package must be provided to the US FDA for sites in all countries participating in a protocol which is subject to an IND submission in the US. The SAM and LRSU Rep coordinate the submission to the Sponsor of the Initial IND Investigator Information Package for each site within the timeline agreed with the Sponsor, and track in the Trial Management System.

- After transition of the SAM from the project, the ML manages the submission to the Sponsor of revised/amended IND Investigator Information Packages, including updated 1572s, updated PI CVs, or changes in PI, for each site, within the timeline agreed with sponsor and makes sure that the package is tracked in the Trial Management System.

{Note: If Global Regulatory Affairs (GRA) is the US Agent for the Sponsor, the SAM/ML needs to work with GRA to establish a process for submission of the Investigator Information package to GRA and document the process in the SAMP. The process may be the same as above with the exception of involving GRA instead of the Sponsor.}

Timeline agreed with Sponsor {GRA} to provide initial IND Investigator Information Package: {Document agreed timeline here.}

# Project Insurance

Obtain Sponsor insurance certificates from the Sponsor and confirm they meet regulatory requirements (where applicable). Refer to Insurance Requirements in RID

IQVIA will not advise, recommend or obtain insurance on behalf of the Sponsor. IQVIA will provide reference information at the study and country level to satisfy the needs of the Sponsor and their vendors to bond insurance and can review insurance certificates provided by the Sponsor to confirm the certificate meets regulations (where country regulations exist). The certificate may be required as part of a Clinical Trial Application. SAM/RAd (for EU CTR countries) will ensure Sponsor understands timeline expectations regarding insurance as it relates to the delivery of the study.

# IP Label Creation and Review

Review and finalize respective country IP labels. Refer to CS_WI_RSU0019, Investigational Product Label Review

{Iinclude any information the SOP indicates will be documented in the SAMP. Update the text below as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}.

{Document who is responsible for the labeling -- IQVIA per our SOP or the Sponsor. If cRSU is not involved, document below as a deviation.

If we will use IQVIA SOP, insert at a minimum a statement such as: “IQVIA will review and finalize country  IP labels per the above referenced SOP.” More details can be included as needed, but do not reiterate the full SOP.

If Sponsor’s labeling process will be followed, document that process here and make sure that all relevant team members (e.g. RAd, LRSU Rep) receive a copy of the Sponsor’s SOP. Ask the RAd to review this section to insert appropriate timelines for the size of project/quantity of labels before finalizing.

Deviations from CS_WI_RSU0019 –Investigational Product Label Review:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.}

- Any activities that cRSU may be performing that are not assigned to cRSU in the SOP, or cRSU activities being performed by another role

# Import/Export Licenses

Confirm each participating country in the project will be allowed to import and export IP drug, equipment, or any other materials as needed. Refer to CS_WI_SM0027, Provision of Clinical Project Supplies and Equipment to Investigator Sites

{If IQVIA is not responsible for import/export licenses (based on the Scope of Work), the text below can be deleted and “not applicable” stated instead. If IQVIA is responsible for Import/Export licenses for the project:

- The SAM should consult with the PL/CL for any Sponsor nuances on import and export requirements.

- The SAM will confirm any information from RID with Local RSU staff regarding required documentation and timelines for obtaining the import and export licenses for approval.

- Notes:

  - In some countries, import/export tasks are the responsibility of Global Regulatory Affairs or other groups. Document in this section if those countries are part of this project and include details on what role will be responsible in each country.

  - IQVIA does not support import/export for all countries. Confirm on RID or with LRSU Rep. If countries we cannot support are included in the project, include the list of countries we will support in this section, and the plan for those we cannot support. If all countries in the project are supported, there is no need to include a full list.

- The SAM will follow up with the Sponsor, PL/CL and relevant third parties to obtain the required documents and data and forward to the LRSU Rep for their local preparation and submission to the relevant body/authority

- The LRSU Rep follows country procedure for import/export license submission and approval process.

- A QC must be performed prior to submission using CS_TP_RSU0024, Global QC Checklist for Clinical Trial Submission Documents and/or CS_TP_RSU0025, Country QC Checklist for Clinical Trial Submission Documents (or other Local QC Checklist), whether the import/export submission/approval is part of the initial CT Application submission or a standalone submission following initial CT Application approval (or subsequently at a shipment level).

The text below assumes that IQVIA is responsible for import/export tasks. Add or delete text as needed}

- IQVIA RSU team is responsible for preparing and submitting import and export licenses, where applicable. Please refer to the TRR for details on the specific countries. The SAM, in collaboration with the respective LRSU Rep, will provide the Sponsor with a list of requirements and timelines for each country and ensure that appropriate import and export licenses are in place for project start-up.

- The SAM in collaboration with the Sponsor, PL/CL and relevant third parties will obtain the required documents and data and forward to the LRSU Rep for local preparation and submission to the relevant body/authority.

- The LRSU Rep will follow country procedures for import/export license submission and approval process and will perform a QC check prior to submission using CS_TP_RSU0024, Global QC Checklist for Clinical Trial Submission Documents and/or CS_TP_RSU0025, Country QC Checklist for Clinical Trial Submission Documents (or other Local QC Checklist), whether the import/export submission/approval is part of the initial CT Application submission or a standalone submission following initial CT Application approval (or subsequently at a shipment level).

- Note: For EU CTR Countries Import/Export of IMP is covered within CTIS within context of the CTA and will be RAd responsibility. Any requirement for import or export licenses for other clinical equipment, lab kits or materials would be managed outside of CTIS would remain the responsibility of the SAM,

- Monitoring of on-going IP Supply will be conducted according to CS_WI_SM0010, Investigational Product (IP) Handling and Monitoring. CL coordinates the maintenance of all import and export licenses for the project duration, including renewal of any license when required ( ML and CML may assist CL in this activity). LRSU Reps will support any needed submissions in their respective countries to maintain the Import/Export licenses throughout the project, unless otherwise stated in the COP.

{Note: Global Regulatory Affairs will perform the import/export activities, instead of Local RSU, in the following countries:}

# Site Ready to Enroll Activities

Refer to CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight for additional information regarding SRtE activities and role responsibilities.

{Instructions: Iinclude any deviations from SOP or WI or any information that SOP or WI indicates will be documented in the SAMP}

Overview of SRtE Activities

- SRtE activities are the combination of all activities required by the Sponsor and study protocol for an Investigator site which culminates in the following milestones:

- IP Release

- Site Initiation Visit (SIV)

- Site Activation

- Each milestone has required activities that must be met, ultimately leading to Site Activation. Figure 1.0 (below) lists all the activities that are required to meet each of these milestones. Many SRtE activities required for IP Release and SIV approval occur in parallel in order to expedite Site Activation, which is the final milestone indicating the site is ready to enroll subjects.

- SRtE Planning: The SAM, with support from the PL CL, PVM, and other applicable OTLs, is accountable to ensure the project specific SRtE activities are identified across all functions and the respective requirements and associated timelines are understood and included in the critical path plan for the study. Based on the critical path plan, each role will have clarity to the timeline expectations of their individual responsibilities (Equipment/materials, access, training, etc.). Any additional detail OTLs need to provide to their teams to execute will be provided in the respective plan (PVM via Vendor Management Plan, CL via COP, PL via Project Management Plan, etc.).

- SRtE KOM: Once the SRtE activities are identified and the critical path plan for the study is determined, the SAM will prepare content for a SRtE Kick Off Meeting (KOM). The SAM will conduct the SRtE KOM to review tasks, roles and responsibilities, and risk mitigation strategies for the site activation activities as documented in SAMP. Attendees include PL, CL, PVM, CML, CMA, and LRSU Rep(s). KOM content should be included in the study e-training for team members not assigned at the time of the KOM.

- Expanded SRtE RACI: The expanded SRtE RACI consolidates and expands on roles and responsibilities for SRtE activities as stated in applicable SOPs and WIs.

- SRtE Site Contact form: Site contacts who will need to complete/participate in SRtE activities

- SRtE checklist: Tracking mechanism to monitor site and study level progress to the overall plan and study timelines.

{Instructions: Using the examples and prompts below as a starting point, discuss the SRtE activities as required by your study design and Sponsor. Consider any critical items outlined in this plan and map your study specific critical path to Site Activation in Appendix A. Any activities noted below must specifically be detailed and explained in the appropriate section within this plan.}

Figure 1. {EXAMPLE ONLY- Critical path must be created with study specifics}

SRtE Roles & Responsibilities:

- Roles and responsibilities for SRtE activities will be carried out in the manner set forth in CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight and the SRtE Expanded RACI.

{ONLY list deviations and/or clarifications to the roles and responsibilities listed in CS_WI_RSU0068 and the SRtE Expanded RACI. For example, based on study resources assigned, specify if any of the below apply and update role referenced throughout the SRtE Plan:

- If no Centralized Monitoring Assistant (CMA) is assigned, the Centralized Monitoring Lead (CML) is accountable for CMA tasks; in rare cases where no CML is assigned, the Project Management Analyst (PMA) is accountable for CMA tasks.

- If no Project Vendor Manager (PVM) assigned, the PL is accountable for PVM tasks.

- If tasks assigned to the LRSU Rep will be performed by the CTA or Monitor and countries impacted are different than the countries in the APAC region and Japan whose country specific nuances are captured in their respective local Clinical Monitoring Requirements WIs.

Identification and Documentation of Site Ready to Enroll Activities

- SAM prepares the study specific Site Ready to Enroll Checklist requirements in accordance with this plan and with input from OTLs

- SAM provides the SRtE requirements to the project team in conjunction with Stage Gate Review 2.

- SAM adapts the SRtE requirements as necessary based on any project specific requirements that impact SRtE activities.

- CML sets-up the SRtE Checklist in the applicable system upon confirmation of the requirements from the SAM.

- The SRtE Checklist will be utilized to provide the status of progress on key SRtE Activities required for IP Release, SIV and Site Activation.

Note: The SRtE Checklist is recommended to be held as an internal living document. In case the team is requested to share the tracker externally, please discuss with the SAM Line Manager and/or Account Manager, if assigned. The completed SRtE Checklist export must be filed in the TMF at the end of Start-Up by the CMA.

- SAM conducts SRtE KOM.

SRtE Site Contact Form (CS_TP_RSU0082, Site Ready to Enroll Site Contact Form)

SAM partners with PL/PVM, CL, and Sponsor to customize the SRtE Site Contact Form to determine the key site roles and contact information necessary for SRtE activities.

- LRSU Rep will send the SRtE Site Contact Form to each selected site with the Site Selection Letter or when assigned to the study and they make the first contact with site.

- LRSU Rep will follow up with the site during regular contacts to obtain the completed form.

- Once received, LRSU Rep will review for quality and completion and {insert instructions for method to send completed form to Centralized Monitoring Assistant (CMA) e.g., upload the form to the study SharePoint}, will notify the CMA it is available copying the SAM.

- CMA updates the respective study trackers/systems using the completed SRtE Site Contact forms as described in the VMP and will track the receipt of the form in the SRtE checklist.

- Site contact information must be actioned as noted below by the referenced team members:

{Instructions: Edit list below as needed with required team members and respective systems}

- Centralized Monitoring Lead (CML): To track/distribute per vendor requirements and/or Vendor Management Plan, to trigger or request any project specific system access, for confirming IP shipment address is in the system of record (e.g., Trial Management System, manual tracker, etc.) {insert role and method for confirming IP shipment address for Interactive Response Technology (IRT) System}

- LRSU Rep: To track the site contact details in applicable Trial Management System, requesting support from cRSU via cRSU landing page for site contact information if needed.

- The SRtE Site Contact Form must be collected no later than {X weeks/months} prior to the planned Site Start-Up (SSU) completion date (PSSUCD/PCD). {For example, if equipment shipment takes 6 weeks from receipt of request you would need the Site Contact Form collected 6 weeks prior to planned SSU Completion date. Edit as required for study needs based on critical path planning}

- LRSU Rep will ensure the completed SRtE Site Contact Form, and any subsequently updated forms, are filed in the TMF during Start-up (either via cRSU Rep or directly). Only fully completed form(s) with accurate site details should be filed in the TMF.

Systems Access, Equipment and other Supplies

The purpose of this section is to provide detailed processes and procedures related to any SRtE activities where IP Release, SIV and/or Site Activation are dependent upon site staff access, training and/or certifications required by the Sponsor, IQVIA, or vendors (edit as appropriate).

- PVM is accountable and responsible for managing vendors and CML is responsible for triggering all SRtE activities as required by applicable vendors in parallel to the completion of the site’s EDP (as completed and projected by LRSU Rep). PVM may support CML in these activities.

Applicable SRtE activities for this project include completion of system access requests and shipping of equipment and supplies as detailed in the following tables:

{Instructions: In the respective tables below, please list applicable access and equipment requirements required for Site Activation. Add columns and rows as necessary to clearly describe all information required. Make sure to remove the example blue text and change font to black before finalizing}

| Systems Requirements and Access |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vendor or System Name | Training and Qualification Requirements | Access Request | Time Frame | Status Tracking System |
| {Enter Vendor/System Name} | {Enter Training and Qualification Requirements.} | {Enter Access Request process and requirements} | {Enter time frame needed for access request to be completed} | {Enter system or process for tracking access status.} |
| For example, Cenduit (IWRS) | Access: To be provided per SRtE Contact Form. Training: No formal training required. Training to be provided during IM or SIV. | CML to request Access to Vendor (XX@XXX.com if available) every Wed/Fri based on SRtE Contact form. | X days from the request of CML to vendor. The access email to be sent to site staff by XXX@XXX. com | CML and vendor to maintain a list of site users with access and to be filed in SharePoint (include link) |
| For example, Bioclinica Portal (central imaging) | Access: To be provided per SRtE Contact Form. Training: CML to request initial site training link to be sent to site. Site must complete training. LRSU rep to follow up with site to ensure completion. | CML to request access to Vendor (XX@XXX.com) upon receipt of SRtE contact form. | Training and access must be completed by site X weeks prior to PCD, so that test scan may be loaded. | CML to download a user report twice per week and track status in SRtE Checklist. LRSU Rep to report training status to SAM. |
| IQVIA Investigator Portal | None | CML to grant access upon receipt of SRtE Contact form. | Training and access must be completed by site X weeks prior to PCD, so that test scan may be loaded. | CML to download a user report twice per week and track status in SRtE Checklist. |

| Equipment and Supplies |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Vendor / Supplier Name | Equipment / Supply | Training and Qualification Requirements | Time Frame and Trigger | How to request shipment | Shipment Tracking System |
| {Enter Vendor / Supplier Name} | {Enter equipment / Supply type} | {Enter if any training requirements for study staff } | {Enter estimated timing of services and/or products being provided by vendors to site } | {Enter method to request shipment } | {Enter how shipments are tracked and receipt confirmed} |
| For example, QECG | ECG | PI, SC, Rater, Radiologist, etc. | ECG machine to arrive at site 4 weeks prior to SIV, 2 weeks for ECG delivery from the request) *If country requires proforma invoice review before shipment approval, the request of invoice to PVM must be made X days before actual shipment target date. | Email, tracker, system portal, etc. “CML to send email to vendor X days before PCD) *If country requires proforma invoice review before shipment approval, CML to request shipment after LRSU Rep/Monitor confirmation. Country list: | ECG system report and add link if applicable. Local RSU Rep to confirm receipt by appropriate site staff. Monitor to also confirm at SIV. |
| For example, Central Lab Vendor | Lab Kits | None | Lab kits to arrive at site 1 week prior to SIV and must be triggered 1 week in advance. *If country requires proforma invoice review before shipment approval, the request of invoice to PVM must be made X days before actual shipment target date. | CML to trigger lab kit shipment based on PCD and after applicable country level approvals are received (i.e. RA approval or import license) | CML to download central lab status from portal. Local RSU Rep to confirm receipt by appropriate site staff. Monitor to also confirm at SIV. |
| IQVIA Patient Recruitment | Patient ID Card | N/A | Patient ID Card to arrive at site 1 week prior to SIV and must be triggered 1 week in advance. | CML to trigger shipment based on PCD and after applicable country level approvals are received. | CML to solicit updates from Patient Recruitment Lead. Local RSU Rep to confirm receipt by appropriate site staff. Monitor to also confirm at SIV. |

Other Investigator and Site Staff Training:

Investigator training will be conducted according to CS_WI_PL0024, Project-Specific Training and Team Member Transition.

Note: IQVIA best practice is that all training and certifications are required for SIV so that Site can be activated as soon as SIV has been completed

The Investigator and/or site staff are required to additionally complete the following training/certification:

{Instructions: Include any additional training requirements required for Site Activation not already covered in another section of this plan (e.g., rater training), including:

- the required audience (site staff roles),

- timeline considerations required for IP Release (# of trainings, time estimate for training completion,

- Trigger time point and responsible role {Example: CML/CMA} for activity start and completion including escalation time point and responsible role {Example: LRSU Rep) if not complete

- Whether the training/certification is required for SIV and/or Site Activation

- IQVIA (and/or external) role who is required for obtaining confirmation of training completion and where confirmation is to be filed. {Example: CML will trigger initial request for site staff to complete training and Local RSU Rep will follow up with site until completion of training/certification.

- Make sure to remove the example blue text and change font to black before finalizing

- If no other training requirements, delete all text and list as “Not Applicable”}.

| Site Training and/or Certification Requirements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Training / Vendor Name | Training and Qualification Requirements | Required for IP Release, SIV or Site Activation? | Time Frame | Status tracking System | Role Responsible for confirming (LRSU Rep, Monitor, CML/CMA, etc.) |
| {Enter training / vendor name} | {Enter requirements for study, including roles required to complete training} | {Enter if training is required before IP release, SIV or Site Activation} | {Enter timing for training completion and trigger point for escalation if not completed by X milestone.} | {Enter how training and access status is tracked} | {Enter role responsible for confirming training has been completed} |
| Example: Rater Training Certification | Site must have 1 rater per scale {add number and type of scale}. Certification to be provided for TMF. | Site Activation | LRSU Rep to make initial request upon receipt of SRtE Contact form. Rater trainings/certification should be completed 2 weeks prior to SIV. | SRtE checklist | LRSU Rep |

Execution and Oversight of Site Ready to Enroll Activities:

{Instructions: Updated text below as needed with specific focus on responsibilities of CML and LRUS Rep with regards of execution of the SRtE activities so that these are tailored according to the specifics of project. Text covers standard IQVIA process as described in SOP}

- SAM oversees execution of SRtE progress and activities as outlined in this plan and in CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight

- SAM acts as point of escalation for status, progress and execution of Site Activation and conducts regular SRtE meetings to review progress, risk and mitigation and assign actions relevant to site activation.

  - CML oversees progress and completion of SRtE Checklist and Site Activation activities

- CML and LRSU Rep execute SRtE activities as outlined in this plan and CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight

  - CML responsibilities include following tasks:

    - Triggers or requests any site, IQVIA and vendor system access.

    - Updates any study level access and equipment tracker.

    - Triggers or makes initial requests for any study specific Investigator and/or site training/certification required to conduct the project to be provided to site (e.g., IRT System, EDC, Protocol and Study Procedures Training).

    - Study and vendor equipment/supply shipment requested or triggered

    - Non-IP supplies and equipment received at local depot and shipment to sites triggered or requested (when local depot required).

- LRSU Rep responsibilities include following tasks:

    - Confirms Planned SSU Completion Date (PCD), Planned SRtE Date, and site level updates are tracked in applicable appropriate systems (e.g., Trial Management System)

    - Essential Documents Pack (EDP) collection and approval

    - Follow up with site and confirmation that study supplies and equipment, if applicable, are available at site prior to SIV

    - Information on locally procured equipment sent to site tracked in Trial Management System per Sunshine Act requirements.

    - Follow up with site and confirmation of system accessibility by the relevant site staff

    - Preparation and Distribution of Investigator Site File (ISF) to site

    - Follow up with site and confirmation of completion of any Investigator and/or site training or certification required to conduct the project (e.g., IRT System, EDC, Protocol and Study Procedures Training, Rater training/certification)

RSU Country Level Meetings:

- LRSU Rep and SAM should refer to PACE Guidelines on Forecasting PCD and Site Activation for developing plan and forecast for delivery timelines.

- Throughout the process, it is also expected that:

- Project team communication will be frequent, timely and efficient

- SRtE status reporting, as a component to Site Activation, should become an agenda topic on the already scheduled team calls

- SAM will escalate any SRtE items to the designated responsible party (typically CL, CML or PVM) if their progress or completion is posing risks to the project timelines.

- In instances where any SRtE activity is at risk for extending beyond the PCD or scheduled SIV, the SAM will address the risk/issue with the Internal team and responsible Project Team Member. The responsible Project Team Member will work with the PL and SAM to review the mitigation strategy with the Sponsor.

Internal team meetings (at minimum weekly):

- CMA collects and tracks all site updates from the project team and updates the Site Ready to Enroll Checklist

- CML reviews the Site Ready to Enroll Checklist and initiates any requests/shipments following the instructions included in the Site Activation Checklist.

- SAM reviews site status and progress towards completion of Site Activation activities

Internal/External Team Meetings and Status Review

- SRtE status is reviewed as a standing agenda item during internal and external weekly team meetings at a minimum. {Instructions: Please list any planned study meetings applicable to SRtE.}

- If issues or delays are occurring due to the Sponsor failing to execute their respective responsibilities, the SAM will escalate to the PL for resolution via the process in CS_WI_PL0051, Project Issue Escalation and Management.

- Essential Document Pack, IP Release Requirements, Timing & Approval

- Refer to Section 13.0 of this plan, CS_WI_RSU0021, Essential Document Pack, project-specific COP and CS_WI_SM0010, IP Handling & Monitoring.

RSU Country and Site Transfer:

- SAM oversees the transfer process.

- Transfer of information on Core and Country Documents –occurs between LRSU Rep and Monitor(s) prior to first SIV in the country and it may occur via e-mail or may be done via formal meeting. LRSU Rep uses CS_TP_RSU0040, RSU Country and Site Transfer Checklist to document handover (Core and Country Transfer Tab).

- Transfer of Information on Site Documents– Transfer of Information on Site Documents occurs between LRSU Rep and Monitor and may occur via e-mail or may be done via formal meeting. Transfer is completed in two steps. The first step will occur before SIV and the second step will occur upon completion of all SRtE activities. LRSU Rep uses CS_TP_RSU0040, RSU Country and Site Transfer Checklist to document handover (Site Transfer Tab).

Site Activation:

Prior to approving Site Activation, the following criteria must be met:

- For US Sites Only: Protocol has been submitted to the FDA

- For Canadian Sites only: Clinical Trial Site Information (CTSI) form has been sent to Health Canada

- <enter additional study specific requirements required for Site Activation (e.g., Site Training completion, confirmation of equipment and/or supplies on site, confirmation of lab kits on site, confirmation of ISF on site)>

- CML confirms to SAM and CL the status of activities per the SRtE requirements; whether all activities are completed or there items left to be completed/verified during SIV to activate the site.

- SAM completes and signs the Site Activation Approval Form (SAAF) and sends it to the Sponsor for approval, if required.

- SAM notifies CL and Monitor in writing when site is approved for IP release, SIV and/or site activation (open for enrollment) indicating any follow up items, if applicable. The email must include, at a minimum, the signed SAAF as an attachment or link.

- SAM enters “SIV Approval Date” and “Authorization for Site Activation” in the Trial Management System and files all signed versions of SAAF in the TMF.

- CL activates the site in IRT system and informs SAM and Monitor

- Monitor changes site status to “Enrollment Open” in applicable Trial Management System as described in CTMS Guidance Documents

- LRSU Rep enters actual Site Ready to Enroll date in Trial Management System upon Site Activation

# Essential Document Pack Collection & IP Release Process

Provide documentation needed for IP release, site initiation and activation. Refer to: CS_WI_RSU0021, Essential Documents Pack

{Iinclude any information the SOP indicates will be documented in the SAMP. Update the text below as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members.

- SAM, in combination with the Sponsor, completes the CS_FM_RSU0047 Essential Documents Pack-Requirements Form (EDP-RF)

- SAM creates the project specific Essential Documents Pack – Review Checklist and provides instructions to the LRSU Rep

- LRSU Rep collects, reviews, and compiles the EDP components and submits for IQVIA approval

- Once EDP is approved, Site Activation Approval Form is prepared for final IP release

| Document | Link to Study Specific Template | Reference Document |
| --- | --- | --- |
| Essential Documents Pack -Requirements Form (EDP-RF) |  | CS_FM_RSU0047 |
| Essential Documents Pack – Review Checklist (EDP-RC) |  | CS_TP_RSU0050 |
| Essential Documents Pack - Review Guidelines |  | CS_TP_RSU0049 |
| Site Activation Approval Form (SA_AF) |  | CS_FM_RSU0048 |

Note: IQVIA standard is to collect electronic copies of all documents required for the Essential Documents Pack. We do not collect wet-ink (paper) versions of the documents unless required by local regulation or by Sponsor.

{If Sponsor requires wet-ink documents to be collected for certain document types (e.g. Form FDA 1572) the documents must be listed in this section AND ALSO on the EDP-RF. It must also be clear whether the wet ink document is required in order to activate the site, or if it can be collected later.}

Deviations from CS_WI_RSU0021 – Essential Documents Pack:

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.

- Any deviations from IQVIA standards for Essential Documents should be captured on the EDP-RF and do not need to be documented in the SAMP.

- Document who is signing SAAF if someone other than SAM (e.g., Sponsor).

- Any activities that cRSU may be performing that are not assigned to cRSU in the SOP will need to be documented here.

- If Sponsor is going to review the Essential Documents in addition to IQVIA review or instead of IQVIA review.

- If Sponsor’s checklist will be used instead of IQVIA (or in addition to IQVIA).

# Investigator’s Site File

Refer to project-specific COP and CS_WI_SM0007, Investigator’s Site File for set-up and content.

LRSU Rep prepares the individual ISF binders for each of the Investigator sites as per CS_WI_SM0007. Upon approval of EDP for each site, ISF binders are shipped to the site by the LRSU Rep or Monitor/CTA, based on local practice (Monitor/CTA in some countries (e.g., Asia Pacific countries)).

The responsible party for shipment is to confirm both shipment and receipt of ISF to the site.

# Handover and Transition Activities during a Clinical Study

Handover and Transition of Key Team Member ( KTM)

Handover and Transition between SAM to SAM, ML to ML or between different roles when there is a transition of responsibilities and scope of activities ( e.g. between SAM and ML when there is ongoing global amendment) will follow process for KTM Transition as per CS_WI_PL0024, Project-Specific Training and Team Member Transition

# Reporting

Document start-up progress in IQVIA’s Trial Management System.

{Update the text below as appropriate – add or delete text as needed.}.

Start-up tracking will be done using the IQVIA Trial Management System Guidance documentation. The CTMS and SAM toolkit reports will show progress related to Site ID Status, Ethics Submission Status, Contract Status, Clinical Trial Application Submission and Approval Status, Document Overview and SIV status. SAM will oversee the start-up tracking and will provide the following reports to the Sponsor. {Update to add list of reports as agreed with Sponsor}

Reports will be provided to Sponsor project/program team {Insert frequency here as agreed at the KOM.}

# Project Team Training

GSA staff be trained according to the needs of the protocol/program. Refer to: CS_WI_PL0024, Project-Specific Training and Team Member Transition

{Per the SOP, the project specific GSA/start-up training must be documented in the SAMP, including clear reference to “who/what/when/where/how”. SAM should work with the PL/PMA to ensure the recording of the GSA/start-up training is uploaded to eTraining, or it must be clearly documented where the training is located (e.g., Sponsor-specific training system). Update the text below as appropriate – add or delete text as needed.}

The SAM provides project specific start-up related training for LRSU team members. Topics for training may include: Site ID process, SAMP, ICF, SRtE , project-specific work instructions, contracts and budget parameters and negotiations, Sponsor SOP(s), EDP-RF and IP release process

Project Team Training and Protocol specific training is the responsibility of the PL/CL.

Project GSA team training for this project is listed below:

{Instructions: The table below must include training, at a minimum, that must be completed as project-specific start up training for the project team, how training is provided, who is providing the training, who and when should perform/attend the training, location of training material, process for accessing the training if applicable. It is recommended that at a minimum the table must include the SAMP, SRtE activities ( i.e. requirements, roles and responsibilities) and the EDP-RF. Make sure to remove the example blue text and change font to black before finalizing}

| Training | Role Required | Training Method | Timing | Location/Link |
| --- | --- | --- | --- | --- |
| Site Ready to Enroll requirements and Local Roles & Responsibilities | SAM to PL, CL, PVM, CML, CMA, LRSU Rep (Monitor/CTA if applicable e.g. APAC countries) | Recorded SRtE KOM Teleconference | Stage Gate 2 | Study eTraining |
| SAMP | SAM to LRSU Rep, PL, CL, PVM, CML, CMA, Monitor/CTA ( if applicable ( e.g. APAC countries | Provision of final SAMP | LRSU Rep/Monitor/CTA assignment & onboarding | Study eTraining |
| EDP-RF | SAM to LRSU Rep | Recorded Teleconference | EDP-RF finalization | Study eTraining |

The SAM/ML is responsible for reviewing GSA Team Members’ training records for the project to ensure they are compliant with training assignments and are receiving the required training prior to a process being implemented on the project. The SAM discusses non-compliance issues/discrepancies with the GSA Team Member (and their LM if needed).

# Translation

Translations related to all applicable documents will be done following IQVIA SOPs. Refer to: CS_WI_RSU0032, Translation of Documents

{Iinclude any information the SOP indicates will be documented in the SAMP. Update the text below as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}.

IQVIA SOPs will be followed for translation of documents, unless translated documents are provided by the Sponsor.

{INSERT: Describe whether translations will be performed by central preferred vendors or by IQVIA Translation Platform (ITP) for studies that were sold with IQVIA Translation Services (to find out if your study is eligible to use ITP use the easy tool.}

For every translation request cost and timelines need to be evaluated in order decision to be taken if standard or rush services to be used.

{INSERT: if Japan is part of the project, most translations of the major project documents will be managed by Sponsor. A detailed accounting of the division of the responsibilities must be documented in this section or in an attachment to the SAMP.}

{INSERT: If back translations are required by the Sponsor and approved by the PL (or if required by local regulations), they will be performed as documented in the SOP or Sponsor-specific process must be described here.}

{INSERT: Describe whether IQVIA or Sponsor is responsible for translation of patient questionnaires and scales, following their own SOPs. If any action is required for Local RSU, training will be needed on the Sponsor SOPs.}

Deviations from CS_WI_RSU0032 - Translation of Documents

{If there are no deviations, state “Not Applicable”. Otherwise list the planned deviations here. The examples below are the most common, but other deviations may need to be recorded.

- Any activities that cRSU may be performing that are not assigned to cRSU in the SOP will need to be documented here.}

# Out of Scope work

Out of scope work is any request for additional work or changes to the agreed scope that are not already included as part of the original scope of work or in a change order. This includes any request to accelerate or compress project timelines. Refer to: CS_WI_PL0018, Project Scope

{Iinclude any information the SOP indicates will be documented in the SAMP. Update the text below as appropriate – add or delete text as needed. Remember, if we will use Sponsor SOPs for any or all of these tasks, include a summary of the Sponsor process and provide copies of the SOPs to the appropriate team members}.

SAM/ML/RAd should identify the out-of-scope changes (i.e., requested activities by Sponsor or IQVIA that are outside of currently established Scope of Work, schedule, budget, and risks) and communicate it to the PL and PMA.

The SAM/ML/RAd will refer these changes to the PL and project team for review and assessment prior to implementation. Planning discussions will consider overall project objectives, project plans, and potential risks (of implementing or not implementing the change). PL must approve any change requests and will follow process detailed in CS_WI_PL0018, Project Scope, to document the approved changes. The identified out of scope changes should be added to the study-specific Change Control Log to ensure adequate budget is agreed and allocated to perform the additional activities prior to work starting.

SAM/ML will update GSA documentation as required for any agreed scope change (e.g. SAMP or EDP-RF) and will update any eTraining that may be associated with the updated documentation.

# Appendix A Critical Path Planning

Instructions: Using the prompts in Figure 1. use the timeline below to describe the activities required for each timepoint leading up to site activation.

Site Activation

| Start-Up Stage | EDP -6 weeks | EDP -5 weeks | EDP -2 weeks | EDP -2 days |
| --- | --- | --- | --- | --- |