|  | IQVIATM Work Instruction Site Identification and Selection |
| --- | --- |
|  | Document Number and Revision: CS_WI_RSU0065 Revision 4 |
| Document Owner: Mary Beatty | Author(s): Sara Crowell, Samuel Masih |

# PURPOSE

To describe the process for the identification and selection of Investigator site(s).

# SCOPE

  - This Work Instruction (WI) applies to projects for which IQVIA RDS is scoped to identify and select Investigator sites for participation in the project.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Site Analytics Lead (SA Lead) | 6.1 |
| Project Leader (PL) | 6.1, 6.2, 6.3 |
| Site Activation Manager (SAM) | 6.1, 6.2 |
| Country Site Activation Representative (CSA Rep) | 6.1, 6.2 |
| Clinical Lead (CL) | 6.2 |
| Global Site ID Lead (GSID Lead) | 6.1, 6.2, 6.3 |
| Therapeutic Medical Advisor (TMA) | 6.1 |

Notes:

- For projects where no SAM will be assigned, the CL performs the tasks assigned to the SAM. For projects where GSID Lead will not be assigned, the SAM performs the tasks assigned to the GSID Lead. For projects where SAM is not yet assigned, the Global Site Activation Analyst (GSAA) performs the tasks assigned to the SAM. For projects where no TMA is assigned, the Medical Strategy Lead (MSL) performs the tasks assigned to the TMA.

- For more information on the spilt between SAM and GSID Lead as to which role is performing tasks during Site ID, refer to Appendix A: GSID Lead and SAM Split of Responsibilities.

# DEFINITIONS

Refer QG_OD_SMT0018, Glossary of Terms – Clinical Services, for definitions.

Confidential Disclosure Agreement (CDA): A signed agreement between two parties (for example, Sponsor and IQVIA, or IQVIA and a site) that authorizes confidential study or product information to be exchanged between the two parties. Also known as a Confidentiality Agreement.

Optimized Site ID and Selection: Process using Investigator data along with a Site Selection Questionnaire (SSQ) to inform selection decisions based on experience, quality, and performance.

Initial Site ID Strategy: Strategy agreed on and documented during the Knowledge Transfer Call (KTC). This is the strategy communicated to CSA Rep during the Site ID Vetting Instructions Meeting (VIM).

Re-opened Site ID: The need to identify additional sites after 100% of the sites were selected according to the initial strategy or according to an updated Site ID strategy that was implemented while initial Site ID was ongoing (i.e., before or during site outreach).

Site Selection Questionnaire (SSQ): A project-specific questionnaire designed to document and assess a potential Investigator site’s interest, qualification, and capabilities for participation in a study (i.e., site details and questions about site’s interest in participating, Protocol concerns, recruitment potential, facilities, and equipment).

Tiered Site List: A prioritized list of potential Investigators that are deemed suitable to participate in a trial based upon the information about them available via internal and external data sources. Investigators are tiered (prioritized) based on multiple data points. Only the following information can be shared with the Sponsor: Country / Site name / Investigator last name / Investigator first name / Email address / State / City / Address / confirmation that Investigator/site participated in previous trial with the same Sponsor. Additional information can be shared in a blinded fashion: patient volume (only as high/medium/low) and Investigator experience in the indication (yes/no). No reference to tiering should be shared with the Sponsor. The information received from the SA Lead within the Tiered Site List is proprietary information and cannot be released in full to the Sponsor.

Trial Management System: When referencing “Trial Management System” throughout this WI, this infers tracking directly into CTMS or other IQVIA trial management systems.

Updated Site ID Strategy: A change in the ‘Sites Selected’ targets (on country-level or global) and/or addition of countries.

Vetted Site List: Tiered Site List that has been reviewed within each country to confirm suitability of the sites. Country staff may make recommendations on sites to be added or removed from the list. Guidance regarding vetting is referenced within Site ID training within the GSA Academy (Refer to Section 7.0).

Note: Tiering information is now also available in some of our Trial Management System reports and must be removed before sending to the Sponsor.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

The SAM is responsible to manage and oversee Site ID and Selection as per CS_OP_RSU0060, Site Activation.

Note: In addition, each role mentioned in this WI is responsible to:

- Ensure tracking, status reporting, risk/issue identification and mitigation of activities to support site activation in applicable systems as per CS_OP_RSU0060.

- File individual documents or pertinent correspondence in the Trial Master File as they are finalized as per CS_OP_RSU0060.

  - Site Identification

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | PL | Confirms Site Identification Strategy - Receives the pre-award strategy from the Therapeutic Strategy Lead (TSL), including Investigator and site profiles, and confirms the process for site communications (refer to CS_WI_TSS0004, Project Strategy and Proposal Development and CS_WI_PL0023, Project Lifecycle Planning) - In collaboration with the TSL, confirms the post-award strategy, in accordance with CS_WI_PL0023, Project Lifecycle Planning. - Confirms that GSID Lead is in scope and assigned to the project. Note: Invite the GSID Lead to provide Site ID guidance and Site ID process timelines prior to the Customer Expectation Meeting. | Setup |
| 6.1.2 | GSID Lead | Prepares the Knowledge Transfer Call (KTC): Reviews information in the Proposal Knowledge and Information Transfer (P-KIT) received/obtained from the PL/TSL and the Communication Elements Document (refer to Section 7.0) to prepare for the KTC. |  |
| 6.1.3 |  | Confirms Site Identification and Selection process - Schedules the KTC to be attended by PL, TSL, SA Lead, Feasibility Analytics Lead (FAL) (if applicable), Analytic Strategy Lead (ASL), MSL and TMA, Operational Deployment Lead (ODL), CL and SAM, if assigned. Optional attendees include members of the applicable Center of Excellence, Site Services Support (SSS) team, Decentralized Clinical Trial Lead (DCTL), and Diversity Lead. Refer to Section 7.0 Knowledge Transfer Call Checklist (KTC Checklist) when planning and executing this meeting. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Confirms and/or updates the pre-award strategy during the KTC, with support of KTC Checklist. - Ensures the project team understands the country strategy and site/Investigator profile. - Drafts proposed initial site/investigator communication referencing the completed Communication Elements Document, if applicable, for approval by TSL, MSL, PL and CL. - Makes certain the following details have been confirmed by the SAM, with the Sponsor, if the use of Sponsor-preferred sites is proposed: - If sites are mandated or suggested - Acceptance of research naïve sites - Acceptance of the use of satellite sites - Requirements for the addition of sites or Investigator name changes - Follows up with CL and SAM to determine how to select a site for study participation as per CS_WI_SM0005, Monitoring Visits. Note: It is recommended that an agreed upon percentage of IQVIA naïve and/or research naïve sites be distributed based on project-level agreements. Best practice: It is recommended that Sponsor list is provided as a single file received prior to the site list development. At minimum Sponsor should provide the site name, address, country, email address of preferred investigators and flag any sponsor-mandated Investigators, if available. |  |
| 6.1.4 | PL | Trial Management System Set Up Uses CS_WI_PL0052, Project Systems Management, to confirm systems required for Site ID implementation are appropriately launched for set-up (e.g., QRPM, Trial Management System, etc.). Note: The project code must match between all Trial Management Systems. If the Protocol number and project code do not match, this will prevent site promotion via Trial Management System causing delay. | Setup |
| 6.1.5 | GSID Lead | Requests CSA Rep resource Submits QRPM CSA Resource Request Template (refer to Section 7.0) | Following Site ID strategy |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.6 | CSA Rep | Country Specification Review Receives the KTC Checklist from GSID Lead and provides insight into country-level information which can be incorporated into the development of the Tiered Site List. | Following Site ID strategy |
| 6.1.7 | TMA | - Reviews feedback from Country Specification Review and all assumptions used by the SA Lead to ensure correct Site and Investigator profiles are targeted for development of the Tiered Site List. - Corrects assumptions and provides recommendations for additional attributes to be considered, if needed. Note: The TMA is responsible and the MSL is accountable. |  |
| 6.1.8 | SA Lead | Generates Tiered Site List Receives finalized ideal Site and Investigator profile. Creates the Investigator list from internal and external data sources, adding any Sponsor mandated sites to generate the Tiered Site List. | Following KTC |
| 6.1.9 | GSID Lead | Determines Confidential Disclosure Agreement (CDA) Factor - Determines in collaboration with SA Lead the appropriate number of sites for outreach in order to meet site selection targets based on specific project attributes (i.e., therapeutic area, study phase, geographic area), called the CDA Factor. - Documents CDA Factor and rationale within the KTC Checklist. |  |
| 6.1.10 |  | Confirms Qualifying Sites for Optimized Site ID and Selection Confirms qualifying top tiered sites (Tier 1, High Priority (HP) Tier Prime and APAC Phase 1 Oncology Priority Sites*) based on last 12-month experience and capabilities to conduct the study against the site profile and tiering results. *APAC Phase 1 Oncology Priority sites may be selected for Optimized Site ID and Selection, regardless of Tier. APAC Priority Sites are identified on the Global Phase 1 Oncology Master List. Any APAC Phase 1 Oncology Priority Tier 2 and Tier 3 sites must have had an on-site visit within the last 12- months and the on-site Ph 1 Oncology Questionnaire completed. | Following Tiered Site List |
| 6.1.11 | SA Lead | Makes Tiered Site List available to CSA Reps - Uploads the Tiered Site List to applicable Trial Management System. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Makes sure the site name / information is consistent across all projects in the Trial Management System if a site number will be duplicated across multiple projects (to avoid causing potential issues in the EDC access). |  |
| 6.1.12 | GSID Lead | Site ID Vetting Instructions Meeting (VIM) - Required team member attendees are PL, CL, SAM, CSA Rep, DCTL, and SA Lead. SSS Team members are optional attendees. - Utilizes all key strategy components documented within the KTC Checklist to generate clear vetting instructions for CSA Reps. - This will include but is not limited to: - Protocol overview, Protocol/Therapeutic overview - Competitive landscape - Customer expectation - Investigator specialty - Site profile and patient profile - If applicable, which countries are known to be able to conduct Decentralized Clinical Trials (DCT) - Optimized Site ID and Selection - Country vetting parameters - Site List development - Vetting instructions for the site list - Configures and sets the country targets within the applicable Trial Management System. Distributes the VIM slides to applicable CSA Reps as well as to the key contact for SSS team in North America. - Uses Site Identification Vetting Instructions Meeting template (refer to Section 7.0) to ensure all necessary items are in place. | Following Tiered Site List |
| 6.1.13 | SA Lead | Provides input into the VIM slides with focus on site/patient profile, vetting parameters, and instructions, as applicable. |  |
| 6.1.14 | SAM | Monitoring Contribution Informs CL of anticipated Tier 1, HP, and Tier Prime site percentages as indicator for Site Selection Visit (SSV) resourcing needs. | After initial tiered list is created and throughout site ID and selection activities. |
| 6.1.15 | CSA Rep | Performs Local Vetting of Potential Sites Receives Tiered Site List and refines based on local intelligence and vetting guidelines, identifying the Investigators and sites to be included in the final Vetted Site List: | Following Tiered Site List |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Clearly documents in the Trial Management System the justification and rationale for recommendation or rejection of the site. - Verifies that all mandatory site contact information is available and that all site data is correctly entered in the applicable Trial Management System. - Contact e-mail addresses cannot be from a public e-mail service provider where sending Sponsor confidential information would be subject to terms and conditions granting additional ownership. - Identifies and reviews any publicly available listings from local regulatory authorities for their assigned country(ies) (except US FDA) if listed as applicable within the country Local Clinical Monitoring Requirements Work Instructions. - Highlights on site list any Investigators and site accounts that have been assigned a Flagged Quality Assurance (QA) Status, as per CS_OP_QA0232, Investigator Compliance Status and Management of Investigators with Non- Compliance Issues. - Verifies applicable Trial Management System is updated if incorrect and/or missing data is identified. - Refer to CS_OP_QA0232 if QA – Review of Investigators (QA-RI) status is incorrect and process for US FDA review. Notes: - This review can also include suggestions of new sites not in the initial list if they meet the study specific site profile and are accompanied with sufficient justification. - If project is firewalled for Business Conflict of Interest (BCOI) reasons, new sites proposed by the CSA Rep that are not included in the Tiered Site List provided by the SA Lead must be vetted back through the SA Lead before contact with the sites. |  |
| 6.1.16 | GSID Lead | Reviews Vetted Tiered Site List Reviews vetted Tiered Site List with the project team within the timelines established during the Site ID VIM. Consults with the SAM throughout the Site ID phase to verify that the number of sites required by the study strategy are identified and the agreed site strategy is kept intact. | Following vetted Tiered Site List |
| 6.1.17 | TMA | Reviews vetted Tiered Site List containing list of atrributes and weighting used, provided by GSID Lead. Consults with SA Lead and MSL Note: The TMA is responsible and the MSL is accountable. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.18 | GSID Lead | Reviews Final Vetted Tiered Site List Reviews final vetted Tiered Site List using the appropriate Trial Management System. | Following vetted Tiered Site List |
| 6.1.19 |  | Conducts Site ID Vetting results and Study Expectations Meeting (SVREM) - Conducts the SVREM with SAM. GSID Lead will focus on site strategy, site profile and tiering methodology with all assigned CSA Reps. SAM will focus on Sponsor specific processes, documents, templates, and escalation requirements. - Presents the vetting results to the project team, ensuring the strategy is aligned with Sponsor expectations. - This meeting is mandatory and must be conducted prior to site list distribution to the Sponsor. Required team member attendees are: PL, CL, SAM, CSA Rep, and DCTL, TSL and SSS team ODL attendance is optional. - This will include but is not limited to: - Site ID Vetting results - Site list development attributes - Country challenges during site vetting - Study Site ID expectations - Optimized Site ID and Selection contribution and monitoring oversight - Correct messaging of study as agreed within the initial site outreach communication plan - CDA/SSQ instructions - Uses Site Identification Vetting Results and Study Expectations Meeting template (refer to Section 7.0) to ensure all necessary items are in place. Note: At the close of the meeting all CSA Reps will have information required to execute the Site ID strategy. They will have received instructions for CDA and SSQ management together with expected timelines from SAM. |  |
| 6.1.20 | SAM | Sponsor authorization of Final Vetted Site List - Sends to Sponsor for authorization if required. - Authorizes CSA Reps to promote approved Investigators in applicable Trial Mangement System. Note: Enriched Sponsor output can be provided but authorization and timeline must be obtained from SA Lead. | After SVREM |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.21 | CSA Rep | Promotes Vetted Sites to the Selection Phase - Promotes approved Investigators without a flagged QA status to the Protocol Country list in applicable Trial Management System. - Consults with CL to promote Investigator and/or site accounts, with a flagged QA Status as defined in CS_OP_QA0232, as needed. | Following Final Vetted Site List |
| 6.1.22 | GSID Lead | Uploads the list of Investigators and sites to the available technology platform using the appropriate report from the Trial Mangement System. |  |

  - Site Selection

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | SAM | Confirms Confidentiality Requirements - Confirms if a Confidentiality and/or Non-Disclosure Agreement (collectively referred to as ‘CDA’ throughout this WI) is required. - Where a CDA is required, for each site, determines the type of CDA that should be used: - If a CDA is not required or is already executed (e.g., Master CDAs (mCDA) proceed to next step. - If an existing CDA template is not used, confirm the appropriate CDA template and fallback language to be used. - Confirms with the Sponsor whether the CDA can be sent together or before the SSQ, or whether the SSQ can be sent only after CDA is executed. - Provides the final CDA template and fallback language (if applicable) to CSA Rep. Notes: - Sponsor CDA templates may be used without seeking IQVIA Legal and the Contract Budget Specialist Lead (CBSL) approval if they do not place further obligations on IQVIA. - If the Sponsor requests revisions to CDA template that are not covered by IQVIA Legal CDA guidance, request CBSL review of the proposed CDA language. | Following Award |
| 6.2.2 | GSID Lead | Creates Site Outreach Email Template - Creates the site outreach email to be used when contacting the sites with CDAs or blinded SSQ depending on the agreed approach. | Following Site ID strategy |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Includes language provided by MSL, and agreed with Sponsor, to ensure all relevant points needed to raise interest from the investigator/site perspective. |  |
| 6.2.3 | GSID Lead | Creates SSQ content - Creates project specific SSQ and annotated SSQ using CS_TP_RSU0063, Site Selection Questionnaire. - Consults with CL to ensure relevant questions are included, including those relating to clinical supplies and equipment needed at the sites as per CS_WI_SM0027, Provision of Clinical Project Supplies and Equipment to Investigator sites. - Consults with MSL to ensure relevant questions to determine investigator and site capabilities are included in the SSQ. - Delivers to PL, TMA/MSL, CL, and SAM to review to ensure only questions that determine if the site is suitable for inclusion in the study are included and to ensure additional documentation or templates, such as the SSV Report or instructions, are aligned and not duplicative of the SSQ. | Following Site ID strategy |
| 6.2.4 | PL | - Obtains Sponsor approval of the SSQ if required. - If changes are required, step 6.2.3 is repeated until final. | SSQ content is final |
| 6.2.5 | GSID Lead | SSQ for programming - Creates the SSQ via the available technology solution. - Shares the SSQ with CSA Rep and SAM via the technology solution. Notes: - All CSA Reps need to be assigned. - If a paper SSQ is needed (as an exception) it can be produced from the technology solution. | Following SSQ finalization |
| 6.2.6 | SAM | Creates the project-specific Selection, Non-Selection, and Back-up Letter Templates - Creates the project-specific templates using CS_TP_RSU0004, Site Selection and Non-Selection Letter, with site specific details provided by CL if required for letter. - Distributes the template letters to assigned CSA Reps. | Following Award |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.7 | CSA Rep | Contacts Sites for Selection: CDA - Approaches promoted sites to confirm their interest in participating in the study in line with confidentiality requirements and Communication Elements Document. - Verifies that a fully executed CDA is in place prior to SSQ delivery, if a CDA is required. Notifies the SAM if the site requests changes to the approved CDA template that places obligations on IQVIA, to facilitate consultation and approval of the requested change. Note: CBSL does not review site requested changes to Sponsor obligations or that require interpretation of fallback language. | Following Finalized Tiered Site List |
| 6.2.8 |  | Contacts Sites for Selection: SSQ Ensures all finalized CDA, SSQ and follow-up attempts are tracked in the Trial Management System. Note: When using paper SSQs, populates the SSQ with previously collected site specific information, when available, and distributes the SSQ to the sites for verification and completion. | Following CDA execution (if required) |
| 6.2.9 |  | Evaluates Site SSQ Responses - Obtains completed SSQ and evaluates site responses based on the requirements contained in the annotated SSQ, contacting sites for clarification as needed. - Approves or rejects the site as a potential candidate. - For sites requiring SSV, designates SSV requirement “on- site”, “remote”, or “waived” based on the criteria outlined in CS_WI_SM0005, Monitoring Visits. - Updates status in applicable Trial Management System accordingly to whether an SSV is required: - For Optimized sites that meet the pre-agreed selection criteria, mark ‘Selected,’ SSV Required as “No,” and SSV Type as “N/A.” - For non-Optimized sites that meet the pre-agreed selection criteria, mark “Approved for SSV” - For non-Optimized sites that meet the criteria for a waived SSV, mark SSV Required as “No” and SSV Type as “Waived.” - For rejected sites that do not meet the pre-agreed selection criteria, select “Rejected for SSV” - Changes site status to “Not Interested” or “Non-Responder” based on Site ID strategy defined in the Site ID SVREM. | Upon receipt of each SSQ |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Tracks all finalized CDA, SSQ and follow-up attempts in the Trial Management System, including rationale for rejecting a site and/or reason(s) why a site declined to participate in the study. |  |
| 6.2.10 | CL | Verifies SSV Completion Where required, verifies that SSV and SSV Report have been completed in accordance with CS_WI_SM0005, Monitoring Visits. | Following SSV completion |
| 6.2.11 |  | Evaluates Sites for Final Selection - Determines, based on Monitor recommendation post SSV, if site qualifies for inclusion in the study. - Updates the site’s status accordingly within the Trial Management System to whether the site is “Selected”, “Not Selected”, or will serve as a “Back-up” site. - Escalates the request in accordance with CS_OP_QA0232 if Principal Investigators (PI), site accounts, and/or Sub- Investigators (Sub-I) with a flagged QA Status are requested for inclusion by the Sponsor. | Throughout site selection |
| 6.2.12 | SAM | Internal Site ID Call Schedules a weekly call with the CSA Rep(s) to review Site ID status. GSID Lead attendance is optional. |  |
| 6.2.13 | GSID Lead | - Monitors trending data to validate site strategy until all sites are selected. Ensures SAM is provided with current status and site counts. - Schedules a strategy check in call with the SAM, depending on study progression. - Monitors Site ID compliance against study interest. |  |
| 6.2.14 | CSA Rep | Notifies Sites of Selection Status - Uses the project-specific Site Selection and Non-Selection Letter templates to notify the site if they were selected, not selected or are back-up sites. - Obtains key site details for selected sites using CS_TP_SM0073, Site Ready to Enroll Site Contact Form. | Decision is made about site selection or non- selection |

  - Re-opening Site Selection

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | PL | - Makes the decision that additional sites are required and documents the decision to re-open Site ID. - Requests resources for GSID Lead allocation. | Ongoing during study |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.2 | GSID Lead | - Schedules strategy check-in call to align the study team on the strategy for Re-opened Site ID to be attended by: PL, TSL, TMA, SAM, CL, FAL and ODL. Optional attendees include: ASL, SAL, SRM, PSM, and Center of Excellence (COE) reps. - Prepares for the call according to the Re-opened Site ID Guidelines Document. - Records outcome of this call using the Strategy Check-in Checklist (Refer to Section 7.0). | After confirmation from PL to re- open site ID |
| 6.3.3 |  | Requests CSA Rep resource Submits QRPM CSA Resource Request Template. |  |
| 6.3.4 | OTLs | Refers to applicable steps within 6.1 and 6.2 in this WI using Site ID Re-Opening Decision Tree and Guideline to guide which step is the starting point depending on each scenario. |  |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| 7.2 CS_OP_RSU0060 | Site Activation |
| 7.3 CS_WI_PL0023 | Project Lifecycle Planning |
| 7.4 CS_WI_TSS0004 | Project Strategy and Proposal Development |
| 7.5 CS_WI_SM0005 | Monitoring Visits |
| 7.6 CS_OP_QA0232 | Investigator Compliance Status and Management of Investigators with Non-Compliance Issues |
| 7.7 CS_WI_SM0027 | Provision of Clinical Project Supplies and Equipment to Investigator Sites |
| 7.8 CS_TP_SM0073 | Site Ready to Enroll Site Contact Form |
| 7.9 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| 7.10 CS_TP_RSU0004 | Site Selection and Non-Selection Letter |
| 7.11 CS_TP_RSU0063 | Site Selection Questionnaire |
| 7.12 CS_WI_PL0052 | Project Systems Management |
| External References |  |
| 7.13 QRPM CSA Resource Request Template | QRPM CSA Resource Request Template |
| 7.14 CDA Template Library | CDA Template Library |
| 7.15 GSA Academy | GSA Academy |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.16 Site ID Re-opening Decision Tree and Guidelines | Site ID Re-opening Decision Tree and Guidelines |
| 7.17 Site Identification Vetting Instructions Meeting Template | Site Identification Vetting Instructions Meeting Template |
| 7.18 Site Identification Vetting Results and Study Expectations Meeting template | Site Identification Vetting Results and Study Expectations Meeting template |
| 7.19 Strategy Check-in Checklist | Strategy Check-in Checklist |
| 7.20 Communication Elements Document | Communication Elements Document |
| 7.21 Knowledge Transfer Call Checklist | Knowledge Transfer Call Checklist |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_RSU0065 | Site Identification and Selection | 3 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Updated LSID Rep and LRSU Rep to CSA Rep | Section 3.0 and throughout | Change in role title |
| Therapeutic Medical Advisor added | Sections 3.0 and 6.1 | Process Change |
| Added “For projects where no TMA is assigned, the Medical Strategy Lead (MSL) performs the tasks assigned to the TMA” | Section 3.0 | Process Change |
| Added Note: “For more information on the spilt between SAM and GSID Lead as to which role is performing tasks during Site ID, refer to Appendix A: GSID Lead and SAM Split of Responsibilities.” | Section 3.0 | Process clarification |
| Updated Optimized Site ID and Selection definition | Section 4.0 | Change in terminology |
| Added definitions for “Initial Site ID Strategy,” “Updated Site ID Strategy,” and “Re-opened Site ID.” | Section 4.0 | Clarify standard terms |
| Wording change to put the action first in the sentence and added reference to CS_WI_PL0029 | Step 6.1.1 | Process clarification |
| Added step for the GSID Lead to prepare the Knowledge Transfer Call | Step 6.1.2 | Process clarification |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Edited text to make clear who attends the meeting as mandatory and optional attendee | Step 6.1.3 | Process clarification |
| Deleted reference to P-KIT as that was moved into step prior | Step 6.1.3 | Process clarification |
| Added “Drafts proposed initial site/investigator communication referencing the completed Communications Elements Document, if applicable, for approval by TSL, MSL, PL and CL.” | Step 6.1.3 | Process change |
| Removed “in accordance with the IQVIA Site Overage Policy” from the Note | Step 6.1.3 | Process change |
| Removed reference to CS_TP_RSU0070 | Step 6.1.3 and throughout | Document made obsolete |
| - Added (“e.g., QRPM, Trial Management System, etc.)” - Corrected note to include reference to Protocol number and project code | Step 6.1.4 | Correction needed |
| Updated Resource request information | Step 6.1.5 | Process change |
| - Added “Received the KTC Checklist from GSID Lead” and - Changed “country specialty prior” to “country-level information which can be incorporated” | Step 6.1.6 | Process clarification |
| Added row to include TMA’s responsibility | Step 6.1.7 | Process change |
| Changed text to state that the finalized ideal Site and Investigator profile is received by the SA Lead, rather than developed by the SA Lead | Step 6.1.8 | Process change |
| Added row to include GSID Lead “Determines CDA Factor” | Step 6.1.9 | Process change |
| Added information on the APAC Phase 1 Oncology Priority Sites | Step 6.1.10 | Process change |
| Added “Makes sure the site name / information is consistent across all | Step 6.1.11 | Process clarification |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| projects in the Trial Management System if a site number will be duplicated across multiple projects (to avoid causing potential issues in the EDC access).” |  |  |
| - Added SSS Team and removed SRM and PSM; changed to optional attendees - changed “Utilizes all key strategy components received from…” to “documented within”; - Deleted “Determines an appropriate number of sites based on the necessary overage based on the CDA conversion factor for each country.” - Changed “Site ID Vetting results…” to “VIM” | Step 6.1.12 | Process changes and language clarifications |
| Changed “Proactively notifies” to “Informs” | Step 6.1.14 |  |
| - Added “Contact email addresses cannot be from a public email service provider where sending Sponsor confidential information would be subject to terms and conditions granting additional ownership.” AND - Added “Identifies and reviews any publicly available listings from local regulatory authorities for all countries except US FDA if listed as applicable within the country Local Clinical Monitoring Requirements Work Instructions.” | Step 6.1.15 | Process change |
| Changed “Authorizes” to “Reviews” Vetted Site List. Removed 2nd paragraph | Step 6.1.16 | Process change |
| Added row to include TMA’s responsibility | Step 6.1.17 | Process change |
| Added row to include GSID Lead responsibility | Step 6.1.18 | Process change |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| - Changed title to “Conducts Site ID Vetting results and Study Expectations Meeting (SVREM)” - Moved paragraph beginning “Conducts the SVREM…” to appear first in the step. - Moved paragraph describing who must attend to after “Presents the vetting results…” - Added bullet “Correct messaging of study as agreed with in the initial site outreach communication plan” - Deleted “Reviews the KTC checklist to get the study background and strategy, if not assigned prior to the KTC.” - In “Note” changed “manage” to “execute the” and added “strategy after “Site ID” | Step 6.1.19 | Process changes |
| Removed reference to CS_TP_RSU0008 and inserted title of new template | Step 6.1.19 and throughout | Document made obsolete and replaced by new template |
| Added “Authorizes CSA Reps to promote approved Investigators in applicable Trial Mangement System.” | Step 6.1.20 | Process change |
| Added “approved” to first paragraph | Step 6.1.21 | Process clarification |
| Added row to include GSID Lead responsibility | Step 6.1.22 | Process change |
| Added row to include GSID Lead responsibility | Step 6.2.2 | Process change |
| Added “Consults with MSL to ensure relevant questions to determine investigator and site capabilities are included in the SSQ.” | Step 6.2.3 | Process change |
| Added “available” to “technology solution” | Step 6.2.5 | Process clarification |
| Added “and Communication Elements Document.” | Step 6.2.7 | Process clarification |
| Changed “tracks” to “Ensures” documents “are tracked” | Step 6.2.8 | Process change |
| - Moved “For sites requiring SSV, designates SSV requirement “on-site”, “remote”, or “waived” | Step 6.2.9 | Process clarification |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| based on the criteria outlined in CS_WI_SM0005, Monitoring Visits“ from end of step to beginning. - Added “SSV Required as “No,” and SSV Type as “N/A”. to 1st bullet - Added new 3rd bullet: “For non- Optimized sites that are meet the criteria for a waived SSV, mark SSV Required as “No” and SSV Type as “Waived.”” |  |  |
| - Moved “Schedules a weekly call to review Site ID status” to the beginning of the step and clarified that GSID Lead attendance is optional. - Deleted rest of text in step | Step 6.2.12 | Process change and clarification |
| Moved “Monitors trending data to validate site strategy until all sites are selected” from Step 6.2.12 | Step 6.2.13 | Process change |
| Deleted step to handover from LSID Rep to LRSU Rep | Previous Step 6.2.13 | Process change |
| Added “Re-opening Site Selection” section | Section 6.3 | Process clarifications |

- APPENDICES

  - Appendix A: GSID Lead and SAM Split of Responsibilities

Appendix A: GSID Lead and SAM Split of Responsibilities

Below are some of the activities that should allow a clear spilt of which role is performing tasks during Site ID. Project details and certain partnership accounts may impact the task distribution.

| Task | GSID Lead | SAM | GSAA |
| --- | --- | --- | --- |
| KTC | Owner | Contributor |  |
| CSA Rep Resourcing | Owner | Contributor | Support |
| Confirms Qualifying Optimized Sites | Owner |  |  |
| Customizing Site ID Workflow | Owner /Oversight |  |  |
| CDA Confirmation and review |  | Owner |  |
| Site ID Vetting Instructions Meeting (VIM) | Owner | Contributor |  |
| Site Vetting Review | Owner |  |  |
| SSQ Development and Annotation | Owner | Contributor |  |
| Conducts Site Identification Vetting results and Study Expectations Meeting (SVREM) | Owner | Contributor |  |
| Extracting SSQ Data |  | Owner | Support |
| Ensuring CTMS compliance |  | Owner | Support |
| Point of contact for Sponsor during Site Outreach |  | Owner |  |
| Client facing (meeting, outputs) |  | Owner |  |
| Weekly Study Analysis up to 100% site selection target (Country Level and Diversity and Inclusion insights) | Owner | Contributor | Support |
| Weekly Study Analysis up to 100% site selection target (Country Level) | Owner | Contributor |  |
| Monitoring of Optimized Sites Progress | Contributor | Owner | Support |
| Ongoing monitoring of defined escalation Trigger Points throughout Site ID | Owner |  |  |
| Site Activation Management Plan (SAMP) development |  | Owner |  |
| Conduct Strategy Check-in at timepoints defined within the Project’s Site Identification Vetting Results and Study Expectations Meeting template | Owner | Contributor |  |
| Diversity and Inclusion Site ID and Selection | Contributor | Owner | Support |

Page 19 of 19

Copyright © 2020, 2021, 2023 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Sneed, John (q109205) Title:

Date: Wednesday, 21 December 2022, 02:01 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Thursday, 22 December 2022, 02:58 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Trieschmann, Twila (q405536) Title:

Date: Thursday, 22 December 2022, 10:13 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Tuesday, 27 December 2022, 12:18 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================