|  | IQVIATM Work Instruction Site Ready to Enroll Execution and Oversight |
| --- | --- |
|  | Document Number and Revision: CS_WI_RSU0068 Revision 2 |
| Document Owner: Laurie Flintom | Author(s): Jessica Gant, Adam Cribbs, Kiril Dinev, Viktoriia Golikova |

# PURPOSE

To describe the process to oversee, execute and drive timely availability of all required critical elements that enable an Investigator site to be activated.

# SCOPE

  - This work instruction (WI) applies to all functional groups involved in the collection, coordination and/or confirmation of all required documents and/or activities to enable an Investigator site to be ready to enroll subjects.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Clinical Lead (CL) | 6.1, 6.4 |
| Centralized Monitoring Lead (CML) | 6.1, 6.2, 6.4 |
| Centralized Monitoring Assistant (CMA) | 6.2, 6.3 |
| Local Regulatory and Start-Up Representative (LRSU Rep) | 6.2, 6.3, 6.4, 6.5, 6.6 |
| Monitor | 6.4 |
| Project Vendor Manager (PVM) | 6.1 |
| Site Activation Manager (SAM) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6 |

Notes:

- If no SAM is assigned to the project, the CL is accountable for SAM tasks in this WI. If no CL is assigned to the project, the PL is accountable for both CL and SAM tasks.

- If no CMA is assigned, the CML is accountable for CMA tasks in this WI. If no CML is assigned, the Project Management Analyst (PMA) is accountable for CMA tasks.

- If no PVM is assigned, the PL is accountable for PVM tasks.

- Countries in the APAC region and Japan may have country specific nuances that will be captured in their respective local Clinical Monitoring Requirements WIs.

- Some of the responsibilities of the Monitor outlined in this WI may be performed by the Clinical Trial Assistant (CTA).

# DEFINITIONS

Refer to QG_OD_SMT0018, GLOSSARY OF TERMS – CLINICAL SERVICES

Site Activation: Milestone indicating the Investigator site is ready to enroll subjects. Pre- requisites for Site Activation include: Investigator site’s Essential Document Pack (EDP)

is approved, Investigator site has been approved for Investigational Product (IP) release, Investigator site staff is fully trained to follow Protocol procedures, the SIV has occurred, and all Investigator site ready to enroll activities have been completed (including but not limited to equipment at Investigator site, non-IP supplies received, training completed and access to project-specific systems verified for Investigator site staff).

Site Ready to Enroll (SRtE) Activities: All activities required by the Customer and study Protocol for an Investigator site to be approved for Site Activation and ready to enroll subjects.

Trial Management System: When referencing “Trial Management System” throughout this WI, this infers tracking directly into the Clinical Trial Management System (CTMS) or other IQVIA trial management systems.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Identification and Documentation of SRtE Activities

Each role mentioned in this WI is responsible to:

    - Ensure tracking, status reporting, risk/issue identification and mitigation of activities to support Investigator site activation in applicable systems as per CS_OP_RSU0060, Site Activation.

    - File individual documents or pertinent correspondence in the Trial Master File as they are finalized as per CS_OP_RSU0060.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | SAM | Identifies and confirms, with input from PL, PVM, Data Team Lead (DTL), CML and CL, project-specific requirements for an Investigator site to be ready to enroll subjects in agreement with Customer. These activities may include, but are not limited to: - Essential Documents Pack (EDP) is approved (CS_WI_RSU0021, Essential Documents Pack) - Investigational Product (IP) has been approved for shipment, if applicable - IP shipment timelines and triggers are defined (CS_WI_SM0010, Investigational Product (IP) Handling and Monitoring) - Vendor study supplies and equipment, as applicable, are available at Investigator site (CS_WI_SM0027, Provision of Clinical Project Supplies and Equipment to Investigator Sites) - Electronic Data Capture (EDC) access provided to the relevant Investigator site staff - Investigator Site File readiness and distribution timelines are defined (CS_WI_SM0007, Investigator’s Site File) | Setup, prior to Stage Gate Review (SGR) 2 |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Any Investigator and/or site training required to conduct the project has been completed (refer to the project-specific Clinical Operations Plan (COP) and to CS_WI_PL0024, Project-Specific Training and Team Member Transition) - Site Initiation Visit (SIV) is approved and completed (CS_WI_SM0005, Monitoring Visits) |  |
| 6.1.2 | SAM | Prepares, with input from the RAd, PL, PVM, CML and CL the project-specific CS_TP_RSU0013, Site Activation Management Plan, (SAMP ) and SRtE Checklist requirements. Note: Planning of specifications should begin at project award. | Setup, prior to SGR 2 |
| 6.1.3 | PVM/CL | - Agrees and documents the respective functional requirements in the CS_TP_PL0028, Vendor Management Plan and CS_TP_SM0021, Clinical Operations Plan Template. - Manages day-to-day execution as outlined in the respective plans. | During Planning |
| 6.1.4 | CML | Sets up the SRtE Checklist in the applicable system upon confirmation of the requirements from the SAM | Prior to first Investigator site selected. |
| 6.1.5 | SAM | - Conducts SRtE Kick Off Meeting (KOM) to review tasks, roles and responsibilities, and risk mitigation strategies for the site activation activities as documented in the SAMP. - Attendees include PL, CL, CML, CMA, and LRSU Rep(s). - KOM content must be included in the project e-training for team members not assigned at the time of the KOM. - Updates the SAMP for any process changes, questions or concerns upon review of the SAMP, and ensures the plan is signed by RAd, PL, and CL. | Prior to SGR 2 |
| 6.1.6 |  | - Files the signed SAMP in the TMF and then shares the location with the RAd, PL, CL, LRSU Rep, CML, and CMA - Trains LRSU Rep on SAMP and execution Note: If vendor details are not available at SGR 2, the SAMP should be signed and revised at a future date to incorporate all remaining details. | After the SAMP is final and signed |

  - Execution and Oversight of SRtE Activities

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | SAM | Oversees execution of SRtE progress and activities as outlined by the SAMP, performing the following tasks: - Confirms with Operational Team Leads (OTLs) and other task owners that vendors, systems, and other required materials or technology are set up in accordance with applicable operational plans | Startup: weekly |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Partners with the CML to ensure timely completion of the SRtE Checklist by the CMA - Acts as point of escalation for LRSU Rep, CMA, and CML to follow up on status, progress and execution of Site Activation activities. - Conducts ongoing analysis on Site Activation status and metrics for selected Investigator sites including the EDP approval, SIV completion and additional Site Activation activities as identified by the SAMP to identify any potential risks - Conducts regular SRtE meetings to review progress, risk and mitigation, and assign actions relevant to Investigator site activation - Communicates with CL regarding SIV timing based on status of Site Activation activities - Acts as Customer point of contact for Site Activation status |  |
| 6.2.2 | CML | Confirms monitoring resource assignments and SIV scheduling and informs the CL about any delays, if applicable | Startup: weekly |
| 6.2.3 | CML | Executes SRtE activities as outlined in the SAMP, COP and VMP including, but not limited to the following tasks: - Triggers or requests any Investigator site, IQVIA and vendor system access. as required by the SAMP. PVM may support with vendor systems. (Refer to CS_WI_PL0052, Project Systems Management and CS_WI_DM0404, EDC Database Build.) - Updates any study level access and equipment trackers, if applicable. - Triggers or makes initial requests for any study specific Investigator and/or Investigator site training/certification required to conduct the study to be provided to the Investigator site (e.g., Interactive Response Technology (IRT) System, EDC, Protocol and Study Procedures Training). PVM may support with vendor training triggers or requests - Arranges the shipment of project and vendor equipment and supplies. PVM may support with vendor equipment. (Refer to CS_WI_SM0027) - Arranges shipment of non-IP supplies and equipment from local depot to Investigator sites if local depot required . PVM may support with vendor supplies and equipment. |  |
| 6.2.4 | LRSU Rep | Executes SRtE activities as outlined by the SAMP, including, but not limited to the following tasks: - Confirms Planned SSU Completion Date (PCD), Planned SRtE Date, and Investigator site level updates are tracked in appropriate systems (e.g., Trial Management System) for activities as assigned by the SAMP and defined in the SRtE Checklist |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Compiles and obtains approval for Essential Documents Pack (EDP). Refer to CS_WI_RSU0021, Essential Documents Pack - Confirms that study supplies and equipment, if applicable, are available at Investigator site prior to SIV. Refer to CS_WI_SM0027 - Confirms completion of any Investigator and/or site training or certification required to conduct the project (e.g., IRT System, EDC, Protocol and Study Procedures Training, Rater training/certification). Refer to CS_WI_PL0024, Project-Specific Training and Team Member Transition. - Confirms project-specific system accessibility by the relevant Investigator site staff including Electronic Data Capture (EDC) access. - Distributes Investigator Site File (ISF) to Investigator site. Refer to CS_WI_SM0007, Investigator’s Site File. - Confirms Investigator site completion of any facility or equipment certification, testing or validation (e.g. test scans, local lab certification, etc.) - Confirms set up of local depot for non-IP supplies (when required locally) - Tracks information on applicable supplies and equipment provided to Investigator site in Trial Management System (refer to CS_WI_SM0027 and Trial Management Guidance documents) - For studies not in Trial Management System, tracks information on applicable supplies and equipment provided to Investigator site using IQVIA Non-CTMS Study Supply and Equipment Template (refer to CS_WI_SM0027) |  |
| 6.2.5 | CMA | - Collects and tracks all Investigator site updates from the project team in the SRtE Checklist, initiating communication within the project team, if applicable, as defined by the SAMP Note: CMA is not responsible for direct communication with the Investigator site. | Ongoing during Startup |
| 6.2.6 |  | Files the completed SRtE Checklist export in the TMF after last site is activated. | After Startup is complete. |
| 6.2.7 | SAM | - Reviews Investigator site status and progress towards completion of Site Activation activities, with input from the LRSU Rep and CML/CMA, referencing the current SRtE Checklist, as outlined in the SAMP. - Obtains regular Investigator site updates from LRSU Rep during regular country/region level meetings - Ensures clear reporting and communication of potential SIV timing to CL - Reports Site Activation updates in external, Customer team meetings | Startup: during internal SRtE meetings |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: As the project transitions from Startup to Conduct, the frequency of these communications may vary depending on project needs. |  |
| 6.2.8 | CML | Oversees progress and completion of SRtE Checklist and Site Activation activities by performing the following tasks: - Oversees timely updates to the SRtE Checklist - Identifies gaps and/or risks to progress based on critical path for Site Activation - Communicates proactively with SAM/CL regarding risks, gaps and progress of Site Activation activities | Ongoing during Startup |
| 6.2.9 | CMA | Follows-up directly with project team members on pending information for the SRtE Checklist, if necessary. | Ongoing during Startup |

  - SRtE Site Contact Form

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | SAM | Creates and completes, with input from the PVM, CL and PL, the project-specific CS_TP_RSU0082, Site Ready to Enroll Site Contact Form (SRtE Site Contact Form), with: - Project-specific system access requirements - IP shipment address - Applicable vendor information to collect Investigator site contact details needed for SRtE activities identified in the SAMP | Setup: After SGR 2 and prior to first Investigator site selected. |
| 6.3.2 |  | Provides the project-specific SRtE Site Contact Form to the LRSU Rep for distribution and data collection. |  |
| 6.3.3 | LRSU Rep | - Distributes the project-specific SRtE Site Contact Form to each selected Investigator site, together with the Site Selection Letter, for completion of required information | Startup, Investigator site selection is approved |
| 6.3.4 |  | - Follows up with Investigator site to obtain completed SRtE Site Contact Form - Tracks received Investigator site contact information in Trial Management System per applicable guidelines - Provides the SRtE Site Contact Form at designated location to the CMA for further distribution - Provides any subsequent updated forms to the CMA and tracks updated information in the Trial Management System per applicable guidelines | Startup, as defined in the SAMP |
| 6.3.5 | CMA | Updates the respective study trackers/systems as described in the Vendor Management Plan (VMP) with information obtained from the completed SRtE Site Contact forms. | Startup, as defined in the SAMP |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.6 | LRSU Rep | Files the completed SRtE Site Contact Form and any subsequent updated forms in the TMF | Startup, after SRtE Site Contact Form is completed |

  - Approving IP Release, Site Initiation Visits and Site Activation

Investigator site activation may proceed only after verification of an executed contract between Customer and IQVIA, or with written approval from Customer and IQVIA. Refer to the Policy for Requirement of Comprehensive Agreement Prior to Site Activation (section 7.0), in accordance with CS_WI_PL0023, Project Lifecycle Planning.

| No. | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | SAM | Refers to SAMP and SRtE Checklist to confirm if the required activities are complete allowing IP Release, SIV and/or Site Activation as applicable | Startup: After EDP is approved, prior to the SIV |
| 6.4.2 | CL | Informs SAM that documentation is in place for conducting SIV without IP, if applicable. (refer to CS_WI_SM0005 and CS_OD_SM0055, Dry Site Initiation Visit Guidance) | Startup: Prior to the SIV |
| 6.4.3 | CML | Confirms to SAM and CL the status of activities per the SRtE requirements: whether all activities are completed or there are items left to be completed/verified during SIV to activate the site. |  |
| 6.4.4 | SAM | Completes and signs the CS_FM_RSU0048, Site Activation Approval Form, (SAAF) and sends it to the Customer for approval, if required. Notes: - The SAAF is used to indicate whether the Investigator site is approved for IP release, SIV, or Site Activation (or a combination thereof) - Refer to CS_FM_RSU0047, Essential Documents Pack - Requirements Form (EDP-RF), for confirmation if Customer approval is required - A pre-requisite for SIV is that all SIV requirements have been met as stated in the SAMP - If IP shipment is not expected to occur prior to SIV and/or Site Activation is not expected to occur immediately following the SIV, a separate SAAF needs to be completed until all activities have been signed off | Startup, prior to SIV and/or Site Activation |
| 6.4.5 |  | - Notifies the CL and Monitor in writing when the Investigator site is approved for IP Release, SIV and/or Site Activation - Sends the signed SAAF to the CL and Monitor Note: If IP release, SIV and Site Activation are approved at different time-points, the CL and Monitor will be notified at the time each activity is approved. | Startup, prior to SIV and/or Site Activation |

| No. | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.6 | SAM | Enters “SIV Approval Date” and “Authorization for Site Activation” in the Trial Management System at the time of SAAF signature for approved activities as described in Trial Management System Guidance Documents (at the time each activity is approved, if at different timepoints). | Startup, once the SAAF is signed |
| 6.4.7 | SAM | Ensures the signed SAAF is filed in the TMF. Note: If IP release approval, SIV, and Site Activation are approved at different time-points, each signed SAAF must be filed in the TMF. | Startup, once the SAAF is signed |
| 6.4.8 | LRSU Rep | Provides the Monitor(s) with an overview of the key areas of the Investigator site status including Investigator site information, Investigator site documents, and any pending SRtE activities / requirements as described in sections 6.5 and 6.6 of this WI. | Startup, prior to SIV |
| 6.4.9 | Monitor | Schedules and conducts SIV. Confirms during SIV that: - All study equipment and supplies were received at the Investigator site - IP is received at Investigator site, if applicable - All study specific training and certification (if applicable) is completed by respective Investigator site staff (e.g., IRT System, EDC, Protocol and Study Procedures Training). - All systems accesses granted Note: After the SIV, any pending SRtE activities/requirements should be communicated to the appropriate role for resolution (i.e. LRSU Rep for training, access, or equipment/materials, CL for IP, etc.) | Startup, prior to, during, and following SIV |
| 6.4.10 | LRSU Rep | Follows to resolution any pending activities to be completed for site activation with Investigator site staff or relevant project team member(s) (CML, CMA etc.) | Startup, after SIV if there are SRtE activities that require resolution after SIV |
| 6.4.11 | CML | Confirms to SAM and CL that all activities per the SRtE requirements are completed. |  |
| 6.4.12 | SAM | - Completes and signs the CS_FM_RSU0048, Site Activation Approval Form to approve Investigator site for site activation and sends it to the Customer for approval, if required. - Notifies the CL and Monitor in writing when the Investigator site is approved for Site Activation - Sends the signed SAAF to the CL and Monitor - Enters “Authorization for Site Activation” date in the Trial Management System at the time of SAAF signature as described in Trial Management System Guidance Documents. - Ensures the signed SAAF is filed in the TMF. | Startup, after SIV and all SRtE activities are resolved |
| 6.4.13 | CL | - Activates the Investigator site in the IRT system - Informs SAM and Monitor of the Site Activation date | Startup, after SAAF is signed for Site Activation |
| 6.4.14 | Monitor | Changes Investigator site status to “Enrollment Open” in the Trial Management System as described in Trial Management System Guidance documents. | Startup, after confirmation from CL that Site |

| No. | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: The CML may perform this step on behalf of the Monitor. | Activation has occurred. |
| 6.4.15 | CL | Confirms that site status of “Enrollment Open” is tracked in the Trial Management System by the Monitor or CML as described in Trial Management System Guidance documents. | Startup, after site activation has occurred. |
| 6.4.16 | LRSU Rep | Enters “Site Ready to Enroll” Date in the Trial Management System as described in the Trial Management System Guidance documents. | Startup, after confirmation from SAM that Site Activation has occurred |
| 6.4.17 | SAM | Confirms that “Site Ready to Enroll” Date is entered in the Trial Management System by the LRSU Rep as described in Trial Management System Guidance documents. | Startup, after Site Activation has occurred |

  - Transfer of Information on Core and Country Documents

    - The purpose of the transfer of information on Core and Country documents is for the LRSU Rep to familiarize and provide an overview to the Monitor on the Core and Country documents, as applicable (e.g. Protocol, Investigator Brochure, Informed Consent Forms, etc.) and to provide an update on the status of the tracking and filing of those documents in the respective Trial Management System and TMF.

    - Transfer of Core and Country Documents should occur between LRSU Rep and Monitor(s) prior to first SIV in the country and it may occur via e-mail or via formal meeting.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | LRSU Rep | Prepares for the Transfer - Confirms that tracking has been completed in the Trial Management System, as described in the SAMP and Trial Management System Guidance, if applicable. Tracking includes but is not limited to all critical fields including submissions and approval dates - Uses the appropriate report from the Trial Management System to document the tracking status and to support transfer of information (refer to CS_TP_RSU0040, RSU Country and Site Transfer Checklist, (Transfer Checklist)) - Confirms TMF filing status of applicable Core and Country documents (e.g. Protocol, Investigator Brochure, Master Informed Consent Form), according to CS_OP_TMF0007, Trial Master File (TMF) and its associated WIs - Uses the appropriate report from the TMF to document the filing status and to support transfer of information (refer to Transfer Checklist) - If transfer is to happen via e-mail, proceeds to step 6.5.3 Note: If any Core documents are not tracked in the Trial Management System or are missing in the TMF, informs the SAM, so | Startup Prior to the Transfer |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | documents are tracked and filed by responsible role (i.e. SAM or RAd). |  |
| 6.5.2 | LRSU Rep | Schedules a Transfer Meeting with the Monitor(s) | Startup Prior to the Transfer |
| 6.5.3 |  | Completes the LRSU – Core and Country Transfer tab in the Transfer Checklist in preparation for the Transfer Meeting |  |
| 6.5.4 |  | Provides the Monitor(s) with an overview of the key areas of the project from the perspective of Core (i.e. versions of Core documents approved in country) and Country documents, as outlined in the Transfer Checklist via email or in a formal meeting. | Startup Prior to the first Site Initiation Visit (SIV) in each applicable country |
| 6.5.5 |  | Documents date of the Transfer by signing the LRSU – Core and Country Transfer tab in the Transfer Checklist. | Startup After the Transfer |
| 6.5.6 |  | Files the signed LRSU – Core and Country Transfer tab of the Transfer checklist to the TMF (Refer to CS_OP_TMF0007, Trial Master File (TMF) and its associated Wis). |  |
| 6.5.7 | SAM | Oversees completion of the Transfer process for Core and Country documents by confirming TMF filing of the signed LRSU – Core and Country Transfer tab of the Transfer checklists Note: If the signed LRSU – Core and Country Transfer tab of the Transfer Checklist is not filed in TMF within the required timelines (refer to CS_OP_TMF0007 Trial Master File (TMF) and its associated WIs) follows up with LRSU Rep until completion of Transition process and if needed informs LRSU Manager. |  |

  - Transfer of Information on Investigator Site Documents

The purpose of the transfer of information on Investigator site documents is for the LRSU Rep to familiarize and provide an overview to the Monitor on the Investigator site and Investigator site documents, as applicable (e.g. Informed Consent Forms, Site Contract, Payment schedule, etc.) and to provide status on the tracking and filing of applicable Investigator site documents in the respective Trial Management System and TMF.

    - Transfer of information on Investigator site documents is required for each Investigator site

    - Transfer of information on Investigator site documents of the first Investigator site(s) in a country may occur at the same time as the transfer of information on Core and Country Documents.

    - Transfer of information on Investigator site documents of multiple Investigator sites is allowed at once; however, there must be a separate Transfer Checklist for each Investigator site.

    - Transfer of information on Investigator site documents should occur between LRSU Rep and Monitor(s) and may occur via e-mail(s) or via formal meeting(s).

    - Transfer of information on site documents will be completed in two steps. The first step will occur before SIV and the second step will occur upon all SRtE activities completion.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | LRSU Rep | Prepares for the start of site transfer: - Confirms that tracking has been completed in the Trial Management System, as described in the SAMP and the Trial Management System Guidance, if applicable. Tracking includes but is not limited to all critical fields including submissions and approvals. - Uses the appropriate report from the Trial Management System to document the tracking status and to support transfer of information (refer to Transfer Checklist) - Confirms TMF filing status of applicable Investigator site documents (e.g. CVs, FDFs, Form FDA 1572 or alternate, etc.). (Refer to CS_OP_TMF0007, Trial Master File (TMF) and its associated Wis) - Uses the appropriate report from the TMF to document the filing status as part of the transfer (refer to Transfer Checklist) - If transfer happens via e-mail proceeds to step 6.6.3 | Startup Prior to the Transfer |
| 6.6.2 |  | Schedules a Transfer Meeting(s) with the Monitor(s) for each Investigator site in each country. |  |
| 6.6.3 |  | Completes the LRSU –Site Transfer tab from the Transfer Checklist. |  |
| 6.6.4 |  | Provides the Monitor(s) via email or in a formal meeting, an overview of the key areas of the Investigator site status including Investigator site information, Investigator site documents, and status of SRtE activities (i.e. systems access, supplies status, training completion) as outlined in the Transfer Checklist | Startup Prior to the Site Initiation Visit (SIV) for the particular Investigator site |
| 6.6.5 |  | Updates (as needed) and signs the LRSU –Site Transfer tab from the Transfer Checklist and informs Monitor(s) about activities completion and updates on Checklist items occurring after SIV. | Startup Upon completion of SRtE activities for the particular Investigator site |
| 6.6.6 |  | Follows up on actions requiring resolution as per signed Transfer checklist. | Startup After the Transfer |
| 6.6.7 |  | Tracks date of transfer of information on Investigator site documents in the Trial Management System as described in IQVIA Trial Management System Guidances |  |
| 6.6.8 |  | Files the signed LRSU –Site Transfer tab from the Transfer Checklist to the TMF. (Refer to CS_OP_TMF0007, Trial Master File (TMF) and its associated Wis). |  |
| 6.6.9 | SAM | - Runs the Trial Management System report to confirm that the transfer process is complete. |  |
|  |  | - Confirms TMF filing of the signed LRSU –Site Transfer tab from the Transfer Checklist. |  |
|  |  | Note: If the transfer process is not completed as required, or if the signed LRSU –Site Transfer tab from the Transfer Checklist is not filed in the TMF within the required timelines (refer to |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | CS_OP_TMF0007 Trial Master File (TMF) and its associated WIs) follows up with LRSU Rep until completion of the transfer process and filing has occurred. If needed, escalates to the LRSU Rep’s Line Manager. |  |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| 7.2 CS_OP_RSU0060 | Site Activation |
| 7.3 CS_WI_RSU0021 | Essential Documents Pack |
| 7.4 CS_WI_SM0010 | Investigational Product (IP) Handling and Monitoring |
| 7.5 CS_WI_SM0027 | Provision of Clinical Project Supplies and Equipment to Investigator Sites |
| 7.6 CS_WI_SM0007 | Investigator's Site File |
| 7.7 CS_WI_PL0024 | Project-Specific Training and Team Member Transition |
| 7.8 CS_WI_SM0005 | Monitoring Visits |
| 7.9 CS_TP_RSU0013 | Site Activation Management Plan |
| 7.10 CS_TP_PL0028 | Vendor Management Plan |
| 7.11 CS_TP_SM0021 | Clinical Operations Plan Template |
| 7.12 CS_WI_PL0052 | Project Systems Management |
| 7.13 CS_WI_DM0404 | EDC Database Build |
| 7.14 CS_TP_RSU0082 | Site Ready to Enroll Site Contact Form |
| 7.15 CS_WI_PL0023 | Project Lifecycle Planning |
| 7.16 CS_OD_SM0055 | Dry Site Initiation Visit Guidance |
| 7.17 CS_FM_RSU0048 | Site Activation Approval Form |
| 7.18 CS_FM_RSU0047 | Essential Documents Pack - Requirements Form |
| 7.19 CS_TP_RSU0040 | RSU Country and Site Transfer Checklist |
| 7.20 CS_OP_TMF0007 | Trial Master File (TMF) |
| External References |  |
| 7.21 IQVIA Comprehensive Agreement Policy | Policy for Requirement of Comprehensive Agreement Prior To Site Activation in connection with Clinical Services |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_RSU0068 | Site Ready to Enroll Execution and Oversight | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Add Monitor in roles | 3.0, 6.4.9 | Monitor activity has been added to make process clearer |
| Change Project Integration Manager (PIM) to Project Vendor Manager (PVM) | 3.0, 6.1 | Change to role title |
| Update Sections that apply to each role | 3.0 | To match current version of WI |
| Add note that some countries/regions may have different roles performing the tasks noted in this WI | 3.0 | To document that some regions (e.g. APAC) may have different roles performing some tasks in this WI |
| Explanation that the term “Monitor” may mean either a CRA that travels to sites or in- house support staff | 3.0 | To make clear that “Monitor” is being used as a broader term than just the CRA that goes to the site. |
| Addition of RAd to help prepare SAMP | 6.1.2 | To clarify that the RAd is involved where needed |
| Addition of roles involved in process (e.g. LRSU Rep, RAd, PL) | 6.1.5, 6.1.6, 6.2.1 | To show involvement in the Site Activation activities |
| Added “Conduct regular SRtE meetings to review progress, risk and mitigation, and assign actions relevant to site activation” | 6.2.1 | To clarify that regular meetings will occur |
| Change in text for clarity | 6.2.2 | To clarify information |
| Added additional steps | 6.2.3, 6.2.3 | To make clear CML and LRSU Rep responsibilities |
| Added text that SRtE checklist is filed in the TMF at the end of start up | 6.2.5 | To clarify when to file |
| Added that SAM obtains regular updates from LRSU Rep during internal meetings. | 6.2.6 | For clarity |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Removed “external meetings” from “when” column |  |  |
| Clarified that the project- specific form is used | 6.3.3 | For clarity |
| Added: “Provides any subsequent updated forms to the CMA and tracks updated information in the Trial Management System per applicable guidelines.” | 6.3.4 | For clarity |
| Changed SAMP to VMP | 6.3.5 | Correction |
| Added steps to indicate LRSU Rep and Monitor tasks | 6.4.8, 6.4.9 | For clarity |
| Added “in the IRT system” and added that both the SAM and the Monitor should be informed when a site has been activated | 6.4.10 | For clarity |
| Removed responsibility for the CL to confirm that the Ready to Enroll date is tracked in the trial management system | 6.4.10 | For clarity |
| Added steps to clarify Monitor and LRSU Rep responsibilities for updating the trial management system | 6.4.11, 6.4.12 | For clarity |
| Added sections 6.5 and 6.6 to describe the Transfer of the Core, Country and Site documents from LRSU Rep to the Monitor | 6.5, 6.6 | Transfer of information is the end of the SRtE process and makes more sense to include here than in a standalone WI. CS_WI_RSU0069, RSU Country and Site Handover, made obsolete |
| Updated SOP references | Throughout document | To provide current correct cross references to other SOPs |
| Removed Appendix A | 10.0 Appendices | Decision made that Appendix A was no longer needed |

- APPENDICES

Not Applicable

Page 14 of 14

Copyright © 2020, 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Nikolova, Danny (q601511) Title:

Date: Friday, 15 October 2021, 03:29 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Herbst, Adene (q742381) Title:

Date: Friday, 15 October 2021, 03:43 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Friday, 15 October 2021, 09:42 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Beatty, Mary (q100217) Title:

Date: Friday, 15 October 2021, 10:38 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================