|  | IQVIATM Work Instruction Global Regulatory Affairs - Project Management of GRA Projects |
| --- | --- |
|  | Document Number and Revision: CS_WI_RA0273 Revision 6 |
| Document Owner: Anja De Pauw | Author(s): Ankit Tyagi |

## PURPOSE

To outline the procedures for initiation through to close out of any GRA project where IQVIA Global Regulatory Affairs (GRA) are responsible for the project management of the project.

## SCOPE

  - This procedure commences as soon as documented confirmation is available that the project has been awarded to GRA and ends when all project activities have been completed.

  - Applies to all GRA staff.

  - Applies to all GRA projects, including but not limited to: Gap Analysis, Regulatory Strategy, Regulatory Intelligence, Regulatory Roadmaps, Meetings with Health Authorities, Expedited Pathways Requests, Pediatric Investigation Plans, Orphan Drug Designations, Regulatory Publishing, Labelling Maintenance, Registration and Lifecycle Maintenance of Marketing Applications.

  - The scope excludes Clinical study projects with Regulatory functional services (e.g., Publishing, INDs) or projects led by other departments e.g., Real World Evidence, which are covered under Project Leadership Standard Operating Procedures (SOPs).

## ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this Work Instruction (WI):

| Role | Sections |
| --- | --- |
| GRA Project Manager (RPM) | 6.1, 6.2, 6.3, 6.4 |
| Regulatory Team Member (RTM) | 6.2 |

## DEFINITIONS

GRA project: Project contract between GRA and the customer. GRA Project Manager is accountable for project and financial management.

## MATERIAL AND EQUIPMENT

Not Applicable

## PROCEDURE

  - Project Initiation

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | RPM | Statement of Work (SOW) or Work Order (WO) - For any Regulatory Project, before initiation review the draft SOW/WO to verify scope, duration, budget and payment schedule are aligned with the proposal and provides feedback to contract analyst. | Upon Receipt of draft SOW from Contract analyst |
|  |  | - Work with the customer to obtain a Purchase Order number (PO No.) and sends to the Project Finance Manager (PFM). - Review the signed SOW/WO and allocates budget to each country/other departments as appropriate. | After execution of the contract |
| 6.1.2 | RPM | Assignment of Regulatory Team Members (RTMs) - Review original proposal for proposed RTMs and confirms availability and appropriate expertise and experience to conduct the work. (The contract may state the expertise and experience required). Liaises with GRA Resource Manager and Line Managers, as appropriate, to resource project adequately. | At project initiation |
| 6.1.3 | RPM | - Verifies the subcontractors are listed on the “IQVIA Vendor List” (refer to the link MyVendor (sharepoint.com) or contact vendorqualification@iqvia.com for support. For vendor oversight, refer to CS_WI_PL0027 Project Vendor Management. (Note section 7.14 provides a link to the IQVIA Vendor List). - Initiates a project specific contract through LCN vendor contract request form (https://www.tfaforms.com/4930759). - Requests that a PO be generated as per the guidance IQVIA Global Procurement > Purchase Orders | If sub- contractors are required as part of the team |
| 6.1.4 | RPM | - Provides RTMs with the available project documentation, as appropriate, and requests review prior to internal kick-off meeting. | After team has been assigned |
| 6.1.5 | RPM | IQVIA Technology systems - For projects executed within IQVIA systems, sets up and maintains the Regulatory Project File on the local server. (Refer to Appendix B for examples of GRA Project Filing Structures). For projects executed within Customer’s systems, ensures the RTMs receive access to any required Customer’s filing systems. Defines the access type that each RTM should have and grants that access level. Ensures that non-project RTMs | At project initiation |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | are given “Visitor/Read-only access” (e.g., during quality audits). - Requests the allocation of electronic project work area to enable global sharing (e.g., SharePoint site, Box, electronic Document Management System (eDMS), file share, MS Teams SharePoint as appropriate). - Documents in the Project Instructions where key customer emails will be filed (refer to section 6.1.12). |  |
| 6.1.6 | RPM | Project Set-up activities in Professional Services Automation (PSA) - Provides the Project Management Office (PMO) Lead with the contract and details of RPM and RTMs to create the project in PSA. - Review the “PSA project hierarchy” to confirm that it captures all the services and deliverables required by the SOW. - Assigns RTMs to the project with the correct forecasted hours and duration. Confirms this is correct in PSA Resource Planner. | At project initiation |
| 6.1.7 | RPM | Project metrics - Confirms applicability of project metrics for internal use which are automatically assigned to all projects set up in PSA. - Confirms the metrics required by the customer detailed in the Master Service Agreement (MSA) and/or SOW/WO, if applicable. - Contacts the GRA Oversight Dashboard Lead, to set up project metrics, if applicable. | At project initiation |
| 6.1.8 | RPM | Kick-Off Meeting Chairs an internal kick-off meeting and/or customer kick-off meeting, as appropriate. The agenda will typically include: | At project initiation |
|  |  | - Introduction of RTMs (roles and responsibility in the project team) - Project background - Project deliverables - Technology systems training and access, if applicable - Training Plan, if applicable (Listing of required project training (customer and/or IQVIA training, as appropriate) and as agreed with the customer) - Project metrics - Allocation of activities to RTMs - Project assumptions - Project Plan or timings - Communication plan - agree on frequency and type of meetings with the customer as per the project instruction - Project status reporting – agree on format, frequency |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Issue escalation process - Next steps |  |
| 6.1.9 | RPM | Project Timelines - Provides RTMs with timelines for key stages in the projects and deliverables. - Develops a Project Plan (e.g., a Gantt chart) for complex projects or complex deliverables or when required by the customer, to address major project activities, with timelines for project milestones and major deliverables as per SOW. If developed, this should be maintained throughout the project and distributed as appropriate to RTMs and the customer. | After Kick- Off meeting |
| 6.1.10 | RPM | Project Deliverables - Agrees with the customer if customer’s templates or SOPs are to be used to prepare the deliverables, and documents this in the Project Instruction, in the section “Procedure”. - Agrees with the customer the type of template, Word document or PowerPoint presentation to be used to prepare the deliverables, if applicable. - If required, develops a project tracker or similar tool to record the name of delivered documents, document owner, document status, and all relevant follow-up dates. | After Kick- Off meeting |
| 6.1.11 | RPM | Customer contact - Develops a communication plan with the customer. Agrees with the customer the methods and frequency of contact. - Prepares a team contact list with roles, responsibilities, and contact information for key IQVIA RTMs. | At Kick-off meeting |
|  |  |  | Following kick-off meeting |
| 6.1.12 | RPM | Project Instructions - Issues Project Instruction(s) to cover the operational management of the project using template CS_TP_PL0073: Project Instruction. This template provides instructions on how to complete it. - Project Instructions are required for all projects under this WI, unless the project is managed and executed by one person (no written deliverables) or two persons (author and QC reviewer). All the items included in the template must be completed, including the rationale why the project instruction is written. - Ensures that an internally approved Project Instruction is available before the first deliverable is sent to the customer. - Documents that the Project Instruction(s) will be reviewed annually from the Project Instruction effective date /last review | Following Kick-off meeting |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | date, or sooner, if required, throughout the duration of the project until Project Close Out. |  |
| 6.1.13 | RPM | Project Team training - Discusses and agrees with customer if they will provide project-specific training or require that IQVIA’s RTMs to follow the customer’s SOPs or other standards. - If needed, prepares training materials and provides training to the RTMs. In some cases, the internal kick-off meeting may serve as the training for the team. - Prepares a project Training Plan if customer SOPs or training is required. - Sets up the project in eTraining, if applicable, and loads all training materials in eTraining including the Project Instructions, except for customer’s training materials, which may be available only on the customer’s platforms. In this case, a “training acknowledgement card” can be added in the IQVIA eTraining for RTMs to document completion of the customer’s training and allow for training compliance reporting. - If applicable, provides RTMs with relevant SOPs related to the project. - Keeps record of training as described in CS_WI_PL0024 Project-Specific Training and Team Member Transition, including sub-contractors if used. - Documents how customer specific training and project eTraining plan will be handled in the Project Instruction(s). | Following kick-off meeting |
| 6.1.14 | RPM | Project Risk Management Plan - Identifies and documents all risks pertinent to the project, determining impact and mitigation strategy. Provides the assessment to the customer for review, completion, and agreement in Risk Assessment Log as defined in template Appendix C. | Following Kick-off meeting for marketing application, large projects or at customer request |

  - Project Execution

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | RPM | Project Administration - Maintains and updates regulatory project files and e-mail database, and, if applicable, technology systems such as SharePoint site. - Files regulatory project files such as deliverable documentation, emails, meeting notes and action items in the allocated Regulatory Project File on the local server or global server in accordance with Section 6.1.5, or in Customer systems, as applicable. Instructs RTMs to file their project documentation in the allocated location, if applicable. - Reviews the Project Instruction(s) annually based on the Project Instruction effective date/last review date, or sooner, if required, throughout the duration of the project until Project Close Out. If no update is required, documents the review on a GRA Note to File (NTF), CS_FM_RA0298. | During project execution |
| 6.2.2 | RPM | Maintenance of Project Management Documentation - Maintains Project Instruction(s). - Maintains meeting minutes/notes and action items. - Maintains Project Risk Management Plan, if applicable. - Maintains and updates Communication Plan, if applicable. | During project execution |
| 6.2.3 | RPM | Project Team Management - Tracks progress of tasks against the SOW. - Keeps track of RTMs’ performance associated with agreed milestone and deliverable deadlines, as defined in the Project Instruction(s). - Provides ongoing updates to RTMs throughout the project as and when required, or as per the Communication Plan. - Monitors resource requirements for the project on an ongoing basis, alerting GRA Resource Manager and Line Manger, if necessary. | During project execution |
| 6.2.4 | RTM | Project RTM (including RPM) handover - The outgoing RTM completes a handover with the incoming RTM, which comprises completing the CS_FM_RA0301 Global Regulatory Affairs - Project Team Member Transition Form (or other type of handover form as agreed with the customer) and holding a meeting to go through the handover, including outstanding actions the incoming RTM needs to complete. - On-board new team members. | Prior to change in RTM |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Off-board team members who no longer work on the project, including removing access to technology systems used for the project. |  |
| 6.2.5 | RTM | Project Risk Management - Provides project-related updates to the RPM. - Raises identified risks and/ or issues and records the risk in Risk assessment Log (Appendix C) after agreement with RPM. - Follows the agreed escalation process and timelines, as defined in Project Instruction. | During project execution |
| 6.2.6 | RPM | Team Meetings - Circulates an agenda prior to the meeting. - Chairs internal and customer project team meetings at a frequency dependent upon the specific needs of the project and as specified in the SOW or as agreed with the customer at project initiation. The meetings may be held face to face, via teleconference, WebEx, Skype, MS Teams, or videoconference. - Documents all meetings with minutes/notes and action items, as appropriate, and files in accordance with Section 6.2.1. - Follows up on actions (internally and/or with customer) and documents status up to completion on a Project Action Log. An example of a GRA Project Action Log template is provided in Appendix D. | During project execution |
| 6.2.7 | RPM | Project Deliverables - If appropriate, and no specific templates provided by the customer, agrees a template with RTMs to ensure consistency across countries/products of the content and format of the deliverable. - Release deliverables to the appropriate customer representative(s) by the agreed time and only after the required internal QC/review has been performed and documented as per the Project Instruction. - Confirms with the country expert that project deliverables comply with current regulatory regulations, guidance, and legislation for the project country and/or region. | During project execution |
| 6.2.8 | RTM | Quality Control - Works to IQVIA’s standard quality practices (refer to CS_WI_RA032 Global Regulatory Affairs - Preparation, Quality Control and Provision of Regulatory Affairs Deliverables), in addition to other quality control standards as required, e.g., the customer’s SOPs or standards agreed in SOW/WO. | During project execution |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.9 | RPM | Project Issues - Identifies and resolves any significant deviation from project timelines, budget, and/or quality of deliverables. Documents any project specific process deviation or explanatory notes on a GRA NTF, CS_FM_RA0298. - Escalates project issues to GRA Resource Manager or Line Manager and QA representative, as appropriate per the applicable SOP: Non-compliances and unplanned process deviations as outlined in CS_WI_RA0270 Global Regulatory Affairs - Quality Oversight and major and critical quality issues as outlined in CS_OP_QA002 Quality Issue Management. | During project execution |
| 6.2.10 | RPM | Project Status and Metrics Reporting - If agreed, prepares status reports for the customer in accordance with pre-agreed format and frequency and as defined in the SOW or agreed at the Kick-off meeting. - Enters current and accurate status information into all GRA project tracking and reporting systems, as required. - Provides the customer with project metric reports, i.e. Key Performance Indicators (KPIs), as agreed with the customer at project initiation, if applicable. This may be screen shots from the Oversight Dashboard. | During project execution |
| 6.2.11 | RPM | Customer Management - Arranges customer meetings at a frequency stipulated in the SOW or as agreed at the Kick-off meeting with the customer. Agreed meeting frequency could also change during the execution of the project as agreed with the customer, and additional meetings may be conducted as needed if budget allows. - Encourages regular customer feedback on project progress and quality of deliverables and acts on feedback as applicable. - Sends GRA Customer Feedback Survey at appropriate milestones or intervals for the project, as applicable. - Documents in meeting notes the key decisions agreed with the customer, confirms with the customer and communicates to the project team. Informs GRA Resource Manager or Line Manager as appropriate. - Addresses customer concerns or complaints and resolves in a timely manner. Escalates to GRA Resource Manager or Line Manager and QA representative, as appropriate, as per CS_OP_QA002 Quality Issue Management. | During project execution |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.12 | RPM and RTM | Scope of Work Change Management - Identifies out of scope work on an ongoing basis. Changes in the scope of IQVIA, customer and/or vendor responsibilities will be managed using Change Orders to the current contracts. - Requests a CO via a web form. (https://www.tfaforms.com/358079) - All changes to the project should be documented in GRA Project Change log as defined in Appendix E. | During project execution |
| 6.2.13 | RPM | Project Finances - Manages project finances (labor and expenses) in accordance with what is defined in the SOW. Refer to Section 6.4. | During project execution |
| 6.2.14 | RPM | Project Governance - If established with the customer, participates or reports to the Project Governance team, as described in the Project Instructions. - When requested, presents at the internal GRA Project Review meetings which provide internal GRA project governance. | During project execution |
| 6.2.15 | RPM | Continuous Improvement - Leads or appoints a RTM to lead Continuous improvement initiatives for large projects (or as agreed with the customer). | During project execution |

  - Project Close Out

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | RPM | Deliverables and Returnables - Oversees the delivery of all deliverables to the customer as specified in the SOW and check for remaining budget, if any. - Confirms with customer that the project is considered complete and that the SOW can be closed. - Verifies that all relevant documents/material/equipment have been returned to IQVIA/customer/vendors, as outlined in the SOW, if applicable. - Requests customers/vendors to confirm receipt of returned materials in writing, if applicable. - Review the Change Order as well, which was raised with SOW and confirm with the client, there is no outstanding actions is pending. - Using the Peoplesoft Finance reports: | At project close out |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Verify the exact final budget for task completion, time and expenses for reconciliation. - Validate the final monthly invoice captures all outstanding fees to be billed. - Confirm with PSA Accounts Payable that all invoices have been paid by the client. - Review any backlog with the project Finance Manager (PFM) and remove backlog, if required. - Verify all tasks for the project is PSA system are completed and project close-out tasks have been completed and status changed to “Complete”. - Finally, notify that the project is completed and verify the PFM has deactivated the project code. |  |
| 6.3.2 | RPM | Project Quality Close Out Review - Project PI should be archived in project file at closer of the project and won’t require any further update or revision. - Verify the metrics (Key Performance Indicator) are reported in the Oversight Dashboard for each month, including the last active month of the project. - Verify all project documentation required to demonstrate compliance are complete for the whole project team and fined in the project file. - Run final compliance reports for Training Compliance Record and upload in the project file, in case of future audit. If there are any non-compliances, investigate the reason and record whether it was caused by the client or project team member (i.e., client or IQVIA dependency). - Also, review and close Risk Log, if set up for project. | At project close out |
| 6.3.3 | RPM | IQVIA Technology System - Remove client and team members access from the SharePoint, as appropriate. - PSA resource planner should be updated with end-date to prevent the team forecasting time to the project after it is closed. - Client system access should be deactivated for all the project teams. | At project close out |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.4 | RPM | Resource and Vendor Management - Check all project team transitions throughout the project are documented and filed. - Notify Line Mangers of the availability of their staff that were on the project. - Also, for all vendors/subcontractors annual review has been documented. | At project close out |
| 6.3.5 | RPM | Lessons Learned (applicable to marketing application, large projects or at customer or GRA management request) - Review record related to continuous improvements and log outcome with appropriate information in a template described in Appendix F. - Organizes a “Lessons Learned” meeting with internal and/or customer project teams at appropriate intervals throughout the project. At a minimum, a “Lessons Learned” meeting should be conducted at the end of a project, if applicable. - Lessons Learned discussion should cover Walls, Wins and Wisdoms and should be recorded in the “Lesson Learned Library” for improvements of deliverables quality in the future GRA projects. | At project close out |
| 6.3.6 | RPM | Project Archiving - Organizes the regulatory project file for archiving (refer to CS_WI_RM0285 Archiving, Destruction, and Shredding), if project files have been managed in IQVIA systems. - Coordinates the archiving process with RTMs as appropriate. | At project close out |

  - Project Finances

The project budget (labor and expenses) defined in the SOW should be managed as detailed. Financial planning activities include, but are not limited to:

    - Reviewing the SOW and highlighting critical components, e.g. bonus/penalty clauses, time for presentation of pass-through expenses, etc.

    - Communicating project budget to RTMs for the portion of the budget for which they are responsible.

In general project finances will include:

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | RPM | Initiate Financial Processes - Reviews the SOW, budget (which will either be Fixed Price or Fee for Service or a combination of both) and identifies resource requirements. - Informs PFM whether the project will be an Estimate at Completion (EAC) project. Note: EAC should not be used for large unit-based projects or consultancy projects - Liaise with the PFM to activate the project code within PeopleSoft (PS), if not activated. - Liaise with the PFM to allocate appropriate budget per country for fixed-price projects (based on the assigned resources’ locations). - Liaise with the PFM to upload the agreed rate card for fee-for-service projects. - Liaise with the PFM to establish procedures for pass- through and sub-contractor expenses, as applicable. - Trains the RTMs on appropriate time-sheet coding, including, if necessary, issuing time coding instructions. | At project initiation, once the project has been contractually awarded or an Authorization to Proceed (ATP)/ Letter of Intent (LOI) is signed |
| 6.4.2 | RPM | - Reviews project hours reports to verify that time is coded by appropriate regulatory RTMs to the appropriate codes and verify that time is in keeping with the contracted budget. - Actions as necessary to rectify any errors. - Initiates and approves invoices and pass-through costs monthly or as stipulated by the SOW invoicing schedule. - Monitors budget cost versus total expected cost (actual cost to date plus expected cost to complete) as required, taking corrective action where appropriate. - Monitors recognized revenue versus actual costs taking corrective action where appropriate. - Submits the revenue recognition and backlog. - Reviews finance reports as provided by PS or the PFM. As necessary, discusses monthly financial status with the PFM. | At least monthly during project execution for NON-EAC projects |
| 6.4.3 | RPM | - For EAC project: Updates and submit EAC | Monthly, on the third full week of each month (EAC Week) |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.4 | RPM | - Verifies that correct final budget is in PeopleSoft Financials, all tasks are complete, and all time and expenses are reconciled. - Verifies that all pass-through expenses have been submitted and invoiced. - Verifies that all invoices have been generated and paid by the customer. - Notifies the PFM that project is complete, providing written confirmation from the customer. - Verifies that project code is deactivated. | At project close out |
| 6.4.5 | RPM | Works with the PFM to review monthly financial status. | At project initiation, during project execution and at project close out |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_RA032 | Global Regulatory Affairs - Preparation, Quality Control and Provision of Regulatory Affairs Deliverables |
| 7.2 CS_WI_RA0270 | Global Regulatory Affairs - Quality Oversight |
| 7.3 CS_WI_RM0285 | Archiving, Destruction, and Shredding |
| 7.4 CS_TP_PL0073 | Project Instruction |
| 7.5 CS_OP_QA002 | Quality Issue Management |
| 7.6 CS_WI_PL0024 | Project-Specific Training and Team Member Transition |
| 7.7 CS_WI_PL0027 | Project Vendor Management |
| 7.8 CS_FM_RA0298 | GRA Note to File (NTF) |
| 7.9 CS_FM_RA0301 | Global Regulatory Affairs - Project Team Member Transition Form |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_RA0273 | Global Regulatory Affairs – Project Management of GRA Projects | 5 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added Regulatory Intelligence, Regulatory Publishing and Labelling Maintenance. | Section 2 | To ensure SOP is applied to wider GRA services. |
| Added text ‘Clinical projects with GRA services’ |  | To clarify the meaning of full- service projects. |
| Renamed roles to RPM and RTM | Section 3 and 6 | To be consistent with other GRA work instructions |
| Multiple updates in Section 6 | Section 6 | To ensure steps are aligned to current GRA practice. |
| Added Appendices in Section 10 | Section 10 | Appendices C, E and F are included as supporting templates for GRA projects and appendices numbering is updated to accommodate the new additions. |

- APPENDICES

  - Appendix A: Process flow

  - Appendix B: Examples of GRA Project File Structures

  - Appendix C: Risk management Log

  - Appendix D: Example of GRA Project Action Log

  - Appendix E: Project Change Log

  - Appendix F: Lesson Learned Library

Appendix A: Process Flow

Appendix B: Examples of GRA Project File Structures

The GRA Project File Structure is a standard approach to setting-up and managing electronic regulatory project files on secure shared drives on the local server and/or ELVIS. The RPM or designee can adapt this structure as necessary. It may be appropriate to have different structures in different regions.

- Europe

CUSTOMER NAME PROJECT NAME

Project Management

  - Contract

  - Finance

  - Guidance documents

  - Meetings

    - Kick-Off meeting

    - Team meetings

  - Planning

  - Status reports Project documents

  - Deliverable

  - Source documents

Regulatory Authority Correspondence (where applicable)

  - Country

    - Submission (Date)

    - Approval (Date)

- Latin America

Example 2:

Example 1:

Appendix C: Risk Management Log

| RISK MANAGEMENT LOG |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Category | Risk Identification | Root Cause | Impact Description | Identified Date (DD-MMM- YY) | Responsibility | Status | Risk Owner | Probability | Impact | Mitigation Action |

Appendix D: Example of GRA Project Action Log

The GRA Project Action Log is a standard approach to setting-up and document any actions (internal and customer) up until completion. The RPM or designee can customise this structure as necessary to make it project specific.

| Customer: |  |
| --- | --- |
| Project Code: |  |
| RPM: |  |

| Date of Action | Responsible Person for Action | Action | Status of Action | Date of Completion |
| --- | --- | --- | --- | --- |

Appendix E: Project Change Log

All changes to the project should be documented in GRA Project Change log.

| Customer: |  |
| --- | --- |
| Project Code: |  |
| RPM: |  |

| Date | Detail/scope | Dose | Date | List of PI(s) | Date PI(s) | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Change | of Change | the | MSA or | requiring | are | Person |
| Identified |  | change | WO is | updating (if | updated |  |
|  |  | impact | updated | applicable) |  |  |
|  |  | the MSA |  |  |  |  |
|  |  | or WO? |  |  |  |  |
|  |  | (Y/N) |  |  |  |  |

The majority of changes to a project will require the project instruction(s) to be reviewed to determine if an update is required. Detailed below are list of changes that may ocour during a project.

| Change | Where to document |
| --- | --- |
| Organization of team(s) | Document in Project Instruction |
| Change to Team members | Refer to section 6.2.4 of this WI |
| Roles and responsibilities | Document in Project Instructions |
| Client SOPS changes | Update Training Plan for the client/project to list the updated SOPs applicable for each role |
| Scope of services | Change Order will be required to update the MSA or Work Order. Project Instructions will also require to be reviewed and updated |
| IT/Systems changes | Document in Project Instructions |
| Transition/Handover from client | Detail on Handover form (CS_FM_RA301) or on Client version of form |
| Internal handover | Detail on Handover form (CS_FM_RA301) |

|  | Document Title: Global Regulatory Affairs - Project Management of GRA Projects |
| --- | --- |
|  | Document Number and Revision: CS_WI_RA0273 Revision 6 |

Appendix F: Lesson Learned Library

| GRA Lessons Learned Library (refer to Lessons Learned Guideline on GRA PMO Team for guidance on the Lessons learned process) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Last reviewed: DD-MMM-YYYY |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Customer | Project Code | Project Name | Therapeutic Area | Topic | Project Status | Wins (what went well) | Walls (what not went well) | Wisdoms (what could be done differently next time) | Regions Involved | Lesson Learned Date | Show Customer | Created By Resource | Created Date |

Page 21 of 21

Copyright © 2015, 2017, 2019, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings, Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

# UNCONTROLLED COPY CS_WI_RA0273 Revision 6 - EFFECTIVE on 01-Jul-2022

UserName: Singh, Priti (q823374) Title:

Date: Monday, 06 June 2022, 05:18 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Lewicky, Tamara (q730348) Title:

Date: Monday, 06 June 2022, 05:44 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: SENGAR, SATISH (q1036027)

Title:

Date: Monday, 06 June 2022, 08:05 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nandikonda, Sruthi (u1076598) Title:

Date: Monday, 06 June 2022, 08:26 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Glizer, Veronica (q735279) Title:

Date: Monday, 06 June 2022, 10:07 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: NAJI, Kenza (u1090913) Title:

Date: Monday, 06 June 2022, 01:49 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Corley, Helen (q730385) Title:

Date: Thursday, 09 June 2022, 03:40 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================