|  | IQVIATM Work Instruction Project Strategy and Proposal Development |
| --- | --- |
|  | Document Number and Revision: CS_WI_TSS0004 Revision 4 |
| Document Owner: Irene Neilson | Author: Eduard van Rijen |

# PURPOSE

To describe the process for responding to a Customer’s Request for Proposal (RFP) for a clinical study where a core strategy is required.

# SCOPE

This work instruction (WI) applies to staff involved in the proposal development process. This WI does not apply to single service projects.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Analytics Strategy Lead (ASL) | 6.1.,6.2,6.7 |
| Business Development (BD) Representative (Rep) | 6.1, 6.2, 6.5 |
| Feasibility Analytics (FA) | 6.2 |
| Global Business Operations (GBO) Triage Manager | 6.1 |
| Medical Strategy Lead (MSL) | 6.2 |
| Project Leader (PL) | 6.2, 6.7 |
| Project Leadership Representative (PL Rep) | 6. 2 |
| Project Leadership Resource Manager (PL RM) | 6.1 |
| Proposal Developer (PD) | 6.1, 6.2, 6.3, 6.4 |
| Therapeutic Strategy Lead (TSL) | 6.2, 6.3, 6.4, 6.5, 6.7 |
| Site Analytics (SA) | 6.2 |
| Strategic Pricing Representative (Rep) | 6.3 |

# DEFINITIONS

Also, refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services.

Triage Managers: Triage Managers are resources from Global Business Operations (GBO), Therapeutic Science and Strategy Unit (TSSU), Applied Data Science Center (ADSC) and Delivery Strategy & Budget (DSB) with the appropriate user permissions in the Salesforce Customer Relationship Management system (CRM) which allows them to manage resource requests.

Proposal Knowledge Information Transfer (P-KIT): A collection of key documents to provide all the relevant information obtained during the proposal and bid defense phase, that is required by the project team to finalize the Customer contract, create the initial risk log and start creating project plans quickly after project award.

For more information, refer to Appendix A: Proposal Knowledge Information Transfer (P-KIT)

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

The tasks in this WI assume a typical Request for Proposal (RFP) with a 10-day turnaround for a core strategy in an indication or therapeutic area where sufficient internal and/or external data can be accessed, allowing the team to make informed decisions with regard to the project strategy.

An overview of the processes for the strategy and proposal development described in subsections 6.1 to 6.7 is shown in Figure 1.

Figure 1 – Proposal Timeline

## RFP Triage

Resources from GBO, TSSU, ADSC and DSB are requested and assigned in CRM. Resource Requests are created when the BD Rep enters the RFP in CRM and creates a new clinical bid.

Any other stakeholders that are required to support the strategy development are notified of the opportunity through the triage email that is sent to the respective mailboxes or contacts. Resources are assigned via their usual resource management method. Refer to the applicable operating procedures for the relevant group.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | BD Rep | Receives notification of the RFP from the Customer. | Pre-Award; before Strategy Call |
| 6.1.2 |  | Follows up with the Customer to confirm needs and requirements; offers clarification and addresses any questions. |  |
| 6.1.3 |  | Creates the RFP in CRM and adds a clinical bid detailing the Customer’s request: - The requested internal services selected by the BD Rep are required to identify which services are to be considered for inclusion in the proposal. - Resource Requests are created where appropriate for GBO, TSSU, ADSC and DSB and assigned by the triage managers for each group. - The triage email is automatically sent to the GBO Proposals mailbox. The email provides an overview of the clinical bid detail and services requested along with a link to the BOX folder containing the RFP documents. |  |
| 6.1.4 |  | Adds the RFP documents to the BOX folder which is automatically created when the clinical bid is created. The BOX folder holds and maintains all proposal-related documentation, communications, and key deliverables. |  |
| 6.1.5 | GBO Triage Manager | Distributes the triage email to the stakeholder groups, according to service areas selected in the clinical bid. | Pre-Award; As soon as possible upon notification of RFP |
| 6.1.6 | PL RM | Allocates a PL or a PL Rep. |  |
|  |  | Note: Until a PL is assigned, a representative from Project Leadership will fulfill PL responsibilities. A summary of the key responsibilities includes: |  |
|  |  | - Guide strategy development - Assist with country selection - Highlight operational risks, contingencies, and opportunities - Support the Bid Defense - Assume budget responsibility |  |
| 6.1.7 | PD | Schedules the Strategy Call. | Pre-Award; before Strategy Call |
| 6.1.8 | ASL | Schedules the Data Call. |  |

## Project Strategy

Upon assignment, the strategy team reviews the RFP to determine project requirements, Customer preferences, timing of response, and complexity in preparation for the Strategy Call.

Stakeholders who review the RFP are applicable to the various services that may be involved in the opportunity.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | All stakeholders | Update Unity with answers, comments and questions related to the RFP. | Pre-Award; before Strategy Call |
| 6.2.2 | PD | Conducts Strategy Call to discuss RFP response strategy, including: - Customer Needs - Business win strategy - Protocol highlights - Timelines - Customer history - RFP assumptions and specifications. - Risks and opportunities - Assess for Business Conflict of Interest - CV’s to be included in the proposal - Note: Key attendees are PD, BD Rep, TSL, MSL, ASL, PL or PL Rep and DSB | Pre-Award; Strategy Call |
| 6.2.3 | PD | Ensures that Unity is complete with questions that are to be presented to the customer to clarify the RFP information. |  |
| 6.2.4 |  | Requests the CVs for all services required for inclusion in the proposal with the exception of the PL CV which is provided by the PL Rep. | Pre-Award; after Strategy Call |
| 6.2.5 | BD Rep | In collaboration with the TSL and MSL engages with the customer to clarify RFP requirements. | Pre-Award; after Strategy Call |
| 6.2.6 | ASL | Conducts the Data Call to discuss research and data analysis required for the creation of the optimal strategy solution for the RFP. Note: Key attendees are ASL TSL, MSL, PL or PL Rep, FA, and SA.. Other groups may be invited depending on the scope. | Pre-Award; After Strategy Call but before MAP Call |
| 6.2.7 |  | Schedules Metrics Analysis Planning (MAP) call. |  |
| 6.2.8 | ASL TSL, MSL, PL or PL Rep, FA,SA | ** Data Acquisition and Analysis ** Mine and analyze numerous data sources and intelligence in support of Protocol, country, and site strategy and enrollment projections. Share findings with the TSL and other team members. |  |
| 6.2.9 | ASL | Conducts MAP Call to create the optimal strategy (countries, sites, recruitment rates, patients per country and timelines). This | Pre-Award; MAP Call |

| No: | Who: | Step: |  |  |  | When: |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | could include multiple scenarios. Depending on later research findings, the strategy may be updated. Note: Key attendees are ASL TSL, MSL, PL or PL Rep, FA, and SA.. Other groups may be invited depending on the scope. |  |  |  |  |
| 6.2.10 | ASL | Distributes the output to the team. Note: The output is used by the PD to incorporate into the pricing tool. |  |  |  | Pre-Award; After MAP Call |
| 6.2.11 | PD | Schedules the Challenge Call to validate the proposed strategy. Note: Key Attendees |  |  |  | Pre-Award; After MAP Call |
|  |  |  | Attendee | Role |  |  |
|  |  |  | PL Leadership | Approver |  |  |
|  |  |  | Sales Leadership | Approver |  |  |
|  |  |  | TSSU – TSL Leadership | Approver |  |  |
|  |  |  | TSSU – MSL Leadership | Approver |  |  |
|  |  |  | PD | Chair |  |  |
|  |  |  | TSL | Presenter |  |  |
|  |  |  | BD Rep | Presenter |  |  |
|  |  |  | MSL | Presenter |  |  |
|  |  |  | PL or PL Rep | Attendee |  |  |
| 6.2.12 | PD | Conducts Challenge Call. |  |  |  | Pre-Award; Challenge Call |
| 6.2.13 |  | Summarizes any actions where applicable for the team |  |  |  | Pre-Award; After Challenge Call |
| 6.2.14 | TSL | Follows up on any action items and if applicable updates strategy. Sends to the PD to update the pricing tool. |  |  |  |  |
| 6.2.15 | PD | Distributes updated strategy, if applicable and obtains the required approvals as per step 6.2.11. |  |  |  | Pre-Award; After Challenge Call |

## RFP Pricing

Preparation of the IQVIA Budget, is an iterative process with multiple reviews by PD, TSL, PL Rep, DSB and stakeholders.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | PD | Incorporates the assumptions and specifications of the RFP into the pricing tool. Note: In collaboration with DSB, the PD holds overall responsibility to assure that the correct service assumptions and specifications are entered. | Pre-Award; after Strategy Call |
| 6.3.2 |  | Incorporates the MAP output and RFP assumptions and specifications into the pricing tool. Distributes to the Stakeholders of the relevant services for review. | Pre-Award: After strategy is developed and before Sign Off Call |
| 6.3.3 | Stakeholders | Review and provide updates where relevant. | Pre-Award; Before Sign Off Call |
| 6.3.4 | PD | Reviews draft Budget with TSL and PL Rep to confirm strategy is accurately reflected and pricing seems accurate. Note: If further discussion and adaptation is required for one or multiple services the PD will schedule a call with the SME(s) for the relevant service, TSL, PL Rep and PD to review (budget scrub call). If the IQVIA labor budget value >25M USD, a Deal Review Call is required before the Sign Off Call | Pre-Award; Before Sign Off Call |
| 6.3.5 |  | Informs the assigned Strategic Pricing Rep as soon as they know that the opportunity will exceed 25M USD | Pre-Award; Before Deal Review Call |
| 6.3.6 | Strategic Pricing Rep | Co-ordinates the preparation with the stakeholders. | Pre-Award; Before Deal Review Call |

| No: | Who: | Step: |  |  | When: |
| --- | --- | --- | --- | --- | --- |
| 6.3.7 |  | Conducts the Deal Review Call with support of the TSL and MSL. Key elements of discussion include: - Overview of the opportunity - Review of IQVIA’s competitive situation - IQVIA / Customer relationships - Selling and delivery strategies - Opportunity Risk Assessment - Proposed commercial approach |  |  | Pre-Award; Deal Review Call |
| 6.3.8 |  | Provides confirmation of commercial approach and action items (if required) to the PD. |  |  | Pre-Award; Before Sign Off Call |
| 6.3.9 | PD | Schedules the Sign Off Call if required or sends sign off email. If RFP value <$10M labor costs, an email sign off is sufficient. The sign off process is required to get formal agreement on overall price and deal construct. Key attendees are: |  |  | Pre-Award; Before Sign Off Call |
|  |  |  | Attendee | Role |  |
|  |  |  | PL Leadership | Approver |  |
|  |  |  | Sales Leadership | Approver |  |
|  |  |  | Strategic Pricing Lead | Attendee |  |
|  |  |  | DSB | Attendee |  |
|  |  |  | PD | Presenter |  |
|  |  |  | TSL | Attendee |  |
|  |  |  | BD Rep | Attendee |  |
|  |  |  | MSL | Attendee |  |
|  |  |  | PL or PL Rep | Attendee |  |
| 6.3.10 | PD | Conducts the Sign Off Call |  |  | Pre-Award; Sign Off Call |
| 6.3.11 |  | Summarizes any actions where applicable for the team |  |  |  |
| 6.3.12 | PD | In collaboration with the TSL, follows up on any action items and if applicable updates the pricing tool and obtains final approvals from approvers via email or second sign off call if required. |  |  | Pre-Award; After Sign Off Call |
| 6.3.13 |  | Files approved Budget in BOX.com |  |  | Pre-Award: After Sign Off Call and |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  |  | all approvals have been obtained |

## RFP Proposal Development

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | PD | Based upon strategy call discussion and Unity input, creates first draft of strategy text / slide presentation, and distributes for review and input to all stakeholders. | Pre-Award; After Strategy Call |
| 6.4.2 | Stakehold ers | Review first draft and update where applicable. Note: The PD is responsible for ensuring: the updates are made and capture IQVIA differentiating messaging; text is concise and focused, formatting and language are consistent. | Pre-Award: Throughout process prior to submission. |
| 6.4.3 | TSL | In collaboration with BD Rep carry out a final review and approve for submission to the Customer. |  |

  - Bid Defense Meeting

If IQVIA is invited to a Bid Defense Meeting (BDM) the team are assigned to develop a Bid Defense presentation.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | BD Rep | Updates CRM with the presentation date. The TSL and MSL assignments are created automatically with the update. | Pre-Award: Before BDM |
| 6.5.2 |  | Schedules a 1:1 meeting with the TSL, to define the storyboard (key win themes, differentiators, agenda topics, suggested attendees, and presenters) and map out the schedule for the preparation meetings for the BDM team. |  |
| 6.5.3 |  | Requests resources that are required to attend the BDM if resources have not been identified as part of the proposal process or if the resource is not available. |  |
| 6.5.4 |  | Sends out meeting invitations to the BDM team and provides the first draft deck with story board. |  |
| 6.5.5 |  | Conducts the first preparation meeting with the BDM team and provides insights to review customer background and culture, outline explicit needs and pain points, and review customer bid defense attendees. |  |
| 6.5.6 | BD Rep | In collaboration with the TSL provide a summary of roles and expectations for the preparation meetings and actual BDM. | Pre-Award: Before BDM |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.7 | TSL | Provides background information to Strategy and win themes to the BDM team |  |
| 6.5.8 |  | Provides the presentation component regarding the strategy. |  |
| 6.5.9 | BD Rep | In collaboration with the TSL support the BDM team with assuring the right win themes, differentiator messages are embedded in their presentations and that the overall story is concise, focused and covers the needs of the customer. The BD and TSL will prepare and support the BDM team also regarding the oral presentation, discuss potential questions, help with actual rehearsals to assure the actual presentation to the customer is successful and engaging |  |
| 6.5.10 | BD Rep | Co-ordinates the BDM with support from the BDM team. | Pre-Award: BDM |
| 6.5.11 | BD Rep | Follows up with the BDM for actions and next steps. | Pre-Award: After BDM |

## Rebids

After the proposal submission or bid defense, the customer may request revisions to pricing and/or strategy.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | BD Rep | Submits a rebid in CRM | Pre-Award; After proposal submission |
| 6.6.2 |  | In collaboration with the PD and TSL assess the required revisions and who is required to support. Note: Depending on the required revisions the rebid process may follow the full, or an abbreviated process as for the initial bid. |  |

## Strategy Handover

Upon study award the BD notifies the stakeholders that the project has been awarded.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.1 | TSL | Transfers to the assigned PL all pre-award information to understand the background and strategy and finalization of customer contract. (P-KIT) | Post Award. |
| 6.7.2 | ASL | Collaborates with SA and TSL to refine the site list (if applicable) prior to handover to operational team. |  |
| 6.7.3 | PL | Commences with transition meetings according to process outlined in CS_WI_PL0023 Project Lifecycle Planning | Post Award. |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_PL0023 | Project Lifecycle Planning |
| 7.2 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_TSS0004 | Project Strategy and Proposal Development | 3 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added Figure 1 – Proposal Timeline 6.0, former Appendix B: Timeline for Proposal Process | 6.0 | Provides better context in the main body of the WI without the need to move to an appendix. |
| Update to roles in line with departmental changes | Throughout | Department changes to role / group names |
| Removal of reference to Request for Information – RFI | Introduction, 6.1 | RFI process is managed by GBO and documented accordingly |
| Updates to process throughout | Throughout | Minor changes to process since last revision. |
| Removal of a separate appendix which outlines the PL/PL Rep’s role in the development of the proposal. Summarized role in section 6. | Appendix D: Proposal Development Process | Provides better context in the main body of the WI without the need to move to an appendix. |
| Addition of Bid Defense and Rebids | 6.5, 6.6 | Provide better overview of process not previously documented. |

- APPENDICES

## Appendix A: Proposal Knowledge Information Transfer (P-KIT)

Appendix A: Proposal Knowledge Information Transfer (P-KIT) Example of documents that may be included.

Example Documents

- Customer provided documents as part of the Request for Proposal (RFP) › Synopsis/Protocol, Questions & Answers, Specification documents/key assumptions documents etc. Note: In case of rebids, make sure latest documents are filed (e.g. updated synopsis, further Questions & Answers etc.)

- Link to UNITY

- Metrics Analysis Planning (MAP) Output(s) (countries/sites/pts/recr rates/timelines )

- Summary of data assets leveraged for MAP: › › Feasibility Analytics outputs and summary of data assets leveraged (e.g. country ranking, recruitment rate analysis, site/country outreach results, inclusion/exclusion patient attrition analysis, competitive environment etc.) › Final Data-Informed Protocol Assessment (DIPA) report › Custom Patient Density Analysis for Site Lists › Site Analytics outputs (site tiering list including patient density data, other)

- Budget documents upon which award is based › UPT (linked to customer grid if applicable), Investigator fees grant plan output, specified patient recruitment tools budget (if not specific in UPT), Q2 costing, QECG, Cenduit costing, etc. › 3rd party vendor documents received (budgets + assumptions etc.)

- IQVIA documents sent to Customer/final client deliverables › Proposal text/slides (pdf to customer, word for internal team), rebid text / slides › Final Customer/IQVIA costing grid › Other (e.g. separate assumptions document, or specific letter(s))

- Risk table

- Business conflict evaluation › If applicable copy of email/documentation of BCOI decision from BCOI Officer

- Bid defense slides

- Further documents supporting Strategy obtained during process (e.g. articles, etc.)

Page 11 of 11

Copyright © 2016,2017,2019,2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Blogg, Ken (q790237) Title:

Date: Friday, 27 August 2021, 05:24 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Sneed, John (q109205) Title:

Date: Friday, 27 August 2021, 11:42 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Monday, 30 August 2021, 03:36 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================