This template makes use of content controls as blue font to guide entry of project information. Complete the entries / actions for all content controls (advisable without using tracked changes to avoid errors / warnings / issues saving the file), and do not leave any content controls unaddressed in a finalized version of the Decentralized Clinical Trials Operations Plan (DCTOP).

- The DCTOP serves as the basis to document the planning and management associated with the application of Decentralized Clinical Trials (DCT) activities.

- The Decentralized Clinical Trials Lead (DCTL) is responsible for development of the DCTOP to reflect the Scope of Work (SoW), contractual agreements, Protocol Schedule of Assessments (SoA), information received from Sponsor and other Project Operational Leads.

  - Only tasks outlined in the SoW and budget should be outlined in the DCTOP. The DCTL should reconcile the draft DCTOP against the SoW to ensure consistency and alignment prior to finalizing. If the SoW changes during the project, the DCTL must review the DCTOP and ensure it is aligned with the SoW.

- Development and maintenance of the DCTOP should be executed before First Patient In (FPI) in accordance with CS_WI_PL0023, Project Lifecycle Planning.

- The DCTOP should be updated when changes to the approved Project Baseline and/or material changes to other core components are required.

- A draft of the DCTOP is to be reviewed by the Project Leader (PL), Clinical Lead (CL), DCT Implementation Manager (DCT IM), DCT Study Coordinators (DCT SCs) / DCT Study Assistants (DCT SAs) if assigned and required, along with additional stakeholders and the Sponsor.

- Use of co-branding (e.g., adding a Sponsor’s logo) when creating the DCTOP is not permitted.

- Information in the headers and footers of this template represent the minimum requirements to be included in these areas when creating the DCTOP for the project and must NOT be deleted (i.e., beyond the Instructions pages).

- The Table of Content must be updated once the DCTOP updates are completed.

- Once the DCTOP is ready for final signature, page numbers and headers must be checked for accuracy and electronic signature approval process to be initiated.

- The approved DCTOP is filed with the CS_TP_PL0013 Integrated Project Management Plan (IPMP) in the project-specific eTMF.

- Refer to the DCT Division of Responsibility for details on who to get input from, consult with and get approval from.

Decentralized Clinical Trials Operations Plan (DCTOP)

| Sponsor | Enter Sponsor Name |
| --- | --- |
| Protocol Title | Enter Protocol Title |
| Protocol Number | Enter Protocol Number |
| Project Code | Enter Project Code |

| DCTOP Version Number | Enter revision number for the most current version |
| --- | --- |
| DCTOP Version Date | Select date |

| DCTOP Authored By | Date | Signature* |
| --- | --- | --- |
| Enter Author’s Name Author’s Title | Enter date or Not applicable for e-signature |  |
| DCTOP Reviewed By | Date | Signature* |
| Enter Reviewer’s Name Reviewer’s Title | Enter date or Not applicable for e-signature |  |
| Enter Reviewer’s Name Reviewer’s Title | Enter date or Not applicable for e-signature |  |
| Enter Reviewer’s Name Reviewer’s Title | Enter date or Not applicable for e-signature |  |
| Enter Reviewer’s Name Reviewer’s Title | Enter date or Not applicable for e-signature |  |
| DCTOP Approved By | Date | Signature* |
| Enter Approver’s Name (usually the PL) Approver’s Title | Enter date or Not applicable for e-signature |  |

Version Control

| Approval Date | Version # | Changes Made to Prior Version |
| --- | --- | --- |
| Click to select a date | 1.0 (Initial Version) | Not applicable |
| Click to select a date | Enter Version Number | Provide brief description of changes made to prior version – now incorporated into this new version of the Plan - indicating the applicable revised section |

Document Storage

Upon completion of the eSign document approval process, this document must reside in the project’s Trial Master File (TMF).

PREFACE

DCTOP Purpose

- This plan is intended to provide the project team and key stakeholders with an overview of Decentralized Clinical Trials (DCT) engagement and integration into the project while working in parallel to underscore the assumptions, Scope of Work (SoW), issues and risks specific to the project.

- The plan will outline activities, information and expectations between the project’s DCT, Project Leadership and Clinical teams with the Sponsor, as well as communication with the site staff where applicable.

- Project-specific operational plans and documents will be developed according to CS_WI_PL0022, Applying SOPs and Project Instructions to the project and CS_WI_PL0023, Project Lifecycle Planning and archived in the eTMF.

- This plan is not shared with sites and would only be provided to regulatory agencies upon request. This plan will be archived in the eTMF, hence be reviewable during an audit.

DCTOP Scope

The DCTOP is a working document to be used throughout the duration of the project. The plan will be adapted and updated accordingly when processes and/or procedures for the project are modified.

All activities will be conducted in accordance with local regulations, the International Council for Harmonization/Good Clinical Practice (ICH/GCP), IQVIATM Standard Operating Procedures (SOPs), applicable Sponsor SOPs, the CS_OP_DCT0016 DCT Operating Manual and specific Project Instructions.

This DCTOP should be used in combination with the Clinical Operations Plan (COP) for [Select: Hybrid/100%] DCT studies. The Clinical Lead (CL) is responsible for the COP and the DCTL maintains responsibility for the DCTOP.

Glossary of Terms

For standard definitions of terms used in this document, refer to QG_OD_SMT0018, Glossary of Terms - Clinical Services

- ARMG		Access Request Management Group

- BCP		Business Continuity Plan

- DCT		Decentralized Clinical Trials

- DCTL		DCT Lead

- DCT LMS	DCT Learning Management System

- DCT IM	DCT Implementation Manager

- DCT IT IM	DCT Information Technology Implementation Manager

- DCTOP	DCT Operations Plan

- DCT SA	DCT Study Assistant

- DCT SC	DCT Study Coordinator

- DCT SS	DCT Solution Specialist

- DOA 		Delegation of Authority

- DPIA		Data Protection Impact Assessment

- DRP		Disaster Recovery Plan

- eISF		Electronic Investigator Site File

- RN		Research Nurse

- RNPS		Research Nursing and Phlebotomy Solutions

- RNPS RS	RNPS Regional Specialist

- PVM		Project Vendor Manager

- TPV		Third Party Vendor

Table of Contents

1.0	Protocol Overview	6

2.0	DCT Technology Strategy and Scope	8

3.0	Team Structure	12

4.0	Financial Management	20

5.0	Technology Plan, Data Protection Impact Assessment (DPIA) and Data Plan	24

6.0	Business Continuity Plan (BCP) and Disaster Recovery Plan (DRP)	25

7.0	Safety Reporting	30

8.0	Project Close Out and Study Hub Decommissioning	31

9.0	DCT Site Operations Scope	32

10.0	DCT Team Resources and Assignment to Sites	42

11.0	Project Team Training and System Accesses	42

12.0	Project Documents and File Set Up	44

13.0	Project Communication and Escalation	47

14.0	Participant and Site Contacts	48

APPENDIX A: Additional Project Resources	53

Protocol Overview

[Provide a high-level synopsis of the project that includes DCT scope and participant schedule of DCT events. Include the countries participating in DCT.] The [insert project description. For example: The XX project is a 50-week, randomized, double-blind, parallel group, multi-center project assessing the efficacy and safety of…]. The project population will consist of [insert project population description]. The main objectives of this project are: [Complete the Primary and Secondary Project Objectives] The [participant population, project design, the project drug administration schedule] make this project suitable for a [Select: Hybrid/100%] DCT approach. [The paragraph below is for Hybrid DCTs. Edit if your protocol is 100% DCT] Visits requiring [Edit: administering project intervention, magnetic resonance imaging, computed tomography or any other procedure listed in the protocol] will be completed on site, whereas the remainder of the visit procedures can be completed remotely by [select: a Research Nurse (RN), DCT Study Coordinator (DCT SC) and Site Coordinator] via tele-visit. DCT Scope: [Modify per project. Upon completion of the tables below, delete the tasks listed as “No” in column “DCT Scope (Y/N)”] Service / Feature; DCT Scope (Y/N); IQVIA/Vendor. Participant Management. Visit Scheduling. Visit Confirmation with the Participant. Randomization. Televisit. Document Upload. Notifications. OMNI Chat. Participant Contact Form (PCF). Data Entry in Electronic Data Capture (eDC). Adverse Event (AE) and/or Concomitant Medication Collection. Protocol Deviations. Treatment Dispensation, Medication Kit Tracking. eDiary (electronic Clinical Outcome Assessment (eCOA)). eConsent. Direct to Patient (DTP). Interactive Response Technology (IRT). Research Nursing and Phlebotomy Solutions (RNPS). [The paragraph below is for Hybrid DCTs. Edit if your protocol is 100% DCT] The DCT scope of the project offers sites and participants an opportunity for participants to complete some of the project visits remotely through a Hybrid DCT option. Participants under the Hybrid DCT approach will complete visits [insert project visits that will be performed at home] at home. Remote visits will take place at the participant’s home using Study Hub for tele-visits as detailed below in the participant journey. Protocol Assessments will be performed as per the Section [insert protocol Section number] “Schedule of Assessments”. Participant and Site Journey: [Modify per project, editable version can be found HERE] Approximately [insert number or participants] participants will be enrolled in this project from [insert number or sites] sites from [insert countries, you can distinguish countries using DCT].

DCT Technology Strategy and Scope

[Outline the technology strategy to include DCT Site Operations, and RNPS activities as well as other integrated systems within Study Hub along with the applicable SOPs. If Study Hub and Connected Devices integration is used, add the project details as this is use case specific]. [Modify per project] The project’s remote visits will be enabled by IQVIA’s DCT Platform technology, Study Hub. Study Hub incorporates tele-visit technology to connect participants with the Principal Investigator (PI), the rest of the site staff and the DCT team. Study Hub is also a collaboration platform that allows the PI and DCT project team to interact electronically, including document sharing and activity notification workflow. Study Hub is validated according to the applicable Code of Federal Regulations (CFR) 21 Part 11, Health Insurance Portability and Accountability Act (HIPAA) requirements and to process personal data in accordance with the applicable General Data Protection Regulation (GDPR)-compliant requirements . Study Hub can be used by the participant in a Desktop using the web browser version or in a Tablet and Smartphone using the iOS or Android Mobile App Version. The site staff can access Study Hub in a Desktop using the web browser version and can only access Lightning Experience on iPad Safari. [Remove if Referral Hub and/or DTP is not used] Participants will be recruited from the PI’s database as well as DTP recruitment methods by IQVIA’s recruitment team, where applicable. The technology application Referral Hub is a secure technology that is used to determine eligibility criteria of a participant to participate in the project through the pre-screening process. It is used to facilitate the recruitment management process by determining if the participant pre-qualifies for the project based on inclusion/exclusion criteria, and if eligible, provide their contact information to the site staff who will contact the referred participant, ideally within 24 hours. [Select: The site will arrange the participant´s First Office Visit (FOV) for further screening process OR potential participants will use an chat-based online scheduling assistant to book their FOV with the site]. The participant will attend the FOV and the PI and Site Coordinator will discuss project suitability and confirm the participant’s interest in the project. At the FOV, the participant will be provided the opportunity to sign the Informed Consent Form (ICF). After signing, the participant will then be screened to finally assess their eligibility, and if eligible, the participant will be enrolled and randomized onto the project. This website is hosted via IQVIA’ s DTP Participant Recruitment Website. If sites are using both Referral Hub and Study Hub, the Site Coordinator will manage the participants in Referral Hub until the day of randomization. Once a participant is randomized and has the "Initial Visit Scheduled" status in Referral Hub, the site will transfer the participant to Study Hub. See Referral Hub trainings for instructions in completing these steps. Participant Enrollment Journey: [Modify per project] [Remove if Site recruitment is not used] Participants may be recruited directly through the site at the pre-screening stage and entered directly into Study Hub by the site staff. To do so, the site staff must gather the verbal consent of the participant to create the account and enter the information, and note the verbal consent gathered in the participant’s (physical) medical records. [Remove if eConsent is not used and add project details] During the screening process, each participant will agree to participate in the project by completing an eICF remotely or in person with the PI or delegate via the eConsent technology accessed via a link within Study Hub. The eICF may be used to either supplement or replace paper-based informed consent processes in order to best address the participant’s needs throughout the course of the study. The informed consent process provides the participant with the opportunity to understand how their personal information will be collected and used. Whether the informed consent is obtained from the participant on-site or remotely, the eICF process must provide sufficient opportunity for the participant to consider whether or not to participate and to ask questions about the study before signing the eICF, as well as at any time during the participants’s involvement in the project. After reviewing the eICF and having all questions answered, the participant may sign the eICF and be enrolled in the project or refuse and not participate. If any or all of the consent process takes place remotely and is not personally witnessed by study personnel, the electronic system must include a method to ensure that the person electronically signing the informed consent is the participant who will be participating in the project or is the participant’s legally authorized representative. [Remove if on-site Consent is not used and add project details] During the screening process, each participant will agree to participate in the project by completing an ICF in person with the PI or delegate at the site. The informed consent process provides the participant with the opportunity to understand how their personal information will be collected and used. If the entire process takes place at the study site, the study personnel can personally verify the participant’s identification, review the ICF content, answer questions about the material, have follow-up discussions and witness the signing of the ICF. After reviewing the ICF and having all questions answered, the participant may sign the informed consent and be enrolled in the project or refuse and not participate. [Remove if IRT integration is not used. Modify per project after technical solution and participant/site data flow finalized] [Modify per project] The [insert project name] Hybrid DCT project will utilize Study Hub to connect the participant with the project team for remote project visits and electronic sharing of [Select: medical records/source documents]. Tele-visit technology incorporated into Study Hub enables the participant to participate in the project remotely. Using high resolution live video technology incorporated into Study Hub, tele-visits allow the PI, participant, Site Coordinator and DCT SC to interact simultaneously from different locations with ease and effectiveness. [Modify per project or remove if RNPS is not scoped] RNs, part of the RNPS team, will be trained and deployed to the participant’s location to conduct project procedures as delegated by the PI. The PI and Site Coordinator will have access to project data from home visits through paper source and uploaded copies in Study Hub. The DCT [Select: SA/SC] will ensure all parties are connected via tele-visit in Study Hub. The PI will join visits as needed. [Remove if eDiary or eCOA is not used and add project details] Study Hub can collect information in the form of an eDiary. For an eDiary to be enabled, an account is established for the participant in the eCOA system under a Study Hub ID. The IQVIA eCOA is an advanced study build and execution platform to optimize real-time, direct-from-patient data collection. The eCOA system, assigns eDiaries to participants once enrolled in the project to complete through the Study Hub system at programmed intervals. The participant enters data into the eCOA system from the device allocated for the project (own or provided by the Sponsor). When eCOA is used integrated with Study Hub, participant identifiable information kept in Study Hub is pseudonymized when transferred to eCOA. [Modify per project] The informed consent, screening and randomization visits will be completed at the site for all participants. Participants will [select if applicable: choose to complete all their visits at the site or to complete their visits via the Hybrid DCT model] during the consenting process. Investigational Product (IP) prescribed by the PI will be [select: dispensed and administered at the site OR will be administrated remotely by a RN]. DCT Tech Flow: [Modify per project – editable version can be found HERE]

Team Structure

[The paragraph below should outline project-specific resource requirements as per the contract with Sponsor and team approval process (including Curriculum Vitae (CV) review/approval by Sponsor) as applicable]. Allocation of project team resources will be conducted according to CS_WI_PL0060 Project Resource Management. Project team transitions will be managed according to CS_WI_PL0024, Project-Specific Training and Team Member Transition and as defined in the project Integrated Project Management Plan (IPMP).

DCT Project Team Responsibilities: [Modify per project, remove activities not performed on the project as per the SoW]

| DCT Project Role | Responsibilities |  |
| --- | --- | --- |
| DCT Project Oversight | - Provide support/guidance to DCTL as needed and ensure consistency between Sponsor projects. - Point of escalation for both IQVIA and Sponsor team when required. |  |
| DCT Lead (DCTL) | Setup and Start-Up: - Engage DCT Vendors 4-5 months prior to First Patient In (FPI) with the Vendor Management Office (VMO) and Project Vendor Manager (PVM) [remove if there are no DCT Vendors]. - Review initial SoW with regards to DCT related deliverables, review related budget, annotate for needed changes or clarifications and provide feedback to the Project Leader (PL). - Participate and provide DCT input in Customer Expectations Meeting, Internal Planning Meeting, Kick-off Meeting. - Develop DCT Operations Strategy including for DCT Site Operations team, DCT IM, Study Hub team and [select if applicable: DCT Vendors / Third Party Vendors (TPVs)]. - Create DCTOP (for IPMP) and DCT Site Operations Playbook (if applicable). - Provide DCT input on the Site ID strategy and procedures to Site Activation Management (SAM), as DCT and the technical parameters associated with the project may impact the sites selection process. - Provide SAM and Site ID team with the DCT briefing notes to be included with the Site Selection Questionnaire (SSQ) to explain the DCT project strategy. - Work with the SAM, CL and PL to ensure DCT is considered and incorporated in site contract, Recruitment Strategy related to DCT activities, budgeting process, ICF strategy, TMF placeholders creation, Core Quality Control (QC) checklist, QRPM:PPM Set-up, Study Risk Management Plan and Risk Assessment Mitigation Plan (RAMP) for IQVIA Risk-Based Monitoring (RBM) studies. - Provide input of DCT elements to be added to COP and Site Activation Management Plan (SAMP). - Interface with DCT Solution Specialist (DCT SS) and DCT Implementation Manager (DCT IM) to ensure data flow prior to FPI. - Present the DCT Tech strategy for approval (perform a presentation meeting) prior to Study Hub configuration plan sign-off. - Obtain and provide project specific DCT Platform screenshots, DCT participant materials and other applicable DCT content for EC / Reg Submissions. - Oversee Study Hub configuration planning led by the DCT IM to include Study Configuration Internal User Acceptance Testing (SCIUAT) and Study Configuration External UAT (SCEUAT) execution. - Develop relevant training strategy and materials materials including Study Hub training slides for external and internal project team members training, including the DCT Material for the Investigator Meeting. - If applicable, establish an 'opt-in' strategy for sites and/or participants with CL that specifies timelines to communicate need to resourcing. - Provide to IQVIA Contact Center of the project specifics (countries, languages, site and particiapnt counts) to guide its staffing and resourcing decisions. - Understand and monitor Protocol and Country milestones relevant to DCT deliverables for initial assumptions and changes. - Send out DCT Platform Go-Live Notification. - Ensure DCT budget loaded in Peoplesoft and Estimate at Completion (EAC) baseline forecasting done. - Develop a country strategy and Data Protection Impact Assessment (DPIA) using the DPIA template. Upload DPIA Confirmation Form signed by Sponsor in TMF. - Complete the Data Plan template based on the DPIA and agreement with the Sponsor. - Work with key stakeholders on the project team to identify any lessons learned from start-up. Conduct: - Work as DCT Site Operations Functional Leader and serve as escalation point for project related questions and issues from the DCT Site Operations team. - Provide training to DCT Site Operations team as needed. - Interface with the PL and needed internal stakeholders for delivery of solution within project timelines and provide input and/or management of DCT elements for [select the applicable: eTMF, COP, IPMP, SAMP, Study Risk Review Management Plan, RAMP, RBM, ICF, QRPM:PPM, SSQ, EAC forecasting, etc.] as needed. - Participate as DCT Operational Team Lead in overall project team meetings. - Overall coordination and link between Information Technology (IT) and DCT Site Operations teams across key activities. Conduct and document regular internal DCT Operations team meetings. - Perform ongoing Resource Request for DCT roles (DCT IM, DCT SC, DCT SA). - Perform oversight of operational Study Hub performance metrics and run Status Reports. Identify improvements needed, escalate to Study Hub IT team, and manage the issue to resolution. - Responsible for DCT Financial Health, Out of Scope activities identification and management and Change Order (CO) budgeting. - Provide oversight and ongoing maintenance of DCT activities and documentation (DCTOP, DPIA and Project Instructions if applicable) in alignment with project milestones, deliverables and protocol amendments. - Maintains external and internal project team members training material on an ongoing basis. - Provide DCT Vendor Management and issue escalation [remove if there are no DCT Vendors]. - Should the DCT Technology be impacted by a protocol amendment, work with the DCT Regulatory Lead to complete and implement a regulatory evaluation of the impact of the amendment in the key DCT processes (including Site Operations and DCT Platform Configuration) from a regulatory perspective. - Manage Quality Issues (QI) related to scoped project DCT deliverables. QI and CAPA management (QI, audits, inspection findings). If performance issue with Site Operations team member, communicate this to DCT Site Operations Manager for appropriate management. Close-Out: - Work with CL and Centralized Monitoring Lead (CML) to ensure that any DCT specific activities related to site closure are added to project specific COP. - Complete DCT financial reconciliation and lessons learned for the project and DCT vendors. - Complete Study Hub system close-out procedures as approved by the Sponsor in writing, including request Study Hub data extraction for sites and Sponsor. - Work with key stakeholders on the project team to identify any lessons learned. |  |
| DCT Information Technology Implementation Manager (DCT IT IM) | - Coordinate creation of joint IT implementation project timeline. - Responsible for weekly IT implementation status call and corresponding meeting minutes. - Responsible for developing system data flow diagram. - Responsible for submitting AHA tickets for any enhancement requests. - Accountable for completing the Hypercare Scorecard and developing the Hypercare plan. - Complete the Hypercare Scorecard, develop the Hypercare plan and coordinate Hypercare if applicable. |  |
| DCT Implementation Manager (DCT IM) | - Attend DCT Solution Strategy delivery meeting. - Responsible for the Study Hub Implementation Plan and Schedule and build Study Hub Configuration Plan and Study Hub Configuration Checklists with oversight of the DCTL. - Collaborate with the applicable technology Product Owners to set up corresponding Study Hub integrations. - Coordinate efforts with the DCTL and DCT Data Privacy team to ensure Study Hub data flows, etc. are updated based on Sponsor approved, specific data correction, retention and deletion rules. - Build Integration Risk Management / Data & Disaster Recovery Plan. - Accountable for UAT of all Study Hub releases including SCIUAT , SCEUATand Sponsor sign off. - Work with DCTL as Study Hub configuration and integration changes are requested post go-live. |  |
| Decentralized Trial Analyst (DTA) | - Perform DCT activities as delegated by the DCTL, which may include but are not limited to: - Granting and following up on DCT Learning Management System (LMS) access - Working with Access Request Management Group (ARMG) (when applicable) on granting Study Hub access - Financial Tasks (i.e., EAC) - Taking and archiving meeting minutes - Assisting with regulatory submissions tasks - Assisting with Project Plan maintenance - Maintaining the training matrix and QRPM. |  |
| DCT Solution Specialist (DCT SS) | - Understand project strategy and develop Preferred DCT Solution (DCT Site Ops Strategy and DCT Data Strategy Toolkit to include the Data and Patient flow mapping). - Collaborate with Product Management and Sponsor success for the DCT operational perspective and inclusion in project specific tech solution. - Collaborate with Product Management and Sponsor success for bid defense presentations requirements for DCT. - Ensure the DCT Site Operations strategy is included in the solution design. - Bring in DCT Site Operations liaison early to identify resourcing gaps and identify operational solutions. - Ensure smooth transition of strategy to DCTL for implementation during the Strategy Handover Meeting (deliver DCT Solution Strategy*/ Kick-off / Expectations Meeting). |  |
| DCT Study Assistant (DCT SA) | - Responsible for administrative support related to Study Hub activities and logistics of the [Select: investigational medicinal product (IMP)/comparator drug/lab samples, televisits, etc.], as per project scope. - Provide Study Hub onboarding and orientation to the PI, site team and participants. - Route Delegation of Authority (DOA) Logs for signature by the PI, and concerning staff. - Support participants with technical issues, rescheduling visits and IP kit tracking. - Provide support with tablet and/or connected device logistics. - Retrieval of medical records from Health Care Practitionare (HCP) offices and upload them in DCT Platform, as defined per project scope. - Support Institutional Review Board (IRB) submission and approvals. - Responsible for PI support with regulatory documents and project close out procedures. - Support tasks in project execution per PI delegation as documented by the DOA [remove if the DCT SAs are not delegated in the DOA]. |  |
| DCT Study Coordinator (DCT SC) | All activities described for the DCT SA above, as well as specific tasks delegated by the PI to support project execution, including: - Support sites and participants with consent, medical records and scheduling visits. - Conduct remote participants visits and support televisits with PI as needed. - May collect information on AEs, drug accountability, concomitant medications and other duties. |  |

| RNPS Project Role | Responsibilities |  |
| --- | --- | --- |
| RNPS Lead | General: - Manage RNPS scope / time / budget management - Primary RNPS project Subject Matter Expert - Client / PL / PI communication - Investigator Meeting support - Project issue escalation / resolution / documentation - Project documentation authoring - Internal partnership management - Metric reporting - Finance management. - COs Start-up: - Review Project documents (protocol, project docs (lab/pharm/Investigator’s Brochure (IB)/site list)) - Organize & execute post-award meetings - Operationalize RNPS services and cross-functional partners (Healthcare Professionals Network (HCPN), Q2, DCT) - Create documents - Tech platform setup, LMS - Obtain document approval internal/external - Train and document team training - External vendor setup if needed Conduct: - RNPS project oversight - Internal/external meetings and general communication - Project/visit escalation - Project metrics |  |
| RNPS Regional Specialist | General: - Reporting project status/updates to RNPS Lead - Site communication regarding visits - Visit issue resolution / documentation - Local service partner alignment - Regional EAC - Proactive nurse allocation - Meeting support - Manage site / clinician team status Conduct: - Site Training and Site Initiation Visits (SIVs) - CRA training - Regional tech platform setup and management - Participant registration - Nurse identification - Nurse approval and delegation - Provide nurses with kits/supplies/equipment - Visit scheduling - Visit logistics - Visit support Source document review Equipment recalls and management |  |
| Research Nurses (RN) and Phlebotomists | - Under the supervision of the PI, execute visit procedures at participant’s home as delegated by the PI in the DOA Log and per RNPS training by RNPS Regional Specialist. - Report observed potential AEs/Serious Adverse Events (SAEs) to the DCTL, RNPS Regional Specialists and site staff according to RNPS project plan and training. - Document visit data within source documents. - For paper source documents, upload a copy into the approved site portal within 1 day of home visit completion for RNPS Regional Specialist review. - For paper source documents, return RNPS Regional Specialist approved and qualiy checked hard copy source document to Site Coordinator within 1 day approval. - Update source document as needed per visit related queries. |  |

[Modify per project]

IQVIA is responsible for overall management of the [insert project name] project, including both traditional and DCT cohorts [modify if your project in 100% DCT]. A PL oversees the project and has ultimate responsibility for the entire project and delivery of all IQVIA contracted components.

The [select the role: PVM / Project Management Analyst (PMA) /PL] has responsibility for integrating DCT deliverables into the overall project. An IQVIA DCT team consisting of [Select: DCT SAs, DCT SC and RNs] acting as delegates of the PI, will support project conduct including remote visits. The DCTL will oversee the [DCT SAs/SCs] and the RNPS Lead will oversee the RNs, RNPS Regional Specialist and RNPS Vendors if applicable. Project oversight and delivery of DCT components, including DCT Vendors if applicable, will be provided by the DCTL.

Project Team Structure: [Modify per project]

Financial Management

[Update relevant DCTOP sections based on hours scoped for work activity budgeted, keeping consistent with the Functional Time Coding Guidance. When executed COs include an update to the scoped hours, the DCTOP should be revised] Project finances will be managed according to CS_WI_PL0069, Project Finance using Estimate at Completion. The hours allotted for relevant tasks (communication with sites, project administration, project team meetings, trainings) are detailed in the Functional Time Coding Guidance. The DCTL, DTA, DCT IM and DCT [Select: SAs/SCs] code hours based on the following categories. For the DCT [Select: SAs/SCs] there is no distinction between start-up and project visit. Different subcategories depend on the activities performed. DCT Project Team Coding Guidance: [modify per project] DCT Roles; PeopleSoft Resource Category; PeopleSoft Category Code Description; PeopleSoft Resource Subcategory; PeopleSoft Sub-Category Code Description; Project Specific Task Time Coding Guidance. DCTL + DTA; 010; Service Lead; 005; Lead Activities; Lead activities associated with Study Hub set up and management / Activities related to DCT Site Operations Oversight / Monthly Finance tasks - Revenue, backlog, managing financial health, contract and CO management/ EAC / budget development. DCTL + DTA; 010; Service Lead; 006; Project Administration; Project system set-up and updates with PL / Translation of documents / Project status review / Risk Management with PL / Resource Management / Quality management. DCTL + DTA; 010; Service Lead; 007; Communication - Other; Communications, meetings, EAC, eTMF, other non-DCT Site Operations or Study Hub implementation activities. DCT IM; 030; Start-Up; 044; System Support; System Issues, Support of System Issues - UAT Testing - System Support: Study Hub, Clinical Ink, Cenduit, any other 3rd party vendor system required for DCT. DCT IM; 030; Start-Up; 071; Dataset Programming; Testing scenario and script review. SCIUAT support. SCEUAT conduct and documentation. Testing of configuration amendments.. DCT SA; 030; Start-Up; 001; Communication - Client; Participant Communication (Telephone, OMNI Chat), Participant Training, Data Surveillance Follow Up (Participant).. DCT SA; 030; Start-Up; 003; Communication - Sites; Training of Sites (i.e., Onboarding), White Glove Visits (before FPI, the DCT SA reviews all activities needed to conduct the first participant visit with the site staff), Call Center, OMNI Chat (Site), Finesse (Site), Data Surveillance Follow Up (Site). DCT SA; 030; Start-Up; 006; Project Administration; Project planning, set up and administrative activities: Internal Team Meetings, Data Entry, eTMF/Investigator Site File (ISF) Setup/Maintenance, Self-Training, Shipment of documents to sites, Patient Zero, IRB Support, Amendment Support. DCT SA; 030; Start-Up; 044; System Support; System Issues, Support of System issues, Study Configuration UATs, System Support: Study Hub, Clinical Ink, Cenduit, any other TPV system required for DCT.. DCT SC; 130; Subject Visits; 001; Communication - Client; Participant Communication (Telephone, OMNI Chat), Participant Training, Data Surveillance Follow Up (Participant).. DCT SC; 130; Subject Visits; 003; Communication - Sites; Training of Sites (i.e., Onboarding), White Glove Visits (before FPI, the DCT SC reviews all activities needed to conduct the first participant visit with the site staff), Call Center, OMNI Chat (Site), Finesse (Site), Data Surveillance Follow Up (Site). DCT SC; 130; Subject Visits; 006; Project Administration; Project planning, set up and administrative activities: Internal Team Meetings, Data Entry, eTMF/ISF Setup/Maintenance, Self-Training, Shipment of documents to sites, Patient Zero, IRB Support, Amendment Support. DCT SC; 130; Subject Visits; 044; System Support; System Issues, Support of System issues, Study Configuration UATs, System Support: Study Hub, Clinical Ink, Cenduit, any other TPV system required for DCT.. These hours, which are based on the agreed scope and budget, equate to the time expected to meet operational requirements and project milestones according to the project lifecycle. Team members must code actual, productive hours. If actual time needed to perform work activities varies from allotment according to the guidance in sections noted above, the team member must discuss with the DCTL to determine possible root causes. DCT Project Team Full Time Equivalent (FTE): [Modify per project] FTE; Start Up; Conduct; Close Out; Number of staff members allocated for FTE. DCTL. DTA. DCT SA. DCT SC.

4.1 DCT Billing and Invoicing

At the project set up, the DCTL works with PL and PMA to ensure DCT budget is correctly loaded in PeopleSoft Financial system to capture time and expense transactions by the Project Finance Manager (PFM) [insert if your project is an EAC project: and all EAC forecasting is put in place at the start of the project].

During project conduct, the DCT billing is performed in adherence with policies, IQVIA Finance Calendar, and any project-specific requirements communicated by PL.

[The section below is for process for EAC projects, remove if not applicable]

On Monday of the third full week of each month, unless indicated otherwise in IQVIA EAC Finance Calendar, the DCTL provides monthly consistent and accurate time and expense coding for DCT on to [Select: PL/PMA/PVM], as per CS_WI_PL0069, Project Finance Using Estimate at Completion, as well as ongoing DCT financial management of contract and DCT budget, to include out of scope activities and change orders in relation to the DCT budget.

[The section below is for process for non-EAC projects, remove if not applicable.]

On Monday of the third full week of each month, unless indicated otherwise in IQVIA Finance Calendar, the DCTL provides monthly consistent and accurate time and expense coding for DCT on to [Select: PL/PMA/PVM], as per CS_WI_PL0026, Project Finance (non-EAC), as well as ongoing DCT financial management of contract and DCT budget, to include out of scope activities and change orders in relation to the DCT budget.

[Modify per project]

Besides, the DCTL also provides monthly input to bill the Sponsors for the work performed on the project according to the payment terms dictated by the Master Services Agreement (MSA)/Contract with the Sponsor. Through the [select: SMART Billing Unit Review (BUR) (for EAC projects) or SMART Revenue Deliverable Review (for non-EAC projects)], the DCTL confirms labor completed through the previous month, achieved milestones, per payment schedule requirements and pass-through expenses, which may include TPV payments. The monthly units billed for DCT with start/end dates agreed per the DCT budget for the executed contract are:

- [Insert your project Billing Units. Consider Labor fees, Study Hub Setup, Study Hub Configuration, Study Hub User Access Fees (Site and participant) and Vendor/Pass Through Costs]

For the DCTL financial activities during Close-out phase, refer to Section 8 of this document.

Technology Plan, Data Protection Impact Assessment (DPIA) and Data Plan

[Remove if DPIA is not applicable as per below] The DPIA Process is detailed in the CS_WI_DCT003 DCT Data Protection Impact Assessment Process and the process checklists, templates and detailed process are located in the Regulatory and Data Privacy SharePoint. The project specific DPIA is located in [insert signed DPIA link]. The DPIA may not be shared outside of IQVIA or the Sponsor. Therefore, a Data Plan is developed which summarizes many of the aspects of the DPIA, that can be shared with third partiessuch as inspectors and Ethics Committees. The Data Plan may be completed with the information agreed with the Sponsor in the DPIA. The project specific Data Plan is located in [insert signed Data Plan link]. Project systems set up and management will be conducted according to CS_WI_PL0052, Project Systems Management and CS_WI_PL0027, Project Vendor Management. Study Hub set up is managed in accordance with CS_WI_DCT0001, Study Hub Configuration and Testing. The process for granting access to Study Hub for sites participating in IQVIA DCTs will be conducted as described in CS_WI_DCT0005, Study Hub User Account Management. Study Hub Configuration Timelines: [Modify per project, to be provided by the DCT IM] System Type; System Name; Project Build Date. eDC. eCOA. IRT. eConsent. DTP Recruitment.

Business Continuity Plan (BCP) and Disaster Recovery Plan (DRP)

[The BCP is Operation’s responsibility, IT will provide input as required. The DRP is IT’s responsibility, the template link is provided below and should be replaced with the project-specific DRP.]

The IQVIA and [insert Sponsor name] BCP and Disaster Recovery Bridge Plan (DRP) [template] provide a framework for actions and measures required for maintaining business continuity and aim to reduce confusion during a Business Disruption Event (BDE) by anticipating critical impacts and establishing alignment between IQVIA, [insert Sponsor name] site staff and participants’ business continuity expectations.

A Business Disruption Event (BDE) is defined as an event that results in the inability of an organization to provide critical business functions for a predetermined period. Should a BDE occur affecting standard business processes at any clinical research-affiliated facility, timely restoration of business processes is the primary concern and responsibility of the organization.

These plans are implemented for Study Hub system-wide outages/issues and related systems which could include [select: Referral Hub, eConsent, eCOA, IRT and Contact Center] and provides guidance to sites, Monitors, DCT Team, participants & Sponsor to maintain business processes and responsibilities in the event of a BDE.

Each IQVIA facility has completed and approved site BCPs and DRPs which are stored in the IQVIA document management system, ELVIS. IQVIA DRPs are completed for applications and data centers.

IQVIA will work with following external parties depending on the issue during a BDE [insert/modify the applicable vendors below]:

- Salesforce (Study Hub)

- MuleSoft (Study Hub)

- Heroku (Study Hub)

- Cenduit (IRT)

- Amazon Web Services (eCOA)

- Connected Device Company

- DTP Shipping (CSM)

- eConsent

- Helpdesk

6.1 Rationale

The success of IQVIA global operations depends on the ability to provide business services in difficult and uncertain circumstances. IQVIA policy requires that a management process, with the goal of detecting serious risks using Business Impact Analysis (BIA) and risk assessments, be identified and safeguards against these risks documented and implemented in Business Continuity (BC), Disaster Recovery (DR). The purpose of this procedure is to (1) enable quick and targeted reaction to events that hinder SOPs and (2) facilitate the resumption of business activities as quickly as possible.

To meet these expectations, IQVIA has developed BCPs and DRPs. The BCP and DRP identify (1) critical operations, applications/systems, dependencies, and/or processes that deliver critical services and products and (2) strategies that ensure continuity of operations and business resilience. IQVIA recovery strategies are designed to remain focused on continuous and dependable delivery of critical services and products to project participants, employees, and Sponsors and maintain data integrity. Executive leadership and senior management are committed to providing the necessary capital, resources, and personnel to ensure that business continuity and disaster recovery missions are successful.

In all global events with potential impact to business operations, facilities/investigator sites, and/or employees, a business impact assessment is conducted, BC/DR teams are mobilized, employee safety is confirmed, and impact levels are assigned with corresponding communication reports. Key members of the IQVIA Crisis Management Team are engaged to drive crisis and communication decisions internally and externally. The need for timely and accurate communication to employees and Sponsors, the method of delivery, and the ability to answer questions represent the hallmark of the communication strategy.

6.2 IQVIA BCP/DRP Activation and Discontinuation

In the event that system(s) are down, IQVIA will notify appropriate stakeholder (Salesforce - Study Hub and/or Helpdesk) following the critical incident notification process until resolved. The Internal and External Study Hub Critical and High Impact incidents will be managed according to DCT Study Hub Critical & High Impact Incident Communication Plan.

Any reported issue should have a corresponding VIA ticket. All the tickets will follow the resolution target time, service levels and if needed will be escalated as detailed in the DCT Study Hub Standard IT Support Services Handbook.

Once systems are restored, notifications to stakeholders will be communicated according to the Critical Incident Notification Process as given in the DCT Study Hub Critical & High Impact Incident Communication Plan. The IT Service Owner is responsible for confirming that systems are restored.

6.3 IQVIA BCP for Study Hub and related systems

[The following sections should be completed for each technology in scope for the project. Study Hub template BCP included below for reference, modify as needed.]

Purpose

Study Hub incorporates telehealth technology to connect participants with the PI and the DCT project team. Study Hub is also an interactive collaboration platform that allows the PI and remote DCT team to interreact electronically, including [Insert Study Hub features. For example: document sharing, manage eCOA].

System Availability

Disaster Recovery (DR) Plan document to be referred. It will be provided if requested as part of audit or inspection.

BCP Scenario Planning (When System is Offline)

- Users are notified 24-48 hours in advance of all planned releases or outages.

- Study Hub and Study Hub integrations outages will be managed according to the table below with specific instructions to the sites and participants as applicable.

Instructions for Sites and Participants for Study Hub and related systems

[Modify per project as needed]

| System/Functionality Failure | BCP for Sites and Participants |
| --- | --- |
| eConsent | Site staff must ensure the ICF is signed prior to adding participants into Study Hub. If Study Hub is not available or the eConsent integration fails, the site staff can still use eConsent separately with any signature modality since the outage is with Study Hub/integrations. If there is a technical outage of eConsent, the site will need to proceed with onsite consent until the system is back. In this case, a paper ICF is to be signed in wet-ink. Besides, these wet-ink signed ICFs can be scanned and uploaded into eConsent by the site staff only if the setting which allows the upload is turned on and the country/site regulatory requirements allow it. If not allowed, this will be filled in the ISF. |
| DocuSign Integration | If DocuSign-Study Hub Integration fails, the person responsible for routing the DOA should route it directly from IQVIA DocuSign with Default Part-11 account configuration. If DocuSign is unavailable, the person responsible for routing the DOA will send it via email to all needed members, who will print the DOA, sign wet-ink and email it back to the sender. |
| DTP Recruitment (Referral Hub) | If Referral Hub-Study Hub integration fails, the site staff will manually enter and create the project participant account in Study Hub as per instructed in the Study Hub User Guides. Site staff must ensure the ICF is signed prior to adding participants into Study Hub. If a Referral Hub outage occurs, the user may contact the Study Hub 24/7 Participant Support Center for further assistance or guidance until Referral Hub is back. |
| Cenduit IRT | If failure occurs prior to participant randomization and Study Hub is unavailable during screening or randomization activities, the screening or randomization transactions via Cenduit (IRT) will be impacted. - Pre-consented: the participant does not exist in IRT, but sites do (pre-configured during or after project go-live). If the participant has not been created in IRT, a manual process should be put in place, where site personnel would interact with IRT to conduct necessary flows to create the participant directly in IRT, and then there would be manual entry on the Study Hub side once integration is restored. As part of the Study Hub-IRT Integration, IRT will receive a message to create the participant that includes the site ID after the participant has consented the use of Study Hub and has being created in Study Hub. For any manual entries, the IRT team need to receive the data entry points (what information or questions would be completed on the IRT form the site would normally run) in writing before they can proceed with any manual transaction. At this step there would not be any manual action to be completed directly on an IRT form. As is stated above, until the participant has consented to the project, no message is sent from Study Hub to IRT. As a result, there would not be an IRT form created for this step. - Consented: Study Hub would send a participant create message (including site ID) to IRT, and then the participant is created in IRT as “Pre-Screened”. If the Study Hub system is unavailable, the site staff can directly access the IRT web portal to create the participant status to “Pre-Screened” by creating the appropriate form (i.e. Participant Pre-Screening Form). If for some reason the site user could not access the form (i.e. internet is down), the IRT Help Desk can run the form on the site’s behalf with the end user providing the data entry points as mentioned above. Should the site staff need assistance, the Study Hub Help Desk can be contacted, who would contact the IRT Help Desk. - Screened: Study Hub would send a participant update message to IRT, and then the participant is updated in IRT as “Screened”. If the Study Hub system is unavailable, the site staff can directly access the IRT web portal to update the participant status to “Screened” by creating appropriate form (i.e. Participant Status Update Form). The form would make the update automatically and no manual intervention would be needed by the IRT Help Desk. Should the site staff need assistance, the Study Hub Help Desk can be contacted, who would contact the IRT Help Desk. - Randomized: - Study Hub would send a participant randomize message to IRT, and then the participant is updated in IRT as “Randomized”. If the Study Hub system is unavailable, the site staff can directly access the IRT web portal to randomize a participant through the appropriate IRT form (i.e. Participant Randomization form). If site staff need assistance, the Study Hub helpdesk would have to contact the Cenduit Helpdesk. - If the IRT system also has an outage, manually randomizing a participant can not be performed until the system is back based on Cenduit Quality Assurance (QA) policy. |
| eCOA (eDiaries) | If the project participant is already randomized, but the visit diary is not available to be completed by the participant, site staff should seek assistance from the Study Hub helpdesk to address any technical issues. [The following paragraph should be agreed with the project team member. Discuss with the PL, CL, eCOA and Study Hub Admin team and add if suitable for your project.] Should an outage occur with the eCOA-Study Hub integration, the eCOA web portal, called “eCOA Sculptor”, can be used independent from Study Hub to allow site staff to log in and have clinicians access the backup questionnaires on behalf of the participants. This back-up solution requires additional set ups by the eCOA team, specific training and monitoring. Paper backup is not encouraged due to issues with having mixed modes since the regulatory authorities intends to review the comparability of data obtained when using multiple data collection modes or types of administration within a single project to determine whether the treatment effect varies by modes or types used. |
| Study Hub (not able to access) | If, at any point the site staff is unable to access Study Hub, the user facing the issue should contact the Study Hub 24/7 Site Support Center for further assistance and/or email and communicate with the DCT SA/SC. If, at any point after randomization, a project participant is unable to access Study Hub, the participant should contact the Study Hub 24/7 Participant Support Center for further assistance. |
| Study Hub (televisit failure) | If a Study Hub outage occurs during a televisit session, sites should immediately contact the participant by telephone to complete the visit. If possible, the user facing the issue should call the Study Hub 24/7 Support Center for assistance and expedite a solution. If needed, the DCT SA/SC can be contacted by the Site Staff. |
| Study Hub (unable to upload source documents after visit completion) | All documents generated during an Study Hub outage (for example source documents) should be placed in the site’s central storage as per the site’s records management schedule and updated retrospectively in Study Hub once normalcy returns. Use site accepted electronic signature platform with part-11 compliance to upload source documents and receive PI oversight signature. If site does not have external electronic signature platform with part 11 compliance, site should use a secure encrypted email attachment and manual certification coversheet. If the site does not have email encryption, site should use paper documents and wet signature. If a disaster occurs accompanied by a prolonged outage, and staff and PI are in different locations, staff should utilize trackable currier services to acquire PI wet signature. |
| Study Hub (Monitors unable to perform remote Monitoring Visit (MV) | If, at any point the Monitor is unable to access Study Hub, all monitoring activities must proceed as per the Site Monitoring Plan timelines throughout system outage. The blinded Monitors, after approval, can reschedule their MVs if the Site Monitoring Plan has the flexibility and the site is available to reschedule in response to the system outage. In case that a MV cannot be rescheduled within Site Monitoring Plan visit frequency or additional MVs are needed due to a project deliverable (for example, data-base lock), the Monitor can conduct remote Source Data Monitoring (SDM) using an alternative secure document exchange, documenting the details in the respective Clinical Trial Management System (CTMS) Site Visit Report (SVR). Monitors should clarify the SDM method used for every MV. |

Safety Reporting

[Outline any additional project-specific safety management reporting instructions not covered in the Protocol and Project Safety Plan]. AE management for this project is applied using CRO_OP_VT0032 Adverse Events and Serious Adverse Events Management in Decentralized Clinical Trials. Details on AE, SAEs and Safety procedures are outlined in the Protocol, Project Safety Plan and additional information for DCT and RNPS teams in the table below: AE and SAE Reporting Instructions for DCT Site Operations and RNPS: [Modify per project or remove if not applicable] Procedures; Project-specific Instructions for DCT and RNPS. AEs and SAEs; [Include specific team instructions for DCT Site Operations and RNPS if the RNPS team is present during the remote visit at the participant’s home in term of any specific requirements or link to specific RNPS SOPs]. Safety Reporting; [the following should be considered]: - Responsibilities of DCT Site Operations team regarding submission to the Site of Investigator Alert Letters (IALs) as agreed with Lifecycle Safety or the Sponsor’s/ Vendor’s Safety unit. - Country-specific requirements for reporting of SAEs and IALs to the Site and/or Sponsor if these deviate from global procedure and/or local Work Instructions (WI).. [Modify per project] Project Specific reporting documents are in [insert link or location of this information]. Details on AE, SAE and Safety procedures are outlined in the Protocol, Project Safety Plan and in the table above. Monitoring activities will be conducted per the COP. Source documentation from home visits, will be stored in Study Hub and are available for monitoring and for site download should they choose. Monitors will complete their activities as defined in the COP.

Project Close Out and Study Hub Decommissioning

[Refer to the Sponsor contract to ensure all Sponsor-specific close out requirements are met. Collaborate with CL for any specific DCT activities to be added to the Site Close Out Checklist. Work with the DCT IM to begin the process of Study Hub close out, VIA submission for data extraction and archiving. Complete the DCT Lessons Learned activities] The DCTL will work with CL to ensure any DCT specific activities are added to the Site Close Out Visit Checklist prior to the beginning of Close Out visits. Monitors will complete Site Close Out process and will confirm that follow-up activities still open after the close out visit were resolved. The DCTL will also complete the DCT Lessons Learned activities, the DCT Financial Reconciliation in collaboration with PL and will work with the PVM/PMA on the financial reconciliation of DCT vendors and TPVs [last part can be removed if there are no DCT vendors or TPVs]. Study Hub Project Close Out for this project will be managed as per CS_WI_DCT0008, Study Hub Project Closure and Decommissioning, unless directed otherwise by the Sponsor. Project specific turnaround timelines for Study Hub project closure activities, including the timeline for data extract from QBOX are [insert project specific guidelines. For example: Study Hub decomissioning will start after Database Lock].

DCT Site Operations Scope

A summary of the DCT Site Operations execution scope is provided in the table below. The list of activities will depend on what DCT Site Operations activities are detailed in the SoW or Work Order. Appropriate references to governing processes such as SOPs will depend on the tasks indicated as part of the scope of services provided. [This section of the DCTOP is completed by the DCTL, in collaboration with the Site Operations Line Managers if required. The table has the DCT SCs and DCT SAs activities, some are only applicable for the DCT SC. Customize the table as applicable. Upon completion of the table below, delete the tasks listed as “No” in column “ Yes/No (if yes add comment)”].

DCT SCs/SAs Execution Scope:

| DCT SCs/SAs |  |  |  |
| --- | --- | --- | --- |
| Task | Yes/No (if yes add comment) |  | If yes, Time Expected to Complete Task |
| Patient Zero Exercise | Yes/No | If yes: add comment as to specifics including the number and types of activities expected to be completed; add any link to resources. Study Hub walk through based on the specific scope of a given project for the DCT SC. The activity will be performed [insert number of times] per project, led by [insert role], and will give a comprehensive overview of intricacies, project tasks, and specifications required by the DCT SC as well as the project. | Insert information about expected time to complete task per budget |
| Support of Site Initiation Visit [only applicable for the DCT SCs] | Yes/No | If yes: add comment as to specifics including the number of visits expected; process for scheduling and communication expectations with other team members such as Monitor/CL or PI); The DCT SC would attend the Site Initiation Visit as a participant. Most likely utilized for 100% DCTs. | Insert information about expected time to complete task per budget |
| Study Hub Orientation/Device Training for Sites | Yes/No | If yes: add comment as to specifics (such as when this is expected to happen; process for triggering; scheduling activities; link to tools- for example the presentation to complete). Study Hub orientation for site consists of the DCT SA providing a training call with the site to orient them to the Study Hub platform and expected project activities that involve the system. This will include how to use Study Hub on any device for the project. | Insert information about expected time to complete task per budget |
| Study Hub Drop In Sessions | Yes/No | If yes: add comment as to specifics (such as: when this is expected to happen; how many are expected; process for triggering; scheduling activities; link to tools- for example the presentation to complete). Study Hub drop-in sessions are an optional service for continuation of learning as it pertains to Study Hub. Examples are topics that may be significantly updated at Study Hub releases, or a topic/task of difficulty within Study Hub. | Insert information about expected time to complete task per budget |
| Protocol Amendment/ Significant System Trainings to the sites | Yes/No | If yes: add comment as to specifics in terms of scope (e.g., number of trainings that are expected; what these are for this project; link to tools- for example the presentation to complete). Specific training of the DCT SA to the sites team regarding significant system changes. This may be necessary if there is a significant protocol amendment that impacts the build of Study Hub. | Insert information about expected time to complete task per budget |
| Source Document Template Creation and Maintenance [only applicable for the DCT SCs] | Yes/No | If yes: add comment as to the specifics of the source document to be completed (example: Visit 2 source for telemedicine visit); define any project specific expectations for review or distribution; link to template storage location; Trigger when the PI would like the DCT SC to develop and maintain source documents for the portion of the visits that are remote. | Insert information about expected time to complete task per budget |
| Remote Support Visit of First Participant at Site | Yes/No | If yes: add comment as to specifics including enablement strategy and number expected per project; indentify any communication strategy with internal team members if applicable. A dedicated time for the DCT SC/SA to be on standby to support the first participant visit at sites outside of the expected protocol activities. Allowing this greater level of support will ensure a project expert DCT SC/SA to facilitate the first visit for the first participant (White Glove visit). | Insert information about expected time to complete task per budget |
| Participant Recruitment/Interest support [only applicable for the DCT SCs] | Yes/No | If yes, indicate the scope of the participant recruitment/interest visit/contact support including the countries/PIs to be supported. Include details such as the total number of contacts or participants to support. Include a link to any project instuctions or SOPs (e.g CRO_WI_VT0025 Virtual Trials Patient Recruitment and Consent); indicate if this process is expected to be reflected on the DOA Log. Facilitating participant inquiries to support their enrollment within the project | Insert information about expected time to complete task per budget |
| Support of Participant Consent [only applicable for the DCT SCs] | Yes/No | If yes: add comment about the number of participants expected to be consented or countries/sites to be supported; link to any process documents (include process for notification of participant to be consented or processes required, reference to the platform/system of e-consent to be used to consent participants, if applicable); include any related SOP documents (e.g. CRO_OP_VT0035 Obtaining Informed Consent in Decentralized Clinical Trials); include any links to trainings; indicate that this activity is expected to be documented on DOA Log. The DCT SC would support remote consent activities with the participant in accordance with ICH GCP guidelines. | Insert information about expected time to complete task per budget |
| Support of Participant Reconsent [only applicable for the DCT SCs] | Yes/No | If yes: add comment about the number of participants expected to be reconsented or sites to be supported (include any number of expected reconsents per SoW for the project - for example 2 reconsents per participant); link to any process documents (include process for notification of participantto be reconsented or processes required, reference to the platform/system of e-consent to be used to reconsent participants, if applicable); include any related SOP documents (e.g. CRO_OP_VT0035 Obtaining Informed Consent in Decentralized Clinical Trials; include any links to trainings; indicate that this activity is expected to be documented on DOA Log. The DCT SC would support remote re-consent activities with the participant in accordance with ICH GCP guidelines. | Insert information about expected time to complete task per budget |
| Support with the set-up, scheduling and execution of tele-visits | Yes/No | If yes, indicate the scope of participant visits for which the team is providing remote Site Coordination activities and in what capacity. Include a link to any specific processes or guidance documents. Include a reference to the activities expected for support for each visit (include examples such as transcription of project source, visual confirmation of RN visits). When participant visits to be scheduled by the DCT SC are in the scope of the project, visit scheduling and management will be done according to CRO_WI_VT0027, Patient Visit Scheduling and Visit Management. | Insert information about expected time to complete task per budget |
| Support in collection of participant data (vital signs, medical history, concomitant medication, etc.) [only applicable for the DCT SCs] | Yes/No | If yes, add comments regarding the specifics of what is expected to be supported by the remote coordinator team or link to any project instructions. Define the requirement as to how this data will be collected; indicate if this activity is expected to be reflected on the DOA Log. | Insert information about expected time to complete task per budget |
| Identification and Management of SAE/AE [only applicable for the DCT SCs] | Yes/No | If yes: add a comment regarding the total expected number of SAEs as indicated per the SoW for the DCT SC team to manage and process or management (SOPs or project instruction- e.g. CRO_OP_VT0032 Adverse Events and Serious Adverse Events Management in Decentralized Clinical Trials). Add link to any specific instructions provided by the Clinical Team. The DCT SC may be delegated to support the identification and management of SAEs at the site by the PI. | Insert information about expected time to complete task per budget |
| Collection of Medical Records [only applicable for the DCT SCs] | Yes/No | If yes: add comment on the scope (for example the sites that are expected for support and any assumptions around the number of requests per participant or site); add reference to any project specific instructions or SOPs. The DCT SC may require to collect medical records on behalf of the PI per protocol. This is most likely on 100% DCTs | Insert information about expected time to complete task per budget |
| Upload medical records and other documents in Study Hub, as needed, and send for signature via DocuSign, if applicable | Yes/No | If yes, define the project specific process for uploading the documents into Study Hub and expected timelines for completion (for example, documents should be complete, oriented correctly, and uploaded in the corresponding placeholder within 1 business day of the visit taking place). Add link to any project specific process. | Insert information about expected time to complete task per budget |
| Data Surveillance Activities (Participant Compliance Follow-up) | Yes/No | If yes: add comment as to specifics including the countries/sites supported- may include the expected non-compliance rate (might include link to the plan); define the requirement as to how activities will be documented; indicate if this activity is expected to be reflected on the DOA Log. The DCT SC may be asked to support follow up activities with project participants for key data points as part of a data surveillance plan associated with the project. | Insert information about expected time to complete task per budget |
| Case Report Form (CRF) / Data Entry [only applicable for the DCT SCs] | Yes/No | If yes, add comment including: Data entry is completed using the XXXXX system withink XXX days after the participant visit using the XXXXXX CRF completion guidelines (link to the eCRF guidelines ) for the following participant visits: XXXX Data queries are expected to be answered within XXX days of query issuance. Indicate if this process is expected to be reflected on the DOA Log. Insert any other project specific guidance as applicable or link to project tools/reference documents. Data entry from source documents or other data points pertaining to the participant may have to be entered into electronic data capture by the DCT SC. | Insert information about expected time to complete task per budget |
| ISF Management (on behalf the site) | Yes/No | If yes: add comment as to specifics including of applicable countries supported and any specific delivery expectations per Sponsor in terms of percent expected to be complete; timeline for uploading, etc. Indicate if this process is expected to be reflected on the DOA Log. Management of the ISF for a project according to CRO_WI_VT0028 Virtual Trial Investigator Site File Management. The DCT SC will be responsible for [modify per project budget and DOA: uploading necessary files to the ISF to assure timeliness of upload, completeness of file with a high level of quality. Standard routine maintenance, site close out and audit preparations to be performed]. | Insert information about expected time to complete task per budget |
| Project Logistics Support | Yes/No | If yes: add comment as to specifics (such as: when this is expected to happen; how many are expected; process for triggering; scheduling, activities - may link to process document). Also, may refer to applicable section of DCTOP (section listed below- Logistical Support Procedures”). The DCT SA may aid in scheduling, maintenance, and support of the participant during the lifecycle of the project in execution of remote visits or procedures such as triggering lab supplies to participant homes, or scheduling remote visits, or delivering the IP DTP. | Insert information about expected time to complete task per budget |
| Site Call Support (Transferred by Call Center) | Yes/No | If yes: add comment as to specifics in terms of scope (e.g., % of calls expected to be transferred, or # of calls transferred); DCT SA will be available to speak with the sites for specific project related questions as it pertains to Study Hub, or DCT scoped tasks | Insert information about expected time to complete task per budget |
| Site Support (direct contact by site through phone/Study Hub) | Yes/No | If yes: add comment as to specifics in terms of scope (e.g., assumptions as to number of calls expected; link to tools- for example scripts or training guides). DCT SA will be available to speak with the sites for specific project related questions as it pertains to Study Hub, or DCT scoped tasks. | Insert information about expected time to complete task per budget |
| OMNI Chat (Chat functionality in Study Hub) | Yes/No | If yes: add comment as to specifics (including hours/days of support) and link to tools/reference documents. Study Hub allows for participants registered on the platform to message with the DCT SC involved in the project through the OMNI Chat functionality. This can aid in AE reporting, as well as participant support and serve as another resource for questions regarding the DCT scoped tasks. PCFs will be created within Study Hub every time a participant is contacted, providing an audit trail within Study Hub. | Insert information about expected time to complete task per budget |
| Participant Call Support (Transfer by Call Center agents) [only applicable for the DCT SCs] | Yes/No | If yes, add comment regarding the specifics of what is expected to be supported by the team related to calls that are directly being held with participants (e.g., number, type of calls, etc). Add link to any project specific documents. DCT SC will be available to speak with the participants for specific project related questions as it pertains to Study Hub, or the DCT-scoped tasks either by direct communication or transfer from the IQVIA Call Center. PCFs will be created within Study Hub every time a participant is contacted, providing an audit trail within Study Hub. PCF will act as the source of information provided by the participant (e.g., AE, concomitant medication, any other relevant data, etc). | Insert information about expected time to complete task per budget |
| MV Support [only applicable for the DCT SCs] | Yes/No | If yes: Add a comment about the number of MVs expected for support (for example sites and countries and duration of visit) and communication expectations with the PI or other IQVIA team members. The project DCT SC may be asked to support MVs in relation to the remote activities that are part of the DCT scope | Insert information about expected time to complete task per budget |
| Investigator Project Status Meeting [only applicable for the DCT SCs] | Yes/No | If yes: add comment about any project specific guidelines around communication regarding project activities on behalf of the PI by the DCT team member; include reference to any SOPs or project instructions or link to tools available. The DCT SC will provide regular updates to the PI about the status of their work, participant updates, or any challenges they may be facing. | Insert information about expected time to complete task per budget |
| Closeout Visit Support [only applicable for the DCT SCs] | Yes/No | If yes, indicate the scope of the closeout activities to be supported including the countries and PIs that are being supported. Include a reference to any SOPs or project instructions to be followed. The DCT SC would attend the Closeout Visit as a participant. This is most likely utilized for 100% DCTs. | Insert information about expected time to complete task per budget |
| Risk Mitigation / Just In Time Enablement Strategy | Yes/No | If yes: define the enablement of the activity (for example the request will be provided XXX weeks ahead of the need by written PI request); link to tools or reference guides | Insert information about expected time to complete task per budget |
| Audit/Inspection Support [only applicable for the DCT SCs] | Yes/No | If yes: add comment about the number of audits/inspections and for which sites/countries. Define any specfic communication workflows around audit support any any related trainings/SOPs or reference documents; A DCT SC may be requested or needed to participate in a site audit or inspection by regulatory authorities. | Insert information about expected time to complete task per budget |

DCT Team Resources and Assignment to Sites

Allocation of project team resources will be conducted according to CS_WI_PL0060, Project Resource Management. The transition of the DCTL and DTA for the project will be managed according to CS_WI_PL0024, Project-Specific Training and Team Member Transition and as defined in the IPMP.

The following tasks are within scope to be delegated to the [Select DCT SCs or DCT SAs] and are defined as needing to be reflected on the DOA Log.

[Insert the activities delegated to the DCT SCs/SAs per the DOA]

DCT [Select: SCs/SAs] will be assigned to sites following the project specific process: [Insert project specific process here- include any expected timelines and requirements for DCT SC/SA assignments such as speaking language needed, capabilities, local presence, previous experience, etc. Indicate any project specific expectation in terms of percentages of sites supported, and how those are identified for support].

Project Team Training and System Accesses

11.1 Internal Team Training Project specific training would be defined by the following [Indicate SOP numbers and/or project instructions. E.g., CS_WI_PL0024, CRO_WI_VT0013] and are documented in the [indicate the system to record the housing of the training. For example: eTraining system and IQVIA DCT LMS]. Additional resources for team training are located: [include link to any project specific training resources] Training for project team members of DCT will be delivered by role and before performing any project related task and participant enrollment in the DCT model. eTraining profile set-up instructions for general and project-specific training, if applicable, are: DCT eTraining Profile: Under Registered Sponsor: Select Sponsor: DECENTRALIZED_CLINICAL_TRIALS Select Role: [choose your role] Select Region or Country: [choose your relevant region or country]. Project specific eTraining Set Up: Select Sponsor: [insert Sponsor] Select Project Code: [insert Sponsor] Select Role: [choose your role]. [If there is Sponsor specific eTraining add the set-up instructions]. 11.2 System Acesses for Site Operations Team Systems relevant to the DCT Site Operations Team are as below along with the relevant process for access and maintenance: System (Include Name); DCT SC or DCT SA need access? (Indicate role); Login Link; Process for Requesting Access / Specific Training Requirements. eDC. IRT. Study Hub; Follow CS_WI_DCT0005, Study Hub User Account Management. The DCTL/DTA grants the DCT [Select: SA/SC] access to the DCT LMS platform. The DCT [Select: SA/SC] completes the required trainings. The DCTL works with ARMG to ensure the DCT [Select: SA/SC] are provided access to Study Hub.. Lab. eISF. Call Center Platform; DCT [Select: SA/SC] manages this with their Line Managers. eCOA. e-Consent. 11.3 Study Hub Training and Supporting Documentation for Sites [Add project specific details not covered in the eSOP. For example: the DCT LMS mandatory trainings for site staff] Site Study Hub Onboarding and training will be conducted as described in CRO_WI _VT0023, Study Hub Site Onboarding. The DCTLs will develop the Study Hub site onboarding material.

Project Documents and File Set Up

All regulatory documents will be uploaded to the eTMF, including the DCT documents part of the Essential Document Package. The Local RSU Representative /delegate will upload the essential documents package to the eTMF after the package is complete per CS_WI_RSU0021, Essential Documents Pack. [Modify per Project or delete if DCTL is not maintaining the eTMF] Ongoing eTMF maintenance will be under the DCTL or delegate responsibility, who will be granted with the appropriate role to upload/index documents into the system. The DCTL will follow the CS_WI_RM0284, General and Trial Master File (TMF)-Specific Document Quality - Good Documentation Practices, with special focus on confidentiality and data privacy guidelines. The following documents will be archived in eTMF by the DCTL or delegate: [List all the documents that apply. Modify per project as needed] Document Type; eTMF Placeholder used for archival; When. Study Hub Configuration Plan; Start-Up. SCEUAT Report. DCTOP; After each new version. DPIA Confirmation Form; After each new version. DCT Team Curriculum Vitae (CV); After DOA signature. DCT Team Training logs. DCT DOAs; After each new version [DCTL to complete per project specific process]. Study Hub Onboarding Slides; After each new version. Study Hub Material for sites. DCT SIV Slide Decks. Key Team Member Transition Form; After transition form signature for DCTL and DTA. DCT Relevant Emails; As needed. Study Hub Data Transfer Completion - Sponsor Acknowledgment; Close-Out. Study Hub Data Transfer Completion - Investigator Acknowledgment; Close-Out for each site. TPV CO [remove if not applicable]; After each new CO. TPV CV and Nursing License [remove if not applicable]; After DOA signature. TPV Training Logs [remove if not applicable]; After DOA signature. TPV Manuals [remove if not applicable]; After each new version. Vendor Management Plan [remove if not applicable]; After each new version. PIs participating in the project will maintain their project files in the ISF. Specific instructions for filling DCT/RNPS documents into the ISF and eTMF are as follows: - RN approval documentation - After a qualified RN is identified and trained, the following RN documentation will be send to the PI via email for review and approval: - CV - Nursing License - Project specific training log - GCP and International Air Transport Association (IATA) certificate - Once approved, the [Select: RNPS Lead, RNPS Regional Specialist, DCTL] or delegate will send the above documentation to the Clinical Trial Assistant (CTA) to be filled in the eTMF [insert Placeholder where it will be archived]. - The CTA will send the documentation to the Monitors to ensure the PI archive them in the ISF. - DCT [Select: SC/SA] approval documentation - After a qualified DCT [Select: SC/SA] is identified and assigned to a site, the following documentation will be sent to the PI for review and approval via email by the DCTL: - CV - GCP training certificate - Project specific training log - The DCTL is reponsible for filling the DCT [Select: SC/SA] documentation in the eTMF [insert Placeholder where it will be archived]. If desired. the PI can raise and resolve any concerns about DCT [Select: SC/SA] qualification with the DCTL and RN qualification with the RNPS Lead or RNPS Regional Specialist. - RNs and DCT [Select: SC/SA] signed DOA - Once the DCT and RNPS project team is approved in writing by the PI, the DCT [Select: SC/SA] will route the DOA for signature. - Once the DOA is signed by all team members, the DCT team (DCTL or delegate) will send them to the CTAs for eTMF filling. - The CTA will send the DOA to the Monitors to ensure the PI archive the DOA in the ISF.

Project Communication and Escalation

Question and Answer (Q&A) Log Project Q&A Log is located here: [Insert link here] DCT Project Communication and Escalation Management Any DCT relevant communication or issue that required escalation will follow the below path. For Study Hub Technical Issues escalation refer to Section 6.1: [Modify per project as needed] Project Status Reporting [Provide any DCT Site Operations specific standard reporting details, if applicable, including type of information reviewed, frequency of reporting, and type of status report available. Link to project specific dashboards.] Logistical Support Procedures Project-specific details supporting logistics for the execution of the project are provided in the [insert information- may be Protocol, IB, DCT Site Operations Playbook or another document] and are summarized below: [Add project specific language regarding the scope of activity (for example, Iab kit shipment triggering for visits 2, 4, 8). Example procedures are below but may not be representative for the project.]. Procedures; Who?; Project-specific Instructions. Participant and Site Staff Onboarding; [Include visits that DCT Site Operations are expected to support and any relevant instructions (or link to process document)]. Visit confirmation and scheduling support; [Include visits that DCT Site Operations are expected to support and any relevant instructions (or link to process document)]. Shipment of lab kits to participant home; [Include visits that DCT Site Operations are expected to support and any relevant instructions (or link to process document)]. Shipment of IP to participant home; [Include visits that DCT Site Operations are expected to support and any relevant instructions (or link to process document)]. Other; [Add project-specific details if required].

Participant and Site Contacts

Communication Platforms [Modify per Project] The PI has several options through which they can communicate with the DCT Project Team, including but not limited to: Study Hub in-app messaging, email, phone, or tele-visit. PIs will be able to communicate with the RNs through tele-visits during scheduled visits when the RN is in the participant’s home or ad hoc tele-visits arranged separately by the DCT SA. The PI can also contact the RNs directly via phone or email at any time during the project. Communication platforms for this project to sites and participants are expected as documented in the below table: Type; Platform; Comments (include link to reference document if applicable); How the communications are documented?. Chat; Study Hub- OMNI Chat; Study Hub- OMNI Chat. Telephone; Twilio; PCF. Telephone; IQVIA issued device; PCF. SMS Text; IQVIA issued device; PCF. Any other platform for communication requires approval by the DCTL and/or Line Management ahead of use. The specific Study Hub support numbers for sites and participants are listed in the table below: Use the Countrywise Site & Patient Numbers for reference. [Complete the table below with the Project specific information] Project Geography Name; Participant Phone Number; Site Phone Number. PI project escalations will be addressed in the following manner: - PIs will document and share with their Monitor the issue and address any immediate participant concerns via a follow-up tele-visit. - Monitors will advance the issue to the CL and create an action item in CTMS and follow up until completion. - Should an escalation include RNPS , the DCTL will notify the RNPS Lead and the PL/CL/PVM for resolution. Depending on the situation, the Sponsor will be informed to formulate and/or approve actions to be taken. Documenting General and Participant Contacts in Study Hub Study Hub PCFs are intended to be the primary documentation of participant and site contacts for this project. Project specific instructions for completion of PCFs including naming conventions for Subject Line are documented below [or provide link to reference document]: Communication Scripts All participant facing material must be IRB/EC approved prior to use when acting on behalf of the PI. Scripts help to assure that participants are receiving approved messaging for consistency and clarity and to confirm that our communication protects the rights, health, and safety of participants in the project. Project-specific scripts are in place for the following: Communication Method; Link to Standard Script location. Text. Other. Other. Text and Call Communication Guidelines To assure positive participant communication, this project will adhere to CS_WI_SPN0019, Call Center Initiative Management TCPA Compliance. All inbound communications to the IQVIA Contact Center will be handled as described in CS_WI_CC0258, IQVIA Contact Centre Virtual Trials Processes [Add Project Specific text and call communication guidelines if applicable]. DCT Site Operations Team Scheduling DCT Site Operations support is expected during the following hours: [Insert project specific information for the specific systems that are supported and the times in Eastern Time and each of the roles expected to provide support] - During Normal Business Hours: The participant can contact their assigned remote project team via Study Hub chat or the local support number provided. - Outside of Normal Business Hours: An IQVIA Call Center will receive participant calls. A PCF will be generated and circulated to an assigned remote project team member. If the participant indicates a safety concern, the remote project team member will contact the PI for further assessment. - Emergencies: Participants will be instructed to call their local emergency number in case of emergencies. Teamwork schedules are available at this link: [Insert link] Work assignments are completed [insert cadence, e.g., weekly, monthly, each Thursday] and are communicated [insert how. If applicable, add information regarding weekend schedule coverage process]. Requests for changes in shifts can be completed using the following process [insert process]. If DCT Site Operations team members are unable to make a shift due to a foreseen circumstance, 24 hours’ notice is requested. [Remove if the DCT SC/DCT SA is not expected to interact with TPVs or other IQVIA Department] DCT Site Operations Interactions with TPVs and IQVIA Departments The DCT Site Operations team could interact with the following internal departments or TPVs as described below: IQVIA Department / TPV Type; Name of Department e.g., IQVIA, Sponsor, TPV; Project-Specific Details Including type of communication, frequency or link to reference document. Site Management. Data Management. Central Monitoring. RNPS. Sponsor. eTMF platform. eDC platform. Participant Recruitment. Call Center. Other. Participant Lost to Follow Up Plan [Modify per project] If delegated to follow up with participants by the PI, and in scope as defined by the Sponsor, DCT Site Operations team members will follow up with participants to assess lost to follow up. Participants will be deemed lost to follow up after [insert number of contacts] contacts [define type of contact and how many- e.g., 3 phone call attempts with voicemail left and 2 text attempts] as per [Select: protocol/COP].

- APPENDIX A: Additional Project Resources

| Team Project Materials/Links [This is not a complete list, add/update for any additional materials used] |  |  |
| --- | --- | --- |
| Weekend Coverage Schedule | [Insert link] |  |
| Site Assignment Tracker | [Insert link] |  |
| Site Contact Information | [Insert link] |  |
| Project SharePoint Site | [Insert link] |  |
| VIA Ticket Tracker | [Insert link] |  |
| Patient Flows | [Insert link] |  |
| Data Flows | [Insert link] |  |
| Team Project Contact List (Vendors, Sponsor contacts, etc.) | [Insert link] |  |
| DCT Team Reference Materials | [Insert link] |  |
| DCT Site Operations Playbook | TEMPLATE LINK [Insert link to the final document upon finalization] |  |
| RNPS Operational Plan | [Insert link] |  |
| Study Hub User Guides (All Roles) | SharePoint Link to User Guides [Insert supporting documents with tips for success in Study Hub if applicable] |  |

| Out Of Office Message Project Specific Example for DCT [select: SCs/SAs] |  |  |  |
| --- | --- | --- | --- |
| Hello, I will be out of office on <DATE> with limited access to emails. Please contact <WEEKEND COVERAGE NAME> with any urgent issues. <WEEKEND COVERAGE EMAIL> <WEEKEND COVERAGE Phone #> For Study Hub issues that immediate assistance, please call: Site Support Line Only: <Add country support numbers> Participant Support Line Only: <Add country support numbers> |  |  |  |

Note: Sponsors and protocol numbers should not be listed in external OOO messages.