|  | IQVIATM Work Instruction Producing a Clinical Study Protocol |
| --- | --- |
|  | Document Number and Revision: CS_WI_MW006 Revision 11 |
| Document Owner: Corinne Willmott | Author(s): Corinne Willmott, Anne Thomson |

# PURPOSE

To describe the steps involved in preparing a clinical study protocol.

# SCOPE

This work instruction (WI) applies to projects in which a clinical study protocol is prepared by IQVIA Global Medical Writing, either as a stand-alone service or in conjunction with other IQVIA service groups.

This WI does not cover the process for preparing subsequent protocol amendments. Refer to CS_WI_MW0236, Producing a Clinical Study Protocol Amendment.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Project Leader (PL) | 6.1, 6.2, 6.3, 6.4, 6.6, 6.7, 6.8 |
| Lead Medical Writer (Lead MW) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7, 6.8 |
| Therapeutic Medical Advisor (TMA) | 6.2, 6.3, 6.4, 6.6 |
| Statistical Team Lead (STL)/Experienced Biostatistician (EB) | 6.2, 6.3, 6.4, 6.6 |
| Pharmacokinetic (PK)/Pharmacodynamic (PD) Scientist | 6.2, 6.3, 6.4, 6.6 |
| Medical Writing QC Reviewer | 6.4, 6.7 |
| Senior Medical Writing (MW) Reviewer | 6.4 |
| Lead Publisher | 6.7 |

## Notes:

  - The PL responsibilities may be undertaken by a member of the Project Leadership group, a Clinical Project Manager from the Early Clinical Development group or IQVIA Biotech, or, in the case of a stand-alone project, by the Lead MW, their Line Manager, or other functional lead.

  - Business units within IQVIA may use different terminology for the roles described above (e.g., for IQVIA Biotech projects, responsibilities of the STL/EB may be undertaken by the Statistical Design Expert).

Page 1 of 13

Copyright © 2000, 2004, 2007, 2013-2016, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

# DEFINITIONS

European Union Clinical Trials Regulation (EU-CTR) EU No 536/2014: impacting clinical trials conducted in the EU and is a replacement for the Clinical Trial Directive 2001/20/EC.

Protocol Concept/Synopsis: Document in editable format detailing key features of the study, including title, objectives, endpoints, description of study design and rationale, disease diagnostic criteria, other inclusion and exclusion criteria, treatments to be administered, prior and concomitant medication rules, a schedule of assessments, and an outline of the planned statistical analyses. May also be referred to as Protocol Outline or Study Design Concept. This document is independent of the full protocol and must be created before the full protocol is drafted.

Statistical Team Lead (STL)/Experienced Biostatistician (EB): Someone who is able to apply specific statistical or therapeutic knowledge and capable of managing challenging discussions with the Customer (refer to CS_WI_BS006, Statistical Review and Input to a Clinical Trial Protocol or, for IQVIA Biotech projects, refer to SOPCR007, Development of Statistical Section of the Protocol).

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

## Preliminary Work and Project Oversight

For most projects, protocol preparation is a cross-functional collaborative task, so it is vital to identify all contributors and reviewers, not only the Lead MW, as early as possible after Award and before drafting of protocol begins.

Note: The protocol delivery timelines are dependent upon the date of reciept of the final, approved Protocol Concept/Synopsis by the Lead MW. All stakeholders should be made aware that the timelines may need to be adjusted based on the actual receipt date.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | PL | - Ensures that the Customer has made a written commitment to award the work and that appropriate budget for all contributing functions is confirmed before work starts. - Ensures that all necessary contributors and reviewers have been identified and advised of their role (may be done after Award but before drafting of protocol begins). - Consults the Lead MW on protocol delivery timelines before communicating them to the IQVIA project team members and Customer or agreeing to timelines requested by Customer. | At Award, before drafting of protocol begins |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Ensures that necessary actions are taken to create a final Protocol Concept/Synopsis approved by all key stakeholders, including completion of CS_FM_MW0231, Protocol Concept/Synopsis Check List (see Section 6.2). - Acts as main contact/liaison between the Customer and the IQVIA project team, as appropriate. - Communicates the protocol delivery timelines (draft and final versions) and milestones to the IQVIA project team members and the Customer. - Obtains the necessary study documents (e.g., final Protocol Concept/Synopsis, Investigator's Brochure) from the Customer when needed. |  |
| 6.1.2 | Lead MW | - Initiates set up of and/or requests access to appropriate filing areas and maintains documentation in accordance with CS_WI_MW0233, Management and Filing of Medical Writing Documentation. - Requests confirmation of the agreed scope and assigned budget from the PL. - Checks with PL if Data Informed Protocol Assessment (DIPA) review has been conducted or is planned. If review is already conducted, requests a copy of the feedback for reference. If review is planned, requests for this to be done before protocol writing begins, to avoid rework. - Determines the Customer's requirements for template, format, and content. - Obtains the Protocol Concept/Synopsis provided by the Customer, or developed internally, from the PL. Assists in completing CS_FM_MW0231 (see Section 6.2). - Checks for regulatory guidelines specific to the indication or intended patient population, as agreed with the Customer. - If the study will be conducted under the EU-CTR, asks Customer if the European Medicines Agency template for “Recruitment and Informed Consent Procedure” will be used. If not, ensures required information per the EU-CTR guidance is included during protocol drafting (see Section 6.3), as applicable. - Receives confirmed list of contributors and protocol reviewers, as applicable, from the PL. This can include IQVIA staff, Customer staff, and/or third parties, including investigators. - Discusses and agrees with Customer the format in which review comments will be returned to the Lead MW. The preference is for one set of consolidated and adjudicated | Upon assignment to project |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | comments. Any deviation from this may incur additional costs and the PL must be informed. - Schedules review of the protocol by relevant internal team members, including a QC Reviewer and Senior MW Reviewer. - Provides input on timelines for delivery of each version. - Requests resource assignment from the Document Publishing group for publishing of the protocol per the agreed timelines, if IQVIA is contracted for this work. |  |

## Protocol Concept/Synopsis Development and/or Review

It is important that a stable, robust, and complete Protocol Concept/Synopsis acceptable to key stakeholders is in place before protocol writing begins.

Note: When Protocol Concept/Synopsis development is contracted to IQVIA, refer to AS_WI_SDD0002, Study Design and Protocol Synopsis Development.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | PL | - Coordinates review of Protocol Concept/Synopsis by TMA, STL/EB, Lead MW, and/or PK/PD scientist, as applicable. - Completes CS_FM_MW0231, incorporating input from reviewers as appropriate. - Communicates any necessary follow-up actions to the Customer. | Protocol Concept/Synopsis is provided by the Customer |
| 6.2.2 | TMA | - Reviews the Protocol Concept/Synopsis and provides input to complete CS_FM_MW0231. - Verifies that the study design and methods are clinically appropriate. | Following receipt of Customer’s proposed Protocol Concept/Synopsis from the PL |
| 6.2.3 | STL/EB | - Reviews the Protocol Concept/Synopsis and provides input to complete CS_FM_MW0231. - Verifies that the study design and proposed statistical methods are appropriate | Following receipt of Customer’s proposed Protocol Concept/Synopsis from the PL |
| 6.2.4 | PK/PD Scientist | - Reviews the Protocol Concept/Synopsis and provides input to complete CS_FM_MW0231 (if applicable). - Verifies that the study design and methods are appropriate to support PK and/or PD objectives (if applicable). | Following receipt of Customer’s proposed Protocol Concept/Synopsis from the PL |
| 6.2.5 | Lead MW | - Reviews the Protocol Concept/Synopsis when requested by the PL according to the items defined in the check list (CS_FM_MW0231), with focus on verifying that content is sufficient to support preparation of a high quality first draft protocol. | Following receipt of Customer’s proposed Protocol Concept/Synopsis from the PL |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Assists PL in completing CS_FM_MW0231, as needed. |  |
| 6.2.6 | PL | If the Protocol Concept/Synopsis is deemed unacceptable for writing the protocol per CS_FM_MW0231: - Communicates findings to the Customer and requests updates to address the deficiencies identified in the Protocol Concept/Synopsis. - Ensures the Customer has approved budget for IQVIA (all contributing functions as applicable) to support revision/finalization of the Protocol Concept/Synopsis if the Customer cannot provide a revised version. - Ensures that appropriate resources are secured to support the finalization of the Protocol Concept/Synopsis document, if required. - Makes Customer and IQVIA team aware that protocol delivery timelines will need to be adjusted based on the actual date of receipt/approval of the final Protocol Concept/Synopsis. - Keeps the team informed of the progress of Protocol Concept/Synopsis finalization, considering the potential impact of delays on resourcing and timelines for the full protocol. | Following review of Customer’s proposed Protocol Concept/Synopsis |
| 6.2.7 | PL | Distributes finalized and approved Protocol Concept/Synopsis to the IQVIA project team and/or Customer, as applicable. | Protocol Concept/Synopsis is finalized/approved |

## Preparing the Draft Protocol

Work can start when the Lead MW receives the final Customer-approved Protocol Concept/Synopsis, budget is approved, essential project team members are in place, and the protocol template has been agreed.

The protocol is created based on the International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (GCP) (R2): Consolidated Guideline, Section 6, and any other applicable regulatory requirements, as well as information provided by the Customer.

Note: For studies conducted under the EU-CTR, the inclusion of specific details in compliance with this regulation should be discussed / agreed with the Customer, as applicable. EU-CTR guidance is included within the IQVIA Global Medical Writing protocol templates.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | Lead MW | - Drafts the protocol using the agreed template, relevant regulatory guidelines, and other information provided. - Provides the protocol template and/or Customer style requirements (if any), and communicates required timelines for contributions, to others who are assigned to write sections of the protocol. - Requests documents needed for the protocol appendices from the PL or the Customer, as appropriate. Some documents may be subject to copyright protection, so the Lead MW must check with the PL before including these in the protocol. | Upon receipt of Customer- approved Final Protocol Concept/Synopsis |
| 6.3.2 | PL | Contributes to protocol development, as required. | Throughout protocol development |
| 6.3.3 | TMA | Acts as main contributor to the first draft protocol for all medical aspects and provides medical input, as required. | Throughout protocol development |
| 6.3.4 | STL/EB | - Prepares agreed statistical sections of the protocol using the template, writing conventions, and style guide provided by the Lead MW, and provides to the Lead MW. - Assumes responsibility for the appropriate formatting, internal Biostatistics review, and QC of the statistical sections. | During development of first draft protocol |
| 6.3.5 | PK/PD Scientist | - Prepares each version of the PK and/or PD sections (or reviews, as applicable) per agreed scope and budget, using template, writing conventions, and style guide provided by the Lead MW. Unless otherwise specified by the Customer, PK/PD Scientist will utilize PI_WI_PK0205, Standardization of Pharmacokinetic and Pharmacodynamic Symbols. - Assumes responsibility for the appropriate formatting, internal review, and QC of the PK and/or PD sections. Note: Internal review and QC of the PK and/or PD sections may occur in parallel with IQVIA internal review of the proposed Draft 1 protocol. | During development of first draft protocol |

## IQVIA Internal Review of the Proposed Draft 1 Protocol

The PL is responsible for confirming which IQVIA internal reviewers should be included and communicating this to the Lead MW (see Section 6.1.1). Quality control and Senior MW reviews are always needed and must be performed before the Draft 1 protocol is sent to the Customer. Other relevant internal reviews should also be performed before issuing the Draft 1 protocol to the

Customer, unless a higher level agreement (e.g., Partnership Manual) allows for parallel review. Internal reviews may include:

- STL/EB: Refer to CS_WI_BS006 or, for IQVIA Biotech projects, SOPCR007.

- TMA: Provides any review comments on the protocol from a medical perspective.

- PK/PD Scientist: Refer to PI_WI_PK0210, Preparation and Review of CP-generated Documents.

- Other IQVIA project team members (as confirmed by the PL), including the PL, may review all or part of the protocol as required.

Note: For IQVIA Biotech projects, reviewers may follow different guidance and/or SOPs, as appropriate for their function.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | Lead MW | Distributes the proposed Draft 1 protocol for IQVIA internal team review, including QC and Senior MW review. | Before issue of Draft 1 protocol to Customer |
| 6.4.2 | Medical Writing QC Reviewer | - Performs QC review in accordance with CS_OP_MW005, Quality Control (QC) Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs form CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables, via electronic approval workflow or wet-ink signature, to confirm completion of their review. | Upon receipt of proposed Draft 1 protocol |
| 6.4.3 | Senior MW Reviewer | - Performs review in accordance with CS_WI_MW0221, Senior Medical Writing Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, to confirm completion of their review. | Upon receipt of proposed Draft 1 protocol |
| 6.4.4 | PL, TMA, STL/EB, PK/PD Scientist, other reviewers (as applicable) | - Reviews the proposed Draft 1 protocol in accordance with the appropriate WI (if applicable – see list at the start of this section). - Provides written findings and comments to the Lead MW, preferably as Microsoft Word tracked changes (annotated protocol). - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, when requested by the Lead MW, to confirm completion of their review. | Upon receipt of proposed Draft 1 protocol |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.5 | Lead MW | - Makes a copy of the comments from each reviewer to create the Medical Writer Response document(s). - Reviews each comment. - Discusses any complex or major findings with the appropriate reviewer. The Lead MW must not make any changes to the PK sections requested during internal review by other reviewers without consultation with the PK/PD Scientist. Similarly, changes to the design requested internally must also be reviewed with the STL/EB and PK/PD Scientist to assess impact on the planned statistical and PK analysis and data interpretation. Any changes to the study design proposed by the internal reviewers should be discussed with the Customer before implementation. - Discusses and resolves conflicting comments. - Makes appropriate revisions to the master copy of the protocol and finalizes the Draft 1 protocol for issue to the Customer. - Annotates the Medical Writer Response document(s) with a response for any review comment that is not incorporated, or that is addressed in a different way to the reviewer’s suggestion. - Requests internal reviewers to sign form CS_FM_MW007 via electronic approval workflow or wet-ink signature. This form should be completed for each review cycle. It is not necessary for all internal reviewers to sign the same copy of the form. - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, to document that all comments have been addressed, as appropriate. | Upon receipt of internal review comments |

## Sending the Draft Protocol for Customer Review

Note: If requested by the Customer, the PL may assume responsibility for delivery of the draft protocol and other communication, as appropriate.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | Lead MW | - Verifies that all contracted internal reviews have been performed and comments addressed, as described in Section 6.4. - Sends the Draft 1 protocol to the Customer by an agreed/secured method (refer to CS_WI_MW0201, Sending Medical Writing Deliverables to Customers Securely). | After Draft 1 protocol has been prepared and internal review process has been completed |
|  |  | - Sends a covering e-mail to the Customer detailing: |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - The status of the document. - Any questions or issues requiring clarification. - The date by which comments are expected. - Request for comments to be returned to the Lead MW as one set of consolidated and adjudicated comments, unless otherwise agreed. Note: In exceptional circumstances, if requested by the Customer, an unreviewed draft protocol may be sent if the PL, key IQVIA project team members, and line manager of Lead MW agree; however, this must be clearly identified as an unreviewed draft. This change from usual Medical Writing process should be documented in a Global Medical Writing File Note (CS_FM_MW0224). Before sending the protocol, the Lead MW must advise the Customer that the protocol has not been reviewed and that the content may change after internal reviews, including QC, are completed. |  |
| 6.5.2 | Lead MW | Forwards the above communication to other IQVIA project team members, as appropriate (refer to CS_WI_MW0201), for information purposes. | Following issue of the Draft 1 protocol to the Customer |

## Handling Customer Comments

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | Lead MW | - Reviews the comments and, if applicable, shares the comments with other IQVIA project team members (e.g., TMA, STL/EB, and/or PK/PD scientist) for resolution of relevant comments. - Plans, depending on the scope and nature of the comments, and the contractual requirements, a comments resolution meeting (CRM) with the Customer and appropriate IQVIA team members to discuss and define exactly what changes are required and to agree on a turnaround time. - Documents the outcome of the discussions from the CRM, as appropriate. For further details, refer to Section 6.3 of CS_OP_MW0203, Preparation of Medical Writing Deliverables. - Highlights any conflicting or unclear comments to the Customer for clarification, consulting first with other IQVIA project team members as appropriate. This may be handled during the CRM, if held. | Upon receipt of Customer review comments |
| 6.6.2 | TMA, STL/EB, PK/PD | Attends the CRM to discuss comments and their resolution with the Lead MW and Customer, if requested by the Lead MW. | Following review of Customer review comments |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  | Scientist, PL, other team members |  |  |
| 6.6.3 | Lead MW | - Updates the protocol, ensuring that every comment is addressed appropriately. The Lead MW must not make any changes to the PK sections requested by the Customer without consultation with the PK/PD Scientist. Similarly, any changes to the design must also be reviewed with the STL/EB and PK/PD Scientist to assess impact on the planned statistical and PK analysis and data interpretation. - Provides an explanation to the Customer, as appropriate, regarding any comment(s) for which the requested change is not incorporated or is addressed in a different way than the Customer suggested. The Lead MW must note the reason on a copy of the Customer’s comments (Medical Writer Response document). | Following review of Customer review comments and CRM (if held) |
| 6.6.4 | Lead MW | Forwards the revised protocol to other IQVIA project team members (e.g., TMA, STL/EB, PK/PD Scientist), if applicable, to review the changes prior to any subsequent delivery to the Customer. Changes requiring review may include: - Changes of a statistical nature or to the statistical section - must be reviewed by the STL/EB. - Changes relating to PK/PD sections and/or study design changes which may affect the PK/PD results - must be reviewed by the PK/PD scientist. | After incorporation of Customer review comments |

Note: Depending on the number of review cycles specified in the agreed scope or as confirmed by the PL, the processes described in Steps 6.5.1, 6.5.2, and 6.6.1 to 6.6.3 above may be repeated as applicable for additional drafts of the protocol.

Sending the Proposed Final Protocol to the Customer

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.1 | PL | Supports the Lead MW in ensuring that sufficient time is allowed for protocol update and QC review after receipt of final Customer comments. | During protocol development and following completion of all review cycles |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.2 | Medical Writing QC Reviewer | Performs QC review of the proposed final version of the protocol in accordance with CS_OP_MW005. | Upon receipt of proposed final deliverable from the Lead MW |
| 6.7.3 | Lead MW | - Ensures that the proposed final version has undergone QC review in accordance with CS_OP_MW005. Sufficient time must be allowed after receipt of final Customer comments to allow for updates and to permit the subsequent QC review to be effective. - Sends the proposed final protocol to the Customer (referring to CS_WI_MW0201). This can be done directly or via the PL. - Asks the Customer to confirm in writing that the protocol is final and that IQVIA Medical Writing activities are complete. | Following completion of all review cycles, resolution of all review comments, and necessary updates made to protocol |
| 6.7.4 | Lead Publisher | - If included in the agreed scope and budget, publishes the protocol in line with Customer requirements/expectations according to CS_WI_RA0292, Publishing - Producing Clinical and Submission Publishing Deliverables - Sends final published deliverable (if applicable) to the Customer securely in accordance with CS_WI_RA0292. | Following Customer confirmation that protocol content is final and ready for publishing |
| 6.7.5 | PL | Ensures that the final protocol is signed by the Customer representative and others, as needed. | Following protocol content approval by Customer |

Filing

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.8.1 | Lead MW | Files documentation relating to protocol preparation in accordance with CS_WI_MW0233, Management and Filing of Medical Writing Documentation. | Throughout development of the document |
| 6.8.2 | PL | If required for TMF filing, obtains a copy of the Customer-approved final protocol from the Customer and files in the TMF. Note: This version may differ from the proposed final version issued to the Customer by the Lead MW. | When Customer has confirmed that the protocol has been approved |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| CS_FM_MW0231 | Protocol Concept/Synopsis Check List |
| AS_WI_SDD0002 | Study Design and Protocol Synopsis Development |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| CS_OP_MW005 | Quality Control (QC) Review of Medical Writing Deliverables |
| CS_WI_BS006 | Statistical Review and Input to a Clinical Trial Protocol |
| PI_WI_PK0205 | Standardization of Pharmacokinetic and Pharmacodynamic Symbols |
| PI_WI_PK0210 | Preparation and Review of CP-generated Documents |
| CS_FM_MW007 | Internal Signature Page for Medical Writing Deliverables |
| CS_WI_MW0221 | Senior Medical Writing Review of Medical Writing Deliverables |
| CS_WI_MW0201 | Sending Medical Writing Deliverables to Customers Securely |
| CS_FM_MW0224 | Global Medical Writing File Note |
| CS_WI_MW0233 | Management and Filing of Medical Writing Documentation |
| CS_OP_MW0203 | Preparation of Medical Writing Deliverables |
| CS_WI_MW0236 | Producing a Clinical Study Protocol Amendment |
| CS_WI_RA0292 | Publishing - Producing Clinical and Submission Publishing Deliverables |
| SOPCR007 | Development of Statistical Section of the Protocol |
| External References |  |
| http://elvis.quintiles.com/ livelink/llisapi.dll?func=ll &objId=82340085&objAc tion=browse&viewType= 1 | IQVIA Global Medical Writing protocol templates (containing specifics relating to EU-CTR guidance) |
| ICH-GCP: E6 (R2) | International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (R2): Consolidated Guideline, Section 6 |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| CS_WI_MW006 | Producing a Clinical Study Protocol | 10 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| All details relating to the Patient | 2.0, 3.0, 4.0, 6.1.2, 6.4, | PSR process is no longer a |
| Safety Review (PSR) process for protocols and associated supporting documentation have | 6.5, 6.6.4, 6.7.1, 7.0 | requirement for new protocols per senior management decision |
| been removed |  |  |
| Added references to EU-CTR and the IQVIA Global Medical Writing protocol templates (which include specifics relating to this) | 4.0, 6.1.2, 6.3, 7.0 | To ensure that required information per EU-CTR guidance is included during protocol drafting (as applicable) |
| Added detail relating to DIPA review | 6.1.2 | Not covered in previous version and to increase awareness |
| Removal of reference to CS_WI_MS0207 | 6.4, 7.0 | CS_WI_MS0207 is obsolete and there is no alternative WI to include as a reference |

- APPENDICES

Not Applicable

Page 13 of 13

Copyright © 2000, 2004, 2007, 2013-2016, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

UserName: Murray, Kelly (q798519) Title:

Date: Thursday, 06 January 2022, 08:52 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Corley, Helen (q730385) Title:

Date: Thursday, 06 January 2022, 09:56 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Eason, Carrie (q605126) Title:

Date: Thursday, 06 January 2022, 10:50 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Emanuel, Joanne (q721304) Title:

Date: Thursday, 06 January 2022, 12:00 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Goodwin, Isy (q630183) Title:

Date: Monday, 10 January 2022, 03:37 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Monday, 10 January 2022, 09:19 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ferrari, Antonio (q844337) Title:

Date: Tuesday, 11 January 2022, 04:58 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Weilert, Doris (q406557) Title:

Date: Tuesday, 11 January 2022, 08:17 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ruppenthal, Nancy (q700659) Title:

Date: Tuesday, 11 January 2022, 09:19 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================