|  | IQVIATM Work Instruction Preparation of Investigators Brochure |
| --- | --- |
|  | Document Number and Revision: CS_WI_MW010 Revision 7 |
| Document Owner: Suzie Hendriques | Author(s): Corinne Willmott, Suzie Hendriques |

# PURPOSE

To describe the procedures for preparing and/or updating an Investigator's Brochure (IB).

# SCOPE

  - This work instruction (WI) applies to all projects for which an IB is written or updated by IQVIA Global Medical Writing.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Lead Medical Writer (MW) | 6.1, 6.2, 6.3, 6.4, 6.5 |
| Medical Writing Quality Control (QC) Reviewer | 6.3 |
| Project Leader (PL) | 6.1, 6.3, 6.5 |
| Project Team Member (PTM)1 | 6.1, 6.2, 6.3 |
| Senior Medical Writing Reviewer | 6.3 |

Note:

1	Project Team Members may be requested to contribute and/or perform document review as detailed in the Scope of Work (SoW) and may include the Therapeutic Medical Advisor (TMA), Pharmacokinetic (PK) Scientist, Regulatory Advisor, or other functions, as appropriate.

# DEFINITIONS

Refer also to QG_OD_SMT0018, Glossary of Terms-Clinical Services

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Preliminary Work

Unless otherwise described in the contracted SoW, IQVIA is responsible only for preparing one specific de novo IB or IB update version at the request of the Customer. The Customer retains responsibility for regular review of the IB and prompting, planning, and delivering all future required updates, including both annual and any ad hoc updates.

Page 1 of 7

Copyright © 2009, 2011, 2015, 2017, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | Lead MW | Reviews SoW to determine whether preparation of the IB is a stand- alone Medical Writing task or involves other IQVIA functions. Note: For IB preparation as a stand-alone Medical Writing task, responsibilities of roles from other functions within IQVIA will be undertaken by members of the Customer team, as needed. | At Project Award |
| 6.1.2 | Lead MW | Holds a kick-off meeting, if required, with the Customer and IQVIA PL, other PTMs as required (typically by teleconference) to plan the de novo IB or IB updates, including agreement of timelines, and determine roles/responsibilities within the project team. This includes agreement on the text/sections to be drafted by the Lead MW, PTM(s), and/or Customer team members, where appropriate. | At Project Award |

  - Preparation of Draft Investigator’s Brochure

The IB is created based on the International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (GCP) (R2): Consolidated Guideline, Section 7.0, and any other applicable regulatory requirements, as well as information provided by the Customer.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | Lead MW | - Receives from the Customer all information/data required to draft the IB. - Works with other PTMs (e.g., PL, TMA, Regulatory Advisor, PK Scientist) and drafts the IB. Ensures that the document includes all elements required by ICH E6 GCP (R2): Consolidated Guideline, Section 7.0, including, where necessary, a Reference Safety Information (RSI) section clearly detailing "expected" Serious Adverse Reactions to support decisions about expedited reporting, and is in accordance with the data provided by the Customer. The current approved Reference Study Information (RSI) content must be provided by the Customer and not drafted or edited by the Lead MW. Note: Additional Customer guidelines and regulatory requirements, when specified, may need to be followed. | Project Setup; when creating a de novo IB |
| 6.2.2 | Lead MW | - Adds new information and/or revises existing information according to the Customer’s instructions and SoW. The source information for the IB updates should be provided by the Customer. - Ensures that all revisions are per the above-mentioned ICH GCP guideline and are accurate and in accordance with data provided by the Customer. | Project Conduct; when updating an existing IB |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Assesses the impact of the update(s) on all sections of the IB, in consultation with other PTMs, as appropriate, and updates all sections accordingly. - If agreed in the SoW, may edit the IB for a mature compound to make non-clinical and early development sections more concise and the document more focused. - Additional Customer guidelines, when specified, may need to be followed |  |

  - Internal Review of Draft Investigator’s Brochure

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | Lead MW | Ensures that the IB undergoes a QC review prior to delivery for Customer review. | After IB is created or updated |
| 6.3.2 | QC Reviewer | - Performs QC review in accordance with CS_OP_MW005, Quality Control (QC) Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables electronically or via wet ink signature. | After IB is created or updated |
| 6.3.3 | Senior Medical Writing Reviewer | - Performs Senior Medical Writing review in accordance with CS_WI_MW0221, Senior Medical Writing Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables electronically or via wet ink signature. | Usually concurrently with QC review |
| 6.3.4 | Lead MW, PL | - The Lead MW ensures that the IB is reviewed by other applicable reviewers, as specified by the SoW. - The Lead MW and the PL determine the number and type of reviewers as well as the scope of the review based on the project SoW. | After IB is created or updated |
| 6.3.5 | Reviewer (PTMs per SoW) | - Performs review of the draft IB per the scope of the review based on the SoW. - Makes clear and specific comments and discusses any complex changes with the Lead MW. - Comments may be made using Microsoft Word track changes feature and/or by annotating a copy of the document, or as a written summary if there are few comments. - Returns comments by the agreed method to the Lead MW. | During review |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: For IB sections drafted by IQVIA PK scientist, PK scientist follows review process outlined in PI_WI_PK0210, Preparation and Review of CP-generated Documents and provides consolidated PK/PD comments. |  |
| 6.3.6 | Reviewer (PTMs per SoW) | Signs CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables electronically or via wet ink signature. | Following review of the IB |
| 6.3.7 | Lead MW | Reviews comments received from internal reviewers and ensures that all comments are addressed as appropriate by updating the draft IB. If any requested updates are not implemented, the reason(s) is/are to be documented and discussed with the reviewer, as appropriate. | Upon receipt of internal review comments |
| 6.3.8 | Lead MW | Signs CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables as Author to confirm all review comments have been reviewed and addressed, as appropriate. Forms can be signed electronically or via wet ink signature. | After all comments have been addressed |
| 6.3.9 | Lead MW | Sends the draft IB to the Customer for review in accordance with CS_WI_MW0201 Sending Medical Writing Deliverables to Customers Securely. | Upon completion of updates following internal review |

  - Revisions to the Draft Investigator’s Brochure Incorporating Customer Comments

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | Lead MW | - Reviews all Customer comments received on the draft IB. - Forwards Customer comments on PK/PD sections prepared by the PK scientist to the assigned author for evaluation and revision. The Lead MW should not make any changes to the sections provided by the PK scientist without consultation. - Depending on the scope and nature of the comments, and the contractual requirements, the Lead MW may plan a comments resolution meeting with the Customer to discuss and define exactly what changes are required and to agree on subsequent steps (refer to CS_OP_MW0203, Preparation of Medical Writing Deliverables). - After incorporation (along with any other comments/changes), ensures that all Customer requests have been addressed. - Ensures that QC review is performed prior to issue of the final version (refer to Section 6.3.1). Notes: | After Customer review of IB is completed |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Depending on the nature of the comments, it may be appropriate for other IQVIA PTMs to review the changes in addition to the Lead MW. - The Customer may review the document more than once if additional drafts are included in the SoW, in which case the process described in Sections 6.3 and 6.4 above will be repeated, as appropriate. |  |
| 6.4.2 | Lead MW | Once the document is finalized, sends IB to the Customer for content approval. | After IB is finalized |

  - Filing of IB

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | PL or delegate | Receives the final, approved IB from the Customer and files as appropriate. | After de novo/revised IB is approved by Customer |
| 6.5.2 | Lead MW | Completes all filing activities according to CS_WI_MW0233, Management and Filing of Medical Writing Documentation. | Throughout project |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_FM_MW007 | Internal Signature Page for Medical Writing Deliverables |
| 7.2 CS_WI_MW0201 | Sending Medical Writing Deliverables to Customers Securely |
| 7.3 CS_WI_MW0221 | Senior Medical Writing Review of Medical Writing Deliverables |
| 7.4 CS_WI_MW0233 | Management and Filing of Medical Writing Documentation |
| 7.5 CS_OP_MW005 | Quality Control (QC) Review of Medical Writing Deliverables |
| 7.6 QG_OD_SMT0018 | Glossary of Terms-Clinical Services |
| 7.7 CS_OP_MW0203 | Preparation of Medical Writing Deliverables |
| 7.8 PI_WI_PK0210 | Preparation and Review of CP-generated Documents |
| External References |  |
| 7.9 ICH-GCP: E6 (R2) | International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (R2): Consolidated Guideline, Section 7.0 |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_MW010 | Preparation of Investigators Brochure | 6 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Minor editorial changes, including change in terminology from “electronic approval workflow” to “electronically” | Throughout | To ensure consistency with other SOPs |
| Senior Medical Writing Reviewer added to Section 3.0 | 3.0 | To align with roles defined in SOP |
| Added text to state that IQVIA is responsible for only preparing 1 specific de novo IB or IB update version at the request of the Customer. | 6.1 | To clarify that IQVIA are not responsible for yearly IB updates, but will do 1 document at the request of the Customer |
| Updated WHO column to state it is the Lead MW to holds the KOM, and Step text updated to include PL and other PTMs as required | 6.1 | One person is responsible for the KOM, and other PTMs attend as required |
| Added text to state that RSI content must be provided by the Customer, and not drafted or edited by MW | 6.2 | To clarify that the RSI content is the Customer’s responsibility |
| Deleted specific step that states PK Scientist may support drafting or updating of PK/PD sections of the IB | 6.2 | Footnote in Section 3 specifies any PTM may contribute and/or perform document review as detailed in SOW, therefore a specific step for PK Scientist is not required. |
| Deleted text that states reviewers will typically include a TMA, but may include experts from other areas based on SOW | 6.3 | Previously stated that the IB will be reviewed by applicable reviewers, as specified in the SoW |
| Deleted note that states the Regulatory Advisor checks the RSI format in the IB | 6.3 | RSI content responsibility added to Section 6.1 instead. Regulatory Advisor may not be included in the SoW |

| Updated WHO column to state “Reviewer (PTMs per SOW); removed mention of PL specifically | 6.3 | To clarify that the Reviewer could be any PTM |
| --- | --- | --- |

- APPENDICES

Not Applicable

Page 7 of 7

Copyright © 2009, 2011, 2015, 2017, 2018, 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Ferrari, Antonio (q844337) Title:

Date: Thursday, 07 July 2022, 06:58 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Willmott, Corinne (q778849) Title:

Date: Thursday, 07 July 2022, 07:15 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Weilert, Doris (q406557) Title:

Date: Thursday, 07 July 2022, 09:26 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Thursday, 07 July 2022, 11:16 PM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================