|  | IQVIATM Work Instruction Producing a Clinical Study Protocol Amendment |
| --- | --- |
|  | Document Number and Revision: CS_WI_MW0236 Revision 2 |
| Document Owner: Corinne Willmott | Author(s): Corinne Willmott, Anne Thomson |

# PURPOSE

To define the circumstances in which a clinical study protocol amendment may be required and to describe the steps involved in preparing a protocol amendment.

# SCOPE

  - This work instruction (WI) applies to projects in which a clinical study protocol amendment is prepared by IQVIA Global Medical Writing, either as a stand-alone service or in conjunction with other IQVIA service groups.

  - This WI does not cover the process for preparing the initial clinical study protocol. Refer to CS_WI_MW006, Producing a Clinical Study Protocol.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Lead Medical Writer (Lead MW) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 |
| Pharmacokinetic (PK)/Pharmacodynamic (PD) Scientist | 6.1, 6.2, 6.3, 6.5 |
| Project Leader (PL) | 6.1, 6.2, 6.4, 6.5, 6.6, 6.7 |
| Clinical Lead (CL) | 6.1 |
| Medical Writing QC Reviewer | 6.3, 6.6 |
| Senior Medical Writing (MW) Reviewer | 6.3 |
| Statistical Team Lead (STL)/Experienced Biostatistician (EB) | 6.1, 6.2, 6.3, 6.5 |
| Therapeutic Medical Advisor (TMA) | 6.1, 6.2, 6.3, 6.5 |
| Lead Publisher | 6.6 |

Notes:

- The PL responsibilities may be undertaken by a member of the Project Leadership group, a Clinical Project Manager from the Early Clinical Development group or IQVIA Biotech, or, in the case of a stand-alone project, by the Lead MW, their Line Manager, or other functional lead.

- Business units within IQVIA may use different terminology for the roles described above (e.g., for IQVIA Biotech projects, responsibilities of the STL/EB may be undertaken by the Statistical Design Expert).

Page 1 of 14

Copyright © 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

# DEFINITIONS

Statistical Team Lead (STL)/Experienced Biostatistician (EB): Someone who is able to apply specific statistical or therapeutic knowledge and capable of managing challenging discussions with the Customer (see CS_WI_BS006, Statistical Review and Input to a Clinical Trial Protocol or, for IQVIA Biotech projects, see SOPCR007, Development of Statistical Section of the Protocol).

Protocol Amendment: Formal documentation of necessary changes to the content of an approved, final protocol.

After the original protocol has been finalized and submitted, the need for a protocol amendment may arise in relation to the following:

- Enrollment issues

- Study logistics

- New guidance documents or information

- Potential safety issues

- Request from a Regulatory Body, Independent Ethics Committee (IEC), or Institutional Review Board (IRB)

- Other reasons.

In general, protocol amendments must not be used as an opportunity to adjust wording/style preference, correct minor typographical errors, or be seen as a substitute for a thorough review of the protocol during the original drafting period. Some Customers may have a template and/or process for protocol amendments which they have determined to be “administrative” and/or for handling of “non-substantial” changes.

Typically, unless otherwise agreed with the Customer, the protocol amendment includes the following components:

- Description of changes: a list of all relevant changes to the protocol, with brief rationale for each (often presented in a tabular format); and

- Revised protocol: with all changes relevant to the protocol amendment incorporated into the protocol text.

Depending on the template used, both components may be included within the same document (e.g., the description of changes may form a new appendix to the revised protocol or preface the revised protocol).

Summary of Changes: A standalone document listing all changes to the protocol presented by section, including previous and revised text, with a rationale for each change. This document will be prepared according to local regulatory requirements, as needed.

Redline Version: A version of the final revised protocol showing all changes using Word track changes functionality, prepared by comparing the previous and new protocol

versions. If requested by the Customer, this document is prepared after the protocol amendment has been content-approved by the Customer.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Establishing Requirement for Protocol Amendment and Preliminary Work

The PL/CL in conjunction with the Customer will decide whether an immediate amendment is needed (see Sections 6.1.2 and 6.1.3).

Unless otherwise requested by and agreed with the Customer, IQVIA policy is that potential changes to the protocol must be assessed for impact as follows:

    - Changes requiring an immediate protocol amendment:

      - Any change that impacts the subject in any way, such as dosing, prior/concomitant medications, restrictions, visit details or adding, removing or amending any assessments (including follow up checks). This includes correcting any inconsistency, ambiguity or error in the protocol that may result in an impact on the subject or the validity or integrity of his/her data. Changes of this type would normally result in a protocol amendment deemed as “substantial”.

    - Other changes requiring a protocol amendment (may be deemed “administrative” or “non-substantial”):

      - Changes with no impact on the subject or the conduct of the study assessments, such as contact details or vendor information.

      - Other clarifications or corrections that have no potential impact on the subjects or safety considerations.

    - Changes not requiring a protocol amendment:

      - Minor corrections, such as typographical, spelling or formatting errors. Any such errors may be corrected in a future protocol amendment, if prepared.

Note: For most projects, protocol amendment preparation is a cross-functional collaborative task, therefore it is vital to identify all contributors and reviewers, not only the Lead MW, as early as possible after the decision/request to prepare a protocol amendment has been made, and before drafting of the amendment begins.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | PL/CL | - Performs the activities outlined in CS_WI_SM0020, Management of Revised Clinical Study Documents. - Obtains, or works with the Customer to create, a proposed list of all changes to be included in the protocol amendment (e.g., using CS_FM_SM0039, Protocol Change Log or a Customer template, as applicable), with rationale for each change and impact on the study. | Upon becoming aware of requirement for potential changes to the protocol |
|  |  | Note: For IQVIA Biotech projects, refer to WPPM018, Communication and Management of Revised Essential Clinical Study Documents and NVA_FM_PM706, Project Management Communication Workbook (External), as appropriate. |  |
| 6.1.2 | PL/CL | - Ensures that all necessary contributors and reviewers have been identified, based on the proposed content of the protocol amendment, and advised of their role before drafting of protocol amendment begins. - Notifies the Lead MW and other team members of the need for an immediate protocol amendment. - Provides the proposed list of changes to the assigned Lead MW. Note: The proposed list of changes to be made to the protocol may also be discussed and/or documented during a meeting with the Customer and may take the form of meeting minutes or email communication, when appropriate. | Having confirmed the requirement for an immediate protocol amendment with the Customer |
| 6.1.3 | PL/CL | - Assesses potential changes to the protocol and obtains agreement from Customer that the changes can be incorporated into a future protocol amendment. - Maintains a list of required changes (e.g., using CS_FM_SM0039, Protocol Change Log, NVA_FM_PM706, Project Management Communication Workbook (External) for IQVIA Biotech projects or a Customer template, as applicable) until the agreed time at which a protocol amendment will be developed. | When an immediate protocol amendment is not needed |
| 6.1.4 | PL | - Ensures that the Customer has made a written commitment to award the work and that appropriate budget for all contributing functions is confirmed before work starts. - Requests review of the proposed list of changes and the rationale for each change by identified contributors and reviewers who provide function-specific input, as appropriate. | At Award or after request for a protocol amendment is received |
|  |  | - Consults the Lead MW on protocol amendment delivery timelines before communicating them to the IQVIA project |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | team and Customer or agreeing to timelines requested by Customer. - Acts as main contact/liaison between the Customer and the IQVIA project team, as appropriate. - Communicates the protocol amendment delivery timelines (draft and final versions) and milestones to the appropriate IQVIA team members and the Customer. |  |
| 6.1.5 | Lead MW | - Requests access to (or initiates set up of) appropriate filing areas (e.g., the electronic Trial Master File [TMF]) and maintains documentation in accordance with CS_WI_MW0233, Management and Filing of Medical Writing Documentation. - Requests a copy of the relevant Scope of Work (SoW)/budget information from the PL, when applicable. - Provides input on required budget to the PL, when applicable, if protocol amendment preparation is out-of-scope (i.e., not included in SoW). - Determines the Customer's requirements for template, format (e.g., tracked changes and/or clean versions), and content. See Section 4.0 (Protocol Amendment) for further details. - Reviews the proposed list of changes (and the rationale for each change) received from the PL, requesting clarification or additional information, as applicable, and communicates with Customer and/or PL if the proposed changes will require input from other contributors or reviewers not previously identified. - Confirms and finalizes identity of protocol amendment reviewers and contributors with input from the Customer and/or PL. This can include IQVIA staff, Customer staff, and/or third parties, including Investigators. - Discusses and agrees with Customer the format in which review comments will be returned to the Lead MW. The preference is for one set of consolidated and adjudicated comments. Any deviation from this may incur additional costs and the PL must be informed. - Schedules review of the protocol amendment by relevant team members, including a Medical Writing QC Reviewer and Senior MW Reviewer. - Provides input on timelines for delivery of each version. - Requests resource assignment from the Document Publishing group for publishing of the protocol amendment per the agreed timelines, if IQVIA is contracted for this work. | Upon assignment to project and/or notification from the PL that a protocol amendment is required |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.6 | TMA, STL/EB, PK/PD Scientist, as applicable | - Reviews the proposed list of changes (and the rationale for each change) received from the PL, requesting clarification or additional information, as applicable. - Provides function-specific input regarding the proposed changes to Lead MW, PL, Customer, and other team members, as appropriate, to support finalization of the list of changes before protocol amendment drafting begins. | Upon notification from the PL that a protocol amendment is required |
| 6.1.7 | PL | - Finalizes and obtains written approval from the Customer for the list of changes, discussing and incorporating input from other team members, as needed. | Following review of proposed list of changes |

  - Preparing the Protocol Amendment

Work can start when the Lead MW receives the approved list of changes required to the protocol, budget is approved, essential team members are identified, and the template is agreed.

Amendments to the protocol must be made with consideration to the International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (GCP) (R2): Consolidated Guideline, Section 6, and any other applicable regulatory requirements, as well as information provided by the Customer.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | PL or Lead MW | If required, arranges a Kick-off Meeting (KOM) with the Customer and the IQVIA project team to discuss the following: - List of changes and rationale - Timelines - Requirement for Summary of Changes document - Requirements for Redline Version, when applicable, including delivery format (pdf and/or Word). | Upon receipt of Customer- approved list of changes and before drafting begins |
| 6.2.2 | Lead MW | - Prepares the Draft 1 protocol amendment, liaising with the IQVIA project team and Customer, as necessary. - Receives and incorporates contributions from other team members into the protocol amendment, as applicable. - Prepares a separate Summary of Changes document, if required per the agreed scope/budget. This may be done following finalization of content of the protocol amendment. Note: The Draft 1 protocol amendment may be prepared using Word track changes functionality to highlight the changes implemented in the protocol, as agreed with the Customer and other IQVIA team members. | Upon receipt of Customer- approved list of changes |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.3 | PL | Contributes to protocol amendment development and supports the Lead MW, as required. | During protocol amendment development |
| 6.2.4 | TMA, STL/EB, PK/PD Scientist, as applicable | - Provides input to protocol amendment, if appropriate (based on nature of changes). - When applicable to their function, assumes responsibility for the appropriate formatting, internal review, and QC of new or significantly amended sections of the protocol. | Upon notification from the PL that a protocol amendment is required and as requested by Lead MW |

  - IQVIA Internal Review of the Proposed Draft 1 Protocol Amendment

Quality control and Senior MW reviews are always needed (for exceptions, see note below) and must be performed before the Draft 1 protocol amendment is sent to the Customer. Other internal reviews, as confirmed by the PL, should also be performed before issuing the Draft 1 protocol amendment to the Customer, unless a higher level agreement (e.g. Partnership Manual) allows for parallel review.

Notes:

    - Senior MW review of administrative changes or small, non-substantial protocol amendments may be omitted, only when discussed and agreed with the Lead MW’s line manager. A QC review must always be performed.

    - The Summary of Changes document, if in scope, does not require internal review, other than a QC review which is mandatory. Other reviews may be conducted if requested by the Customer and/or PL and when appropriate budget is assigned.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | Lead MW | Distributes the proposed Draft 1 protocol amendment and all applicable source documents for IQVIA team reviews (as identified by the PL per Section 6.1.2), including QC and Senior MW review. Note: Source documents may differ for each type of internal review but may include the Customer-approved list of changes and documentation of other discussions (e.g., minutes of the KOM). | Before issue of Draft 1 protocol amendment to Customer |
| 6.3.2 | Medical Writing QC Reviewer | - Performs QC review in accordance with CS_OP_MW005, Quality Control (QC) Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs form CS_FM_MW007, Internal Signature Page for Medical Writing Deliverables, via electronic approval | Upon receipt of proposed Draft 1 protocol amendment |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | workflow or wet-ink signature, to confirm completion of their review. |  |
| 6.3.3 | Senior MW Reviewer | - Performs review in accordance with CS_WI_MW0221, Senior Medical Writing Review of Medical Writing Deliverables. - Provides written comments to the Lead MW. - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, to confirm completion of their review. | Upon receipt of proposed Draft 1 protocol amendment |
| 6.3.4 | TMA, STL/EB, PK/PD Scientist, other reviewers, as applicable | - Reviews the proposed Draft 1 protocol amendment: - TMA: Provides any review comments on the amendment from a medical perspective. - STL/EB: Refer to CS_WI_BS006 or, for IQVIA Biotech projects, SOPCR007. - PK/PD Scientist: Refer to PI_WI_PK0210, Preparation and Review of CP-generated Documents. - Other team members, as agreed with Customer and PL, may review all or part of the document, as required. - Provides written findings and comments to the Lead MW, preferably as Microsoft Word tracked changes (annotated protocol amendment). - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, when requested by the Lead MW, to confirm completion of their review. | Upon receipt of proposed Draft 1 protocol amendment |
| 6.3.5 | Lead MW | - Requests internal reviewers to sign form CS_FM_MW007 via electronic approval workflow or wet-ink signature. This form should be completed for each review cycle. It is not necessary for all internal reviewers to sign the same copy of the form. - Makes a copy of the comments from each reviewer to create the Medical Writer Response document. - Reviews each comment. - Discusses any complex or major findings with the appropriate reviewer. The Lead MW must not make any changes to the PK sections requested during internal review by other reviewers without consultation with the PK/PD Scientist. Similarly, any changes to the study design requested internally must also be reviewed with the STL/EB and PK/PD Scientist to assess impact on the planned statistical and PK analysis and data interpretation. Any changes to the study design proposed by the internal reviewers should be discussed with the Customer before implementation. - Discusses and resolves conflicting comments. | Upon receipt of internal review comments |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Makes appropriate revisions to the master copy of the protocol amendment and finalizes the Draft 1 protocol amendment for issue to the Customer. - Annotates the Medical Writer Response document with a response for any review comment that is not incorporated, or that is addressed in a different way to the reviewer’s suggestion. - Signs form CS_FM_MW007 via electronic approval workflow or wet-ink signature, to document that comments have been addressed. |  |

  - Sending the Protocol Amendment for Customer Review

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | Lead MW | - Verifies that all internal reviews have been performed and comments addressed, as appropriate. - Sends the Draft 1 protocol amendment to the Customer by an agreed and secure method (refer to CS_WI_MW0201, Sending Medical Writing Deliverables to Customers Securely). | Draft protocol amendment is finalized (after internal review comments have been addressed) |
|  |  | - Sends a covering e-mail to the Customer detailing: |  |
|  |  | - The status of the document. |  |
|  |  | - Any questions or issues requiring clarification. |  |
|  |  | - The date by which comments are expected. |  |
|  |  | - Request for comments to be returned to the Lead MW as one set of consolidated and adjudicated comments, unless otherwise agreed. |  |
|  |  | Note: In exceptional circumstances, if requested by the Customer, an unreviewed draft protocol amendment may be sent if the PL, key team members, and line manager of Lead MW agree; however, this must be clearly identified as an unreviewed draft. This change from usual Medical Writing process should be documented in a Global Medical Writing File Note (CS_FM_MW0224). Before sending the protocol amendment, the Lead MW must advise the Customer that the protocol amendment has not been reviewed and that the content may change after internal reviews, including QC, are completed. |  |
| 6.4.2 | Lead MW | Forwards the above communication to other IQVIA team members, as appropriate (refer to CS_WI_MW0201), for information purposes. | Following issue of the Draft 1 protocol to the Customer |

  - Handling Customer Comments

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | Lead MW | - Reviews the comments and, if applicable, shares the comments with the PL and other IQVIA project team members (e.g., TMA, STL/EB, and/or PK/PD scientist) for resolution of relevant comments. - Plans, depending on the scope and nature of the comments, and the contractual requirements, a comments resolution meeting (CRM) with the Customer to discuss and define exactly what changes are required and to agree on a turnaround time. - Documents the outcome of the discussions from the CRM, as appropriate. For further details, refer to Section 6.3 of CS_OP_MW0203, Preparation of Medical Writing Deliverables. - Highlights any conflicting or unclear comments to the Customer for clarification, consulting first with other IQVIA project team members as appropriate. This may be handled during the CRM, if held. | Upon receipt of Customer review comments |
| 6.5.2 | TMA, STL/EB, PK/PD Scientist, PL, other team members | Attends the CRM to discuss comments and their resolution with the Lead MW and Customer, if requested by the Lead MW. | Following review of Customer review comments |
| 6.5.3 | Lead MW | - Updates the protocol amendment, ensuring that every comment is addressed appropriately. The Lead MW must not make any changes to the PK sections requested by the Customer without consultation with the PK/PD Scientist. Similarly, any changes to the design must also be reviewed with the STL/EB and PK/PD Scientist to assess impact on the planned statistical and PK analysis and data interpretation. - Provides an explanation to the Customer, as appropriate, regarding any comment(s) for which the requested change is not incorporated or is addressed in a different way than the Customer suggested. The Lead MW must note the reason on a copy of the Customer’s comments (Medical Writer Response document). | Following review of Customer review comments and CRM (if held) |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.4 | Lead MW | Forwards the revised protocol amendment to other project team members (e.g., TMA, STL/EB, PK/PD Scientist), if applicable, to review the changes prior to any subsequent delivery to the Customer. Changes requiring review may include: - Changes of a statistical nature or to the statistical section - must be reviewed by the STL/EB. - Changes relating to PK/PD sections and/or study design changes which may affect the PK/PD results - must be reviewed by the PK/PD scientist. | After incorporation of Customer review comments |

Notes:

    - Depending on the number of review cycles specified in the budget and/or confirmed by the PL, the processes described in Steps 6.3, 6.4, and 6.5 above may be repeated as applicable for additional drafts of the protocol amendment.

    - In situations where additional changes are requested by the Customer and/or other team member(s) during preparation of the protocol amendment, via review comments or other communication, the Lead MW and PL should work with the Customer to agree the additional changes required and discuss potential impact on scope, agreed timelines, and budget for the protocol amendment. Such situations may require additional review cycles, involving internal and/or Customer teams as applicable.

  - Finalization of the Protocol Amendment and Delivery to Customer

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | PL | Supports the Lead MW in ensuring that sufficient time is allowed for final updates to the protocol amendment and for QC review after receipt and resolution of final Customer comments. | Following completion of all review cycles |
| 6.6.2 | Medical Writing QC Reviewer | Performs QC review of the proposed final version of the protocol amendment and the Summary of Changes document, where applicable (see Section 6.3.2). Note: The QC review of the Summary of Changes document may occur after the protocol amendment has been finalized. | Upon receipt of proposed final deliverable(s) from the Lead MW |
| 6.6.3 | Lead MW | - Ensures that the proposed final protocol amendment version has undergone QC review in accordance with CS_OP_MW005. Sufficient time must be allowed after receipt of final Customer comments to allow for updates and to permit the subsequent QC review to be effective. | Following completion of final QC review, resolution of all review comments, and necessary updates |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Sends the proposed final protocol amendment to the Customer (referring to CS_WI_MW0201). This can be done directly or via the PL. - Asks the Customer to confirm in writing that the protocol amendment is final and that IQVIA Medical Writing’s activities are complete. |  |
| 6.6.4 | Lead MW | - If publishing is included in SoW/agreed budget for IQVIA, sends the final protocol amendment to the Lead Publisher. - Sends the Summary of Changes document, if prepared, to the appropriate IQVIA team member(s) and/or the Customer, as confirmed by the PL. | Following Customer confirmation that protocol amendment content is final |
| 6.6.5 | Lead Publisher | - If included in SoW/agreed budget, publishes the protocol amendment in line with Customer requirements/expectations according to CS_WI_RA0292, Publishing - Producing Clinical and Submission Publishing Deliverables. - Sends final published deliverable (if applicable) to the Customer securely in accordance with CS_WI_RA0292. | Following Customer confirmation that protocol amendment content is final and ready for publishing |
| 6.6.6 | Lead MW | - Prepares redline version of the final protocol amendment using appropriate Microsoft Word functionality. - Checks the accuracy and clarity of the redline document for each applicable delivery format (pdf and/or Word). - Delivers redline version to Customer and distributes to IQVIA team members, as needed. | Following Customer confirmation that protocol amendment content is final (and where redline version is required) |
| 6.6.7 | PL | Ensures that the final protocol amendment is signed by the Customer representative and others, as needed. | Following protocol amendment content approval by Customer |

  - Filing

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.1 | Lead MW | Files documentation relating to protocol amendment preparation in accordance with CS_WI_MW0233, Management and Filing of Medical Writing Documentation. | Throughout development of the document |
| 6.7.2 | PL | If required for TMF filing, obtains a copy of the Customer-approved final protocol amendment from the Customer and files in the TMF. Note: This version may differ from the proposed final version issued to the Customer by the Lead MW. | When Customer has confirmed that the protocol amendment has been approved |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_WI_BS006 | Statistical Review and Input to a Clinical Trial Protocol |
| 7.2 SOPCR007 | Development of Statistical Section of the Protocol |
| 7.3 CS_WI_SM0020 | Management of Revised Clinical Study Documents |
| 7.4 CS_FM_SM0039 | Protocol Change Log |
| 7.5 CS_WI_MW0233 | Management and Filing of Medical Writing Documentation |
| 7.6 CS_OP_MW005 | Quality Control (QC) Review of Medical Writing Deliverables |
| 7.7 CS_FM_MW007 | Internal Signature Page for Medical Writing Deliverables |
| 7.8 CS_WI_MW0221 | Senior Medical Writing Review of Medical Writing Deliverables |
| 7.9 PI_WI_PK0210 | Preparation and Review of CP-generated Documents |
| 7.10 CS_WI_MW0201 | Sending Medical Writing Deliverables to Customers Securely |
| 7.11 CS_FM_MW0224 | Global Medical Writing File Note |
| 7.12 CS_OP_MW0203 | Preparation of Medical Writing Deliverables |
| 7.13 CS_WI_RA0292 | Publishing - Producing Clinical and Submission Publishing Deliverables |
| 7.14 CS_WI_MW006 | Producing a Clinical Study Protocol |
| 7.15 WPPM018 | Communication and Management of Revised Essential Clinical Study Documents |
| 7.16 NVA_FM_PM706 | Project Management Communication Workbook (External) |
| External References |  |
| 7.17 ICH-GCP: E6 (R2) | International Council for Harmonisation of Technical Requirements for Pharmaceuticals for Human Use (ICH) E6 Good Clinical Practice (R2): Consolidated Guideline, Section 6 |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_MW0236 | Producing a Clinical Study Protocol Amendment | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Discretionary use of Patient Safety Review (PSR) process for protocol amendments has been removed | 6.1.7 | PSR process is no longer a requirement for protocols per senior management decision |
| For preparation of redline version, added verification of required delivery format at kick- off meeting and verification of accuracy and clarity of redline versions prior to delivery to Customer(s). | 6.2.1, 6.6.6 | Where submission of redline version(s) is required, clarifies the steps to be followed to ensure quality of deliverable(s). |
| Removal of reference to CS_WI_MS0207 | 6.3.4, 7.0 | CS_WI_MS0207 is obsolete and there is no alternative WI to include as a reference |
| Add references to WPPM018 and NVA_FM_PM706 | 6.1.1, 6.1.3, 7.0 | Inclusion of these SOPs was required since IQVIA Biotech staff should follow their business unit-controlled documents |
| Minor updates to cross-reference details and hyperlink properties | 6.3.1, 7.0 | To correct typo and link to current effective SOP versions. |

- APPENDICES

Not Applicable

Page 14 of 14

Copyright © 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

UserName: Nikolova, Danny (q601511) Title:

Date: Thursday, 06 January 2022, 08:07 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Murray, Kelly (q798519) Title:

Date: Thursday, 06 January 2022, 08:53 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Corley, Helen (q730385) Title:

Date: Thursday, 06 January 2022, 09:57 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Eason, Carrie (q605126) Title:

Date: Thursday, 06 January 2022, 10:50 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Emanuel, Joanne (q721304) Title:

Date: Thursday, 06 January 2022, 11:59 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Goodwin, Isy (q630183) Title:

Date: Monday, 10 January 2022, 03:36 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Monday, 10 January 2022, 09:41 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ferrari, Antonio (q844337) Title:

Date: Tuesday, 11 January 2022, 04:57 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Weilert, Doris (q406557) Title:

Date: Tuesday, 11 January 2022, 08:20 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Ruppenthal, Nancy (q700659) Title:

Date: Tuesday, 11 January 2022, 09:21 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================