|  | IQVIATM Work Instruction Clinical Trial Agreement and Budget |
| --- | --- |
|  | Document Number and Revision: CS_WI_RSU0066 Revision 2 |
| Document Owner: Mary Beatty | Author(s): Paige Niemczyk, Merab Puleo |

# PURPOSE

To describe the process and responsibilities for the preparation, negotiation, approval, and execution of the Clinical Trial Agreement (CTA) for Investigator sites, including the Budget and Payment Schedule.

# SCOPE

  - This work instruction (WI) applies to projects for which Global Site Activation, Global Investigator Contract Solutions (gICS), or other functional group(s) prepare, negotiate, approve, or execute CTAs.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Contract and Budget Solutions Lead (CBSL) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7, 6.10 |
| Project Leader (PL) | 6.2 |
| Site Activation Manager (SAM) | 6.2, 6.3, 6.4, 6.5, 6.10 |
| Country Site Activation Representative (CSA Rep) | 6.2, 6.4, 6.5 6.6, 6.7, 6.8, 6.9, 6.10 |
| CSA Global Services - Protocol Pricing Rep | 6.2 |
| Fair Market Value (FMV) Legal Liaison | 6.7 |

Notes:

- For studies in Lifecycle Maintenance, the Maintenance Lead (ML) and Global Site Activation Analyst (GSA Analyst) may perform the tasks of the SAM.

- Investigator site CTA refers to the Country CTA Template, Budget and Payment Terms for an individual site.

# DEFINITIONS

Refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services

Grant Plan® is the tool for Fair Market Value (FMV) determination; Grant Plan® data up to the 90th percentile, as available, will be provided for studies applicable to IQVIA FMV compliance.

Trial Management System: When referencing “Trial Management System” throughout this WI, this infers tracking directly into CTMS or other IQVIA trial management systems.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

Each role mentioned in this WI is responsible to:

- Ensure tracking, status reporting, risk/issue identification and mitigation of activities to support site activation in applicable systems as per CS_OP_RSU0060 Site Activation.

- File individual documents or pertinent correspondence in the Trial Master File as they are finalized as per CS_OP_RSU0060 Site Activation.

Per ICH-GCP (5.6.2), IQVIA must provide the Investigator with the Protocol and the Investigator’s Brochure before signing the CTA to conduct the study. IQVIA does not ship Investigational Product (IP) to a site until there is a signed CTA in place or until the Sponsor agrees to an exception in writing, if local regulations allow this exception. In medical device projects, even if the Sponsor agrees to an exception in writing, the device cannot be shipped until a fully signed CTA is in place, pursuant to the applicable medical device regulations.

  - Creating the CTA and Budget Templates Notes:

    - Refer to the Regulatory Intelligence Database (RID) to understand

country contracting intelligence and whether the CTA is part of the submission package to the Ethics Committee/Institutional Review Board (EC/IRB) and/or Regulatory Authority (RA).

    - Refer to the “Country Process Flow Summary Models” In the Submission Authorities and Timelines information found on RID for guidance on how the contract process influences the entire EC/IRB and RA submission process by country.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | CBSL | Consults with the PL on the Scope of Work and determines whether there has been previous discussions or agreement with the Sponsor to follow a specific CTA template development process. Note: Wherever possible, the IQVIA CTA process and templates will be proposed to the Sponsor as the most efficient contracting strategy. | Setup Upon Resourcing to the Study |
| 6.1.2 |  | Confirms with the Sponsor the appropriate global, country, governmental, site-specific and ancillary templates to be prepared for use in the project and based upon the country mix. | Setup |
| 6.1.3 |  | Reviews and negotiates with Sponsor the Global CTA Templates (including ancillary templates) and Global CTA Fallback language based upon the contracting parties (Sponsor and/or IQVIA) in |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | accordance with IQVIA Legal Manual and with appropriate approvals from the Investigator Contract Solutions (ICS) Legal Liaison and the Global Legal Department (GLD) Rep, as needed. Incorporates approved changes from the IQVIA Global CTA Template into the IQVIA Country CTA Templates, as appropriate. |  |
| 6.1.4 | CBSL | Provides IQVIA language or Sponsor “must have” clauses to the CSA Rep for inclusion in the regional or industry template, if being used, and sends the CSA Rep revised template to Sponsor for review and negotiation with approval from ICS Legal Liaison and the GLD Rep, as needed. | Setup |
| 6.1.5 |  | Inserts Protocol information into the Country CTA templates. |  |
| 6.1.6 |  | Files the approved Global and/or Country CTA Templates, Global Fallback Guidance Document, and approvals in the appropriate Sponsor-specific working folder. |  |
| 6.1.7 |  | Delivers approved, final Country CTA Templates, ancillary agreement templates and Global Fallback Guidance Document including documentation of Sponsor approval, to the SAM |  |
| 6.1.8 |  | Tracks the development of templates at the Protocol-Country Level in the Trial Management System. |  |

  - Developing Protocol Pricing Template and Protocol-Country Budgets

Protocol Pricing is developed according to CS_OP_RSU0060, Site Activation, Appendix C: Compensation to Healthcare Professionals for Clinical Research Services.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | PL | Performs one of the following: - Notifies the assigned CBSL if IQVIA is scoped to develop Protocol Pricing Template and Protocol Country Budget(s) OR - Provides the Sponsor’s Protocol Pricing Template and/or Protocol- Country Budget(s) to the CBSL if the Sponsor is scoped to develop Protocol Pricing Template and/or Protocol-Country Budgets. Where Sponsor builds the Investigator budgets, but IQVIA is contracting with and paying the Investigators, obtains written confirmation from the Sponsor that the budget is based on FMV determinations prior to contracting with and making payments to the Healthcare Professionals (HCP) or institution. Proceeds to Step 6.2.2 or 6.2.9, depending on Scope of Work. | Setup After Final Protocol is available |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.2 | CBSL | Establishes and chairs a contracting strategy meeting that is attended by PL, SAM, Clinical Trial Payments (including Drug Dev, as applicable) (both “CTP”) to establish a contracting and budget strategy for the project. Note: It is ideal to have a separate Sponsor contracting strategy meeting for sign off on a CTA strategy plan. | Setup After Final Protocol is available |
| 6.2.3 | CBSL with CSA Global Services - Protocol Pricing Rep | Develops Protocol Pricing Template (i.e., the first country’s Protocol- Country Pricing Budget) using Grant Plan®, with input from CTP, PL, Clinical Lead (CL), and Therapeutic Medical Advisor (TMA), as needed. Grant Plan® data up to the 90th percentile, as available, will be provided for FMV compliance. May modify Protocol Pricing Template in accordance with the Sponsor-requested format. |  |
| 6.2.4 | CBSL | Considers the following, in consultation with the PL and TMA, when developing the Protocol Pricing Template: - Complexity of the required services and procedures. - Anticipated recruitment challenges. - Time commitment required of the HCP or HCP staff. - Inflation factors. - Potentially necessary “conditional” procedures or tests. - Procedures or tests needed to determine subject eligibility for study; and - Subject reimbursement or compensation fees, if approved by the applicable Ethics Committee or Institutional Review Board (EC/IRB). Notes: - Additional fees may be budgeted for extra time and effort to enroll appropriate research participants, including additional study coordinator or other resource needed to perform chart reviews or to conduct subject outreach, or for additional expenses such as advertising costs. - Any proposed additional fee for achievement of subject enrollment goals within a specified time must be escalated to the FMV Legal Liaison for review and approval prior to budget finalization. If the arrangement is approved, additional conditions or requirements may apply. |  |
| 6.2.5 |  | Validates the Protocol Pricing Template with the PL and TMA and updates the Protocol Pricing Template, as appropriate. |  |
| 6.2.6 |  | Develops the Global Payment Schedule. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.7 | CBSL | Attends the CTP scheduled Investigator Payment Alignment meeting (refer to CS_WI_SM0028, Investigator Payments) where the Grant Plan®, EDC, Subject Visit Template and CTA are discussed, and the Protocol Pricing Template and the recommended Payment Schedule are reviewed, resulting in the development and creation of the “Site Visit Template Alignment Specification.” Note: CTP, CBSL, PL, Data Team Lead, CL, SAM, TMA, and Centralized Monitoring Lead (“Budget Build Team”) participate in this meeting. Budget Build Team verifies that the budget is comprehensive and adequate for the work the Sites will need to do to conduct the Protocol, including all necessary and potentially necessary procedures, tests, and study staff resources. | Setup After Final Protocol is available |
| 6.2.8 |  | Performs these tasks: - Reviews the Protocol Pricing Templates and Payment Schedule with the Sponsor, and/or sends the documents to the Sponsor for review and revisions until final approval. - Develops Country Budgets and Country Payment Schedules for all other countries, as needed, using the approved Protocol Pricing Template and incorporating any approved changes from the Global Payment Schedule, and obtains approval for the budget(s) and payment schedule(s) from the Sponsor, if applicable. - Develops negotiation parameters with Sponsor, including all conditional procedures and budget up to approved Grant Plan® limits. Grant Plan® 90th percentile, as available, will be provided separately as the limits for FMV approval. Note: For governmental or site-specific budget and payment term templates, provides IQVIA language or Sponsor “must have” clauses and Grant Plan® pricing to the CSA Rep for inclusion in the regional or industry template and sends the CSA Rep revised template to Sponsor for review and negotiation. |  |
| 6.2.9 |  | Delivers approved, final Country Budgets (including/indicating Grant Plan® Sponsor approved high for negotiation limits and FMV 90th percentile for FMV limits), Country Payment Schedules, and negotiation parameters including documentation of Sponsor approval, to the SAM. |  |
| 6.2.10 | CSA Rep | Determines if a budget is split across contracts, the appropriate payment and invoicing entity, and enters applicable costs from the Country Budget into their Country Payment Schedule Template. |  |
| 6.2.11 | CBSL | Tracks the development of Budget Templates in the Trial Management System. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.12 | SAM | Files documents/records directly in Trial Master File (TMF) or, when applicable, via a Trial Management System workflow process, as appropriate. | Setup After Final Protocol is available |

  - Distributing Protocol-Country CTA Templates

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | CBSL | Inserts Protocol information into the Country templates | Startup After Global and Country Master templates are approved |
| 6.3.2 |  | Delivers the Country CTA Templates, Global CTA Guidance Document, and Sponsor approvals, to the SAM and the Sponsor, as needed. |  |
| 6.3.3 | SAM | Distributes the Country CTA Templates, Global CTA Guidance Document, Country Budget Templates, Country Payment Schedule Templates, negotiation parameters to the CSA Rep. |  |
| 6.3.4 |  | Files the Country CTA Templates, Global CTA Guidance Document, Budget Country Templates, Country Payment Schedule Templates, negotiation parameters, and approvals per the agreed project filing process in the TMF Quality Plan. |  |

  - Training the Project Team on CTA Country Documents

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | CBSL | Provides training to the SAM and the CSA Rep on Sponsor expectations, CTA Processes, Country CTA Templates, Global CTA Guidance Document, Country Budget and Payment Schedule Templates, and budget negotiation parameters (refer to CS_WI_PL0024, Project-Specific Training and Team Member Transition). Note: Training will be recorded and may occur more than once if there are changes to any of the templates. | Startup Before customizing and negotiating Investigator site CTAs |
| 6.4.2 | CBSL | Provides the link to the recorded training and any accompanying presentation to SAM. |  |
| 6.4.3 | CSA Rep | Attends or listens to the recorded CBSL Study specific training prior to beginning work on CTAs for the project. |  |
| 6.4.4 | SAM | Submits the link to the training and any accompanying presentation for posting in eTraining system and assignment to the appropriate eTraining roles as per Project eTraining Guidance (refer to CS_WI_PL0024). |  |
| 6.4.5 |  | Provides rationale in a Memo-to-File if training did not occur. Refer to CS_TP_TMF0059, Trial Master File (TMF) Memo to File (MTF). |  |

  - Customizing and Negotiating Site CTAs

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | CSA Rep | Reviews the Country CTA Template, Country Budget and Country Payment Terms, formats and removes any internal directions, adjusts non-material issues and formatting, if needed. Creates a version of the Country CTA Template, Country Budget Template & Country Payment Schedule (including any ancillary agreements) appropriate for site distribution, as applicable, in accordance with the study specific CTA training from CBSL. | Startup |
| 6.5.2 |  | Completes the translation process in accordance with for any required translations, or updates/changes to the template that need translation. Refer to CS_WI_RSU0032, Translation of Documents. Note: Standard translations are available for standard CTA template wording. |  |
| 6.5.3 |  | Submits the CTA to the EC/IRB/RA, as appropriate, if EC/IRB and/or RA approval of the Country CTA Template and/or Budget Country Template is required (refer to CS_WI_RSU0067, Project Lifecycle Clinical Trial Applications). |  |
| 6.5.4 |  | Inserts the site-specific information into the relevant Country CTA template, including contracting parties, addresses, payees, invoicing information, self-billing information, budget and payment schedule, as applicable. Note: The CSA Rep will determine and action if a site budget may be split across several payees or across several contracts for a site. |  |
| 6.5.5 |  | **Site Requires a Site-Specific Template (Steps 6.5.5 to 6.5.11)** Obtains the site-specific template (e.g. Italy, Spain, Japan, VA CRADA in US), if required, and verifies whether it can be modified to include IQVIA and Sponsor required language. |  |
| 6.5.6 |  | Updates the site-specific template with study, IQVIA and Sponsor must have terms and/or costs included in their Country CTA Template, Budget and Payment Terms |  |
| 6.5.7 |  | Sends the updated site-specific template to the CBSL, including any information from the site about what modifications may be allowed to include IQVIA and Sponsor required language. |  |
| 6.5.8 |  | Tracks the site-specific template in the Trial Management System. |  |
| 6.5.9 | CBSL | Reviews and approves the site-specific template with input from ICS Legal Liaison and IQVIA GLD Rep, as needed, and obtains Sponsor approval. |  |
| 6.5.10 | SAM | Obtains Sponsor approval and/or comments of the site-specific template and sends to the CSA Rep. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.11 | CSA Rep | Turns on Track Changes and Password Protect features in Investigator site CTA documents to ensure all site changes are highlighted. Sends the draft Site CTAs to site electronically or as hard copies, per site or Sponsor preference. | Startup |

  - Negotiating Investigator Site CTA Terms & Conditions

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | CSA Rep | Negotiates Investigator site CTA terms and conditions with the relevant site contacts (e.g., lawyer, Investigator, Board of Directors), according to the CBSL CTA Training and negotiation parameters. Escalates any issues with site responsiveness according to project escalation instructions. Accepts without further review and approval all site requested changes that are within negotiation parameters and do not materially change the meaning of the contract provision. | Startup |
| 6.6.2 |  | Performs these steps if the site’s requested changes are not covered in the CBSL CTA Training and negotiation parameters: - Utilizes the Protocol to evaluate if the site’s request is appropriate - Requests that the site provides a rationale and supporting documentation for the revision requests to be considered. - Evaluates the rationale and negotiates with the site to accept position within negotiation parameters. - Evaluates contractual or operational risk to IQVIA and/or Sponsor if changes are accepted. If the site’s requested changes remain outside negotiation parameters, forwards revision request and rationale to the CBSL for review, or as communicated in the CBSL CTA Training. |  |
| 6.6.3 | CBSL | Reviews revision request, rationale, and supporting documentation, with input from ICS Legal Liaison, GLD Rep as needed, and provides feedback to CSA Rep and indicates if Sponsor approval is needed. Note: Depending on the directive of the Sponsor, Sponsor approvals may be obtained by either the CBSL or SAM. |  |
| 6.6.4 | CSA Rep | Reviews CBSL feedback and if Sponsor approval is needed, follows the path for obtaining Sponsor approval as outlined in the CBSL CTA Training |  |
| 6.6.5 |  | Updates the Investigator site CTA per feedback received and resends the Investigator site CTA to the site. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.6 | CSA Rep | Negotiates with the site until language is approved, then inserts approved language in the CTA. | Startup |
| 6.6.7 |  | If site agreement to the CTA cannot be obtained, informs SAM and PL to determine whether the site should be dropped. |  |

  - Negotiating the Investigator Site Budget and Payment Schedule

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.1 | CSA Rep | Negotiates Investigator site budget and payment schedule with the relevant site contacts (e.g. lawyer, Investigator, Board of Directors), according to the CBSL CTA Training and negotiation parameters. Accepts without further review and approval all site requested changes to the budget and/or payment schedule that are within the Sponsor approved negotiation parameters. | Startup |
| 6.7.2 |  | Performs these steps if the requested Investigator site budget and/or payment schedule revisions are not within the CBSL CTA Training and negotiation parameters: - Evaluates if the request made by the site is 1) supported by the Protocol (PL consultation may be required) and 2) is assumed in another cost found in the budget - Requests that the site provides a rationale and supporting documentation for the revision requests to be considered. - Evaluates the rationale and negotiates with the site to accept a budget and/or payment schedule within negotiation parameters. - Provides the site request including rationale and supporting documentation (in English) to CBSL if a site requests fees not in the budget and CSA Rep determines the fee is supported by the Protocol and not present in another cost already in the budget. Acceptable additional procedures and tests may include: - Additional conditional procedures and diagnostic tests, lab tests, or subject eligibility tests. - Administrative fees such as third-party payment company fees, recruitment company fees, advertising fees, database/software fees, Complian fees, Medicare coverage analysis fees, annual overhead or "start- up"/admin fees. - Subject compensation and reimbursement amounts, if approved by applicable IRB/EC. |  |
| 6.7.3 | CBSL | For fees requested that were not in the budget but have been determined to be proper by the CSA Rep (in accordance with the Protocol), provides feedback to CSA Rep to inform site if fees are acceptable. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | If fees are acceptable, provides the GrantPlan® amount (per same parameter that was approved for the budget) and the GrantPlan® 90th percentile benchmark to the CSA Rep. |  |
| 6.7.4 | CSA Rep | Submits the site’s requested revisions, rationale, and supporting documentation to the appropriate stakeholder for review: - If IQVIA provided the budget, and the request is over the GrantPlan® 90th percentile, sends to FMV Legal Liaison for review. Prior to escalation to FMV Legal Liaison, ensures that the GrantPlan® 90th percentile benchmark has been received from the CBSL and is provided in the escalation to FMV. - If request is under the GrantPlan® 90th percentile, or if the Sponsor provided the budget, proceed to Step 6.7.6. Note: Refer to CS_OP_RSU0060 Site Activation, Appendix C: Compensation to Healthcare Professionals for Clinical Research Services. | Startup |
| 6.7.5 | FMV Legal Liaison | Reviews the justification and information provided by the CSA Rep for the site’s revision request and informs CSA Rep of the outcome of the review. Liaises with Site Fee Committee as needed. Refer to CS_OP_RSU0060 Site Activation. ,Appendix C: Compensation to Healthcare Professionals for Clinical Research Services. |  |
| 6.7.6 | CSA Rep | Follows the CBSL Training for obtaining Sponsor approval, if applicable, to a site’s requested revisions, rationale, and supporting documentation to the FMV with Grant Plan® amounts and FMV review, as applicable. |  |
| 6.7.7 |  | Continues negotiation with the site until approval is obtained. |  |
| 6.7.8 |  | Informs SAM, CL and PL to determine whether the site should be dropped if site agreement to the Investigator site budget and/or payment schedule cannot be obtained (refer to CS_WI_RSU0021, Essential Document Pack.) |  |
| 6.7.9 |  | Inserts the final approved Investigator Site budget and/or payment schedule into the Investigator site CTA if the revised Investigator site budget and/or payment schedule has been approved. Divides the budget amounts and payment schedule across all contracts, if there are multiple contracts for a site, ensuring that the sum of the individual budgets exactly matches the approved total budget. |  |

  - Preparing the Investigator Site CTA for Review and Approval

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.8.1 | CSA Rep | Creates “final redline” and “clean” final versions of the Investigator site CTA after all negotiations are complete and all relevant approvals have been obtained. | Startup |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.8.2 |  | Files all applicable email approvals (i.e., Sponsor, PL, CBSL, CTP, etc.) and “final redline” directly in Trial Master File (TMF) or, when applicable, via a Trial Management System workflow process, as appropriate. |  |
| 6.8.3 | CSA Rep | Completes and signs CS_FM_RSU0029, Global Contracting QC Form, as Contract Negotiator (self-reviewing documentation) prior to beginning the signature process. | Startup |

  - Executing the Investigator Site CTA

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.9.1 | CSA Rep | Determines how many wet signature originals must be obtained, if applicable. Note: If wet ink signatures will be required, the number of contracting parties determines the total number of originals to be sent for signature. | Startup |
| 6.9.2 |  | Provides “clean” final versions of the Investigator site CTAs and the signed Global Contracting QC Form to the IQVIA/Sponsor signatory for signature. Note: Although it is preferred that the appropriate IQVIA and/or Sponsor signature is obtained prior to obtaining the signature from the Investigator site, it is acceptable for the IQVIA and/or Sponsor signature to occur after receipt of the signed Investigator site CTA from the Investigator site. |  |
| 6.9.3 |  | Sends the Investigator site CTA to the Sponsor and site for signature, as applicable. |  |
| 6.9.4 |  | Completes the “Post Execution Review & Activities” listed on the Global Contracting QC Form. |  |
| 6.9.5 |  | **CTA Changes Are Required** Takes corrective action to obtain revision or justification until Investigator site CTA is acceptable. Repeats steps 6.9.1 to 6.9.4 for completion of the Global Contracting QC Form. |  |
| 6.9.6 |  | Follows ‘ELVIS -- Processing Clinical Trial Agreements in pre-DIA eTMF projects and in DIA environment and Wingspan – Guidance’ specific to the relevant TMF Sponsor Folder location for the scanning and/or filing directly, or via a contract management workflow system, of the fully executed original Investigator site CTA and Global Contracting QC Form for each site, as applicable. (Refer to Section 7 for link to this Guidance). |  |
| 6.9.7 | CSA Rep | Ensures CTP/Finance is notified/has access to the fully executed Investigator site CTA via system, e-mail or report. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.9.8 | CSA Rep | Sends one fully executed original or copy, as applicable, Investigator site CTA to each contracting party. | Startup |
| 6.9.9 |  | Archives one fully executed original paper copy Investigator site CTA when required by country regulations. |  |
| 6.9.10 |  | Tracks Investigator site CTA in the Trial Management System |  |

  - Amending the CTA Notes:

    - Request sender to resubmit any communication, invoices, or accompanying

documentation if any personal identifying information is included (refer to QCP_CG_IGP0003, Protection of Personally Identifiable Information.)

    - After CSA Rep transfer to Clinical Site Monitoring, the ML and CSA Rep will handle amendments to the Investigator site CTA as described in CS_TP_RSU0013, Site Activation Management Plan In the event Sites send requests directly to PLs, CLs, Monitors, or others for payment of changed or additional services (e.g., reimbursement for costs related to a health fair they are to follow CS_OP_RSU0060 Site Activation,Appendix C Compensation to Healthcare Professionals for Clinical Research Services.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.10.1 | SAM/ML or CSA Rep | Sends a request for Global, Country, or One-off CTA Amendment, Assignment, or Notice Letter Template(s) to the CBSL. Provides a clear explanation and background for the request. | Setup, Startup, Conduct Can occur throughout the project |
| 6.10.2 | CBSL | Determines the appropriate instrument to effect the change (for example, a CTA Amendment, Assignment, or Notice Letter depending on the circumstances). |  |
| 6.10.3 |  | Provides the SAM/ML with the appropriate Global or Country CTA Amendment, Assignment or Notice Letter Template(s), Country Budget Template(s), and/or budget negotiation parameters and instructions, for applicable countries. Note: For One-off CTA Amendment/Assignment/Notice Letter template requests, the CBSL will provide template(s) directly to the requestor. |  |
| 6.10.4 | SAM | Distributes Country CTA Amendment, Assignment, or Notice Letter Template(s), instructions, and budget negotiation parameters to the CSA Rep(s) as appropriate. |  |
| 6.10.5 | CSA Rep | Adds site-specific details to the CTA Amendment, Assignment or Notice Letter Template(s). Negotiates the amendment changes to the Investigator site CTA with the appropriate site(s) as per sections 6.6 through 6.7 of this WI, if negotiation is needed. Note: Some amendments may not require or allow for negotiation. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.10.6 | CSA Rep | Prepares the Investigator site CTA Amendment, Assignment or Notice Letter(s) for review and approval as per subsection 6.8 of this WI. | Setup, Startup, Conduct |
| 6.10.7 |  | Executes the Investigator site CTA Amendment, Assignment or Notice Letter(s) as defined in subsection 6.9 of this WI. | Can occur throughout the project |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 CS_FM_RSU0029 | Global Contracting QC Form |
| 7.2 CS_OP_RSU0060 | Site Activation |
| 7.3 CS_TP_RSU0013 | Site Activation Management Plan |
| 7.4 CS_TP_TMF0059 | Trial Master File (TMF) Memo to File (MTF). |
| 7.5 CS_WI_PL0024 | Project-Specific Training and Team Member Transition |
| 7.6 CS_WI_RSU0021 | Essential Document Pack |
| 7.7 CS_WI_RSU0032 | Translation of Documents |
| 7.8 CS_WI_RSU0067 | Project Lifecycle Clinical Trial Applications |
| 7.9 CS_WI_SM0028 | Investigator Payments |
| 7.10 QCP_CP_IGP0003 | Protection of Personally Identifiable Information |
| 7.11 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| External References |  |
| 7.12 Global Contract Intelligence | Regulatory Intelligence Database: https://quintiles.appiancloud.com/suite/tempo/records/view/all |
| 7.13 ELVIS - Processing Clinical Trial Agreements in pre- DIA eTMF projects and in DIA environment and Wingspan - Guidance | ELVIS User Resources https://elvis.quintiles.com/livelink/llisapi.dll/properties/148871634 |
| 7.14 IQVIA Legal Manual | IQVIA Clinical Trial Agreement Templates – SharePoint |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| CS_WI_RSU0066 | Clinical Trial Agreement and Budget | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Update LRSU Rep to CSA Rep | Throughout | Change in role title |
| Updated cRSU to CSA Protocol Pricing Rep | Section 3.0 and Section 6.2 | Change in role title |
| Changed CBSL to SAM in Who column | Steps 6.3.3 and 6.3.4 | Previously attributed to CBSL in error |
| Combined two bullets into one | Step 6.7.4 | Language clarification |
| moved Note regarding number of originals down to Notes section of Step 6.9.2 | Section 6.9 | Wet Ink signatures are no longer the norm for most countries, so it’s more appropriate to put the information in Step 6.9.2 |
| Changed the words “portion of” to “listed on” | Step 6.9.4 | Modified language to make it clear that the activities are to be completed, but there’s not a portion of the form to also complete |
| Removed PL, CL and local monitoring staff from being responsible for CTA amendments. This is now the ML and the CSA Rep. | Section 6.10, Notes | Process change |
| Added step for SAM/ML or CSA Rep to request templates from CBSL | Step 6.10.1 | Process change |
| Added step for CBSL to determine the appropriate type of amendment document template to use | Step 6.10.2 | Process change |
| Added “or Country” and “Notice Letter Template(s)” and “Instructions” to existing step text | Step 6.10.3 | Process clarification |
| Added “Note” “For One-off CTA Amendment/Assignment/Notice Letter template requests the CBSL will provide template(s) directly to the requestor. | Step 6.10.3 | Process change |
| Deleted step requiring SAM to complete the Country CTA Amendment Template(s) | Previous Step 6.10.4 | Process change |
| Added “Assignment, or Notice Letter” to step text | Step 6.10.3 through Step 6.10.7 | Process clarification |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added task to step “Adds site- specific details to the Amendment, Assignment or Notice Letter Template(s) provided by the SAM/ML” | Previous Step 6.10.6, new Step 6.10.5 | Process change |
| Removed Appendix 10.1 | Section 10.1 | No longer required as it is now located in a local to Japan WI |

- APPENDICES

Not Applicable

Page 15 of 15

Copyright © 2020, 2022 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Trieschmann, Twila (q405536) Title:

Date: Friday, 18 November 2022, 09:24 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Friday, 18 November 2022, 09:25 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Tuesday, 22 November 2022, 08:31 AM Eastern Daylight Time Meaning: Signing this Document Indicates My Approval

================================================