|  | IQVIATM Work Instruction Essential Documents Pack |
| --- | --- |
|  | Document Number and Revision: CS_WI_RSU0021 Revision 2 |
| Document Owner: Mary Beatty | Author(s): Kiril Dinev, Mary Beatty |

# PURPOSE

To outline the requirements and process for the collection and review of the Essential Documents Pack (EDP) from Investigator sites required for Investigational Product (IP) or device release, site initiation, and/or site activation for clinical projects.

# SCOPE

  - This work instruction applies to functional groups involved in the collection and review of the Essential Documents Pack (EDP) required for IP or device release, site initiation, and/or site activation.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Site Activation Manager (SAM) | 6.1, 6.2, 6.3, 6.4 |
| Account Manager, Site Activation (AM SA) | 6.2 |
| Line Manager, Site Activation (LM SA) | 6.2 |
| Local RSU Representative (Local RSU Rep) | 6.4, 6.5, 6.6 |
| Designated/Authorized Approver (DAA)* | 6.6 |

* The Designated/Authorized Approver (DAA) can be the SAM, Local RSU Line Manager, Senior Local RSU Rep, cRSU Rep, or other role identified per country and/or region standard practices but must always be a different person than the person compiling the EDP.

Note: Centralized RSU (cRSU) may be involved in performing and/or coordinating certain activities described in this WI that are not shown as assigned to cRSU. Please refer to CS_OP_RSU0061, Centralized RSU Scope of Activities for more information on activities performed by cRSU.

# DEFINITIONS

Refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services

Essential Documents Pack (EDP): The subset of Essential Documents that IQVIA and the Customer agree must be in place prior to Investigational Product release to a site, Site Initiation Visit and/or Site Activation. The EDP generally consists of the Essential Documents which must be in place according to ICH E6, section 8 (or ISO14155 Annex E for device projects) related to the stage of the trial, supplemented by other relevant project and/or country specific documents to ensure a high quality outcome

“ctms” in lower case letters is used throughout this document to designate any “clinical trial management system”. This includes, but is not limited to, a customer-specific system, @Work-RSU Workflow, and the IQVIA database officially named “Clinical Trial Management System.” When reference is specifically to the IQVIA database named Clinical Trial Management System, the abbreviation used will be “CTMS” in all capital letters.

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

Note: Refer to Appendix A of this WI for an example list of Essential Documents collected for the EDP. A complete EDP varies among countries and projects. Country-specific requirements can be found in the Regulatory Intelligence Database (RID) and in each country’s Local Monitoring Work Instructions. Any additional Sponsor-specific requirements will be captured in CS_FM_RSU0047, Essential Documents Pack – Requirements Form (EDP-RF).

  - Define EDP Requirements

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | SAM | Creates the project-specific EDP requirements using CS_FM_RSU0047, Essential Documents Pack - Requirements Form (EDP-RF). Note: Checks first with the RSU AM, if one is assigned, to confirm whether there is a Sponsor-specific EDP-RF; otherwise, uses the standard, blank EDP-RF to develop a project-specific form. | Start-up |
| 6.1.2 |  | Works with the Clinical Lead (CL) and Sponsor to draft the content of the EDP-RF for the project based on the requirements in CS_TP_RSU0049, Essential Documents Pack – Review Guidelines (EDP-RG). Note: The EDP-RF is already annotated with the IQVIA best practices from the EDP-RG. Any changes from best practices need to be negotiated with the Sponsor, and budget implications need to be assessed. |  |
| 6.1.3 |  | Reviews the EDP-RF with the Sponsor at a meeting to specifically discuss this form |  |
| 6.1.4 |  | Updates and finalizes the EDP-RF, as appropriate, based on the meeting discussion |  |

  - Quality Control (QC) Review of the EDP-RF

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | AM SA, LM SA or | Reviews the EDP-RF to confirm that there are no discrepancies between the information in the body of the EDP-RF and the Hold/Not Hold list at the | Once the EDP-RF is |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  | another SAM | end of the document, then signs and dates the QC section of the EDP-RF and returns the form to the SAM Note: The EDP-RF QC review may be performed by a SAM but must be a different SAM than the one that created the document. | final and ready for Sponsor signature |
| 6.2.2 | SAM | Sends the EDP-RF to the Sponsor for approval and signature |  |

  - Prepare the Project-specific EDP

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | SAM | Reviews, discusses and obtains from the Sponsor any project-specific documents that have to be included in the Essential Documents Pack (EDP) and are required for Investigational Product (IP) or device release, site initiation, and/or site activation. Note: - Refer to CS_OP_RSU0060, Site Activation, for information and processes related to documents to be obtained from Sponsor for the Core Clinical Trial dossier to be used for submission to the Regulatory Authority/Independent Ethics Committee/Institutional Review Board (RA/IEC/IRB) - All project documents that need to be collected from investigational sites must be described in the CS_TP_RSU0013, Regulatory and Start Up Management Plan (RSUMP). | Start-up At External KOM and as EDP-RF is being prepared and finalized |
| 6.3.2 |  | Obtains all project-specific versions of subject recruitment material from the Patient Recruitment Lead (if Global Patient and Site Solutions are involved in creating recruitment materials) or PL/CL (if Sponsor is providing recruitment materials); provides any documents that require a regulatory review to the RAd for review. Refer to CS_OP_RSU0060, Site Activation. |  |
| 6.3.3 |  | Determines, with input from CL/PL or Sponsor, whether the IQVIA or Sponsor templates will be used for any documents or forms that need to be collected/used in the project and signed off by the site and completes any project-specific fields. Template examples include, but are not limited to: - PI CV template CS_FM_RSU0035, Curriculum Vitae - Investigator Site Staff - Financial Disclosure template (refer to CS_WI_RSU0022, Collection of Financial Disclosure Information from Investigator Sites, for more detail) - Investigator’s Brochure (IB) receipt form (CS_TP_RSU0051, Site Receipt of Clinical Trial Documents and Supplies., - CS_FM_RSU0046, Device Statement of Investigator (for projects under a United States (US) Investigational Device Exemption (IDE) application) |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - United States (US) Food and Drug Administration (FDA) Form FDA 1572 (for projects under a US Investigational New Drug (IND) application) or equivalent Investigator Statement (CS_FM_RSU0059, Statement of Investigator). |  |
| 6.3.4 | SAM | Creates the project-specific CS_TP_RSU0050, Essential Documents Pack - Review Checklist (EDP-RC), adding: - Project-specific information to the header - Standard information for all sites (e.g., the Protocol date/version, the IB date/version) - Country- and project-specific information as appropriate Note: Any country-specific information (e.g., requirements for Import licenses, Export licenses) added to the EDP- RC should be sourced from the Regulatory Intelligence Database (RID) and from each country’s Local Monitoring Work Instruction in consultation with the Local RSU Rep. | As the EDP-RF is being finalized |
| 6.3.5 |  | Prepares the project-specific CS_FM_RSU0048, Site Activation Approval Form (SAAF) by adding project-specific information to the header; for projects with sites in the US, completes the FDA Submission Date field in Section II (refer to Notes below). Notes: - The EDP-RC and the SAAF cannot be considered final until the EDP- RF is final. - For projects with sites in the US, if the Protocol has not been submitted to the FDA at the time the SAM is first preparing the project-specific SAAF, the FDA Submission Date field may be left blank; however, the SAM or CL must confirm that the Protocol has been submitted and must complete the FDA Submission Date field in Section II before IP can be released to the first site in the US. |  |

  - Distribute the Project-specific EDP and Forms to the Project Team

Note: Once the project is out of start up, if additional sites or countries are added and no SAM is assigned the CL is responsible for performing the applicable tasks in Section 6.4 and 6.6 that are assigned to the SAM”

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | SAM | - Provides the final versions of the project-specific EDP-RF, EDP-RC, and SAAF to the CL and the Local RSU Rep and uploads them in eTraining (refer to to CS_WI_PL0024, Project-Specific Training). Notes: - During Start-up, the SAM must notify the Local RSU Rep immediately, | Start-up |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | in writing, of any change to project-related procedures/requirements that can influence document review using the EDP-RF. - The EDP-RF, EDP-RC, and RSUMP must be updated by the SAM in a timely fashion, forwarded to the project team and uploaded in eTraining. |  |
| 6.4.2 | SAM | Provides the project-specific documents to be sent to the sites, Regulatory Authorities, and EC/IRBs to the Local RSU Rep (refer to steps 6.3.1 – 6.3.5 of this WI) | Start-up |
| 6.4.3 |  | Distributes and coordinates country adaptations and translations of project- specific recruitment materials with the Local RSU Rep after RAd review, if applicable (refer to step 6.3.2) |  |
| 6.4.4 |  | In case there are deviations from standard IQVIA process and upon discretion of the SAM training session(s) may be conducted on the EDP compilation and review process for the Local RSU Rep responsible for those tasks at the country-level. Notes: - Training is focused only on Sponsor- and Protocol-specific requirements for the project rather than normal RSU responsibilities. - The training must be uploaded to eTraining and acknowledged by project team members responsible for EDP compilation and review. - cRSU Reps may receive the training either by participating in the meeting or by reviewing the recorded training session. Training will be documented by self-reporting in Learning Curve. |  |
| 6.4.5 |  | Files the final project-specific versions of the EDP-RF, EDP-RC, and SAAF documents, and information on any other Sponsor-specific requirements, in the Trial Master File (TMF) |  |

  - Adapt the Project-specific EDP and Forms for Country and/or Investigator Site Requirements

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | Local RSU Rep | Reviews project-specific documents and forms against country-specific requirements and contacts the SAM to notify the Sponsor of any country- specific discrepancies Note: Sponsor confirmation or approval in writing is needed to allow country-specific discrepancies (e.g., EDP-RF states that GCP certification must be valid within two years but country requirements permit a longer period of being valid). | Start-up |
| 6.5.2 | Local RSU Rep | Adds any country- or site-specific information to the appropriate sections of the project-specific templates before sending to site for further completion and sign-off, where needed | Start-up |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Notes: - The Local RSU Rep must not make any modifications to the template text of the project-specific templates (refer to step 6.3.3 of this WI) without agreement from the SAM. - Any additional country-required documents for which the SAM does not provide a template are generated by the Local RSU Rep of that respective country and sent to SAM for Sponsor approval, if necessary (e.g., site- or country- specific recruitment materials). |  |
| 6.5.3 |  | Arranges for translations of project-specific documents or templates, if needed before submission to Regulatory Authorities, EC/IRB, or sites, per CS_WI_RSU0032, Translation of Documents. Note: Refer to CS_WI_SPN0006, Patient Recruitment Material Translation Process, for the process for the translation of patient recruitment and retention materials created by or on behalf of Global Patient and Site Solutions (GPPS), including materials created by the Sponsor where GPPS is solely managing the translation. |  |
| 6.5.4 |  | Submits country-specific applications to Regulatory Authorities (RA) and/or Central EC/IRB, if required. Refer toCS_OP_RSU0060, Site Activation. |  |
| 6.5.5 |  | Tracks any country-required documents that are submitted to RA/EC/IRB in ctms |  |

  - EDP Compilation, Review, and Approval

Note: Signatures can be either electronic or wet signature per CS_WI_RM0278, Managing Wet Ink Signature and Mandatory Retention Documents or IQVIA Electronic Trial Master File (eTMF) (Wingspan) Management CS_WI_RM0302, eTMF (Wingspan), or ELVIS Guidances (ELVIS QRG09, Electronic Signing for Initiator or ELVIS QRG10, Electronic Signing for Signatory), as applicable. Electronic signatures are preferable, when possible.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | Local RSU Rep | Provides project-specific documents and templates to Investigator site(s) with instructions to complete templates to meet regulatory requirements and Sponsor expectations | Start-up after project- / country- specific documents are available |
| 6.6.2 | Local RSU Rep | Collects all Essential Documents as listed in the RSUMP from the Investigator site and reviews the documents per the EDP-RF and EDP- RG, then performs one of these actions: - If documents are acceptable, proceeds to step 6.6.4 - If documents are not acceptable, proceeds to step 6.6.3 | Ongoing from the start of project activities |
| 6.6.3 |  | Works with the site to correct or replace any documents that do not meet |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | requirements of the EDP-RF or EDP-RG, then proceeds to step 6.6.4 |  |
| 6.6.4 |  | Checks the QA status of each Investigator and Account(s) associated with the study in CTMS and marks the status on the EDP-RC |  |
| 6.6.5 |  | Performs one of these actions: - If an Investigator and/or an Account has a derogatory QA status in CTMS, escalates this issue to the SAM and CL, then proceeds to step 6.6.6 - If an Investigator and/or an Account has an acceptable QA status in CTMS, proceeds to step 6.6.7 |  |
| 6.6.6 |  | Refers to CS_OP_QA0232, Investigator Compliance Status and Management of Investigators with Non-Compliance Issues for guidance. Consults with the SAM and CL to determine whether the Investigator/Account will remain part of the project, and then performs one of these actions: - If the determination is to continue with this Investigator/Account, includes documentation with the EDP that the consultation has made that determination, and then proceeds to step 6.6.7 - If the determination is not to continue with this Investigator/Account, the CL determines how the information will be communicated to the Investigator in consultation with the SAM and Sponsor Note: The Local RSU Rep must not communicate any information about replacing the Investigator/Account or dropping the site without written instruction from the CL or Sponsor. |  |
| 6.6.7 |  | Prepares the EDP for review and approval | Prior to submitting EDP for review |
| 6.6.8 |  | Conducts a QC check of the final package using the EDP-RF and EDP- RG. Note: If the site provides any site generated patient recruitment materials (if allowed by the sponsor -- see the EDP-RF) these will need to be reviewed using CS_TP_RSU0034, Regulatory Review Checklist for Subject Recruitment Material before being included in the EDP. |  |
| 6.6.9 |  | Confirms the currency and/or expiration dates of documents. |  |
| 6.6.10 |  | Completes the EDP-RC with all required information and completes the Compiler field on the last page of the EDP-RC. |  |
| 6.6.11 | Local RSU Rep | Completes the first page of the SAAF with required Country/Site details. | Prior to submitting EDP for review |
| 6.6.12 |  | Performs one of these actions: - If this is a final EDP, submits the EDP to the DAA with the EDP-RC | Within two working days of receipt of |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | and SAAF in Word format. - If this is a partial EDP, notes the currency and/or expiration date of documents (e.g., CV, lab certification) for future reference prior to submitting the partial EDP to the DAA with the EDP-RC. Notes: - It is acceptable to request a review for a partial EDP that is missing one or two mandatory documents (e.g., signed contract, financial disclosure), if the missing mandatory documents will be available within one month of the initial review. - When the final EDP is sent to the DAA after a partial EDP has been reviewed, the SAAF must be included in Word format, along with the corrected or added documents, new version of the EDP-RC and the earlier versions of the EDP-RC | final document |
| 6.6.13 | DAA | Reviews and QCs the EDP against the requirements in the EDP-RF and EDP-RG, taking into consideration the scheduled dates for Site Initiation Visits (SIVs) Note: The SAM may perform the review and approval of the first EDP issued for each participating country, under some circumstances. If this is a requirement for the project, it must be documented in the RSUMP | Within three working days of receipt of final documents |
| 6.6.14 |  | Completes the Approver section on the EDP-RC, then performs one of these actions: - If all mandatory documents are present and correct and the EDP-RC is completed correctly, proceeds to step 6.6.18 - If mandatory documents are missing or require correction, proceeds to step 6.6.15 Notes: - It is acceptable to perform review for a partial EDP that is missing one or two mandatory documents (e.g., signed contract, financial disclosure) if the missing mandatory documents will be available within one month of the initial review. - The EDP must not be approved under any circumstances on the promise that updated or missing mandatory documents will follow. All mandatory documents must be available at the time of EDP approval. |  |
| 6.6.15 | DAA | Sends the completed and signed EDP-RC back to the Local RSU Rep with status “not approved” and describes the needed corrections or missing documents | Upon completion of review |
| 6.6.16 | Local RSU Rep | Updates the EDP as necessary, creates a new EDP-RC, entering the new version number and new submission date of the EDP in the document header. Repeats steps 6.6.8 through 6.6.12 | If EDP is not approved |
| 6.6.17 | DAA | Reviews only the documents in the updated EDP that were previously | Within three |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | inaccurate or missing, and confirms that the new version number and submission date of the EDP have been included in the document header; repeats steps 6.6.13 through 6.6.15 until the EDP is correct and ready for approval, then proceeds to step 6.6.18 | working days of receipt of final documents |
| 6.6.18 |  | Completes and signs the EDP-RC with status “approved without actions” or “approved with actions” to confirm that the EDP is approved. | Upon approval of EDP |
| 6.6.19 |  | Notifies the Local RSU Rep of the approval, and provides a copy of the signed EDP-RC to the Local RSU Rep and SAM together with the pre- completed Word version of the SAAF (previously provided by the Local RSU Rep in step 6.6.12) Note: When the final review/approval is performed by a DAA other than a cRSU Rep, the Local RSU Rep (the Compiler) is responsible for ensuring that a copy of the EDP-RC and the pre-completed Word version of the SAAF are provided to the SAM. |  |
| 6.6.20 | Local RSU Rep | Updates the CTMS Site Status to ‘Essential Documents in Place’ |  |
| 6.6.21 |  | Confirms that all documents have been tracked in ctms and are filed in the Trial Master File (TMF) as per CS_OP_RM0296, Management of Trial Master File. Note: Even if filing to the TMF is delegated to another role (e.g. cRSU Rep), the Local RSU Rep remains accountable for ensuring the documents have been filed appropriately in the TMF. |  |
| 6.6.22 |  | Provides site documents and information to the Monitor. Refer to CS_OP_RSU0060, Site Activation. |  |

  - Investigator Site Initiation and Activation

Details regarding preparation for the Site Initiation Visit and site activation are found in CS_OP_RSU0060, Site Activation, CS_WI_SM0005 Monitoring Visits, and CS_WI_SM0027 Provision of Clinical Project Supplies and Equipment to Investigator Sites.

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |
| 7.2 CS_OP_RSU0060 | Site Activation |
| 7.3 CS_FM_RSU0035 | Curriculum Vitae - Investigator Site Staff |
| 7.4 CS_FM_RSU0046 | Device Statement of Investigator |

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| 7.5 CS_FM_RSU0047 | Essential Documents Pack - Requirements Form |
| 7.6 CS_FM_RSU0059 | Statement of Investigator |
| 7.7 CS_FM_RSU0048 | Site Activation Approval Form |
| 7.8 CS_OP_QA0232 | Investigator Compliance Status and Management of Investigators with Non-Compliance Issues |
| 7.9 CS_TP_RSU0013 | Regulatory and Start Up Management Plan |
| 7.10 CS_TP_RSU0034 | Regulatory Review Checklist for Subject Recruitment Material |
| 7.11 CS_TP_RSU0049 | Essential Documents Pack – Review Guidelines |
| 7.12 CS_TP_RSU0050 | Essential Documents Pack – Review Checklist |
| 7.13 CS_TP_RSU0051 | Site Receipt of Clinical Trial Documents and Supplies |
| 7.14 CS_WI_RSU0022 | Collection of Financial Disclosure Information from Investigator Sites |
| 7.15 CS_WI_RSU0032 | Translation of Documents |
| 7.16 CS_WI_RM0302 | IQVIA Electronic Trial Master File (eTMF) (Wingspan) Management |
| 7.17 CS_WI_PL0024 | Project-Specific Training |
| 7.18 CS_WI_RM0278 | Managing Wet Ink Signature and Mandatory Retention Documents |
| 7.19 CS_OP_RM0296 | Management of Trial Master File. |
| 7.20 CS_WI_SM0005 | Monitoring Visits |
| 7.21 CS_WI_SM0027 | Provision of Clinical Project Supplies and Equipment to Investigator Sites |
| 7.22 CS_OP_RSU0061 | Centralized RSU Scope of Activities |
| 7.23 CS_WI_SPN0006 | Patient Recruitment Material Translation Process |
| External References |  |
| 7.24 ELVIS QRG09 | Electronic Signing for Initiator |
| 7.25 ELVIS QRG10 | Electronic Signing for Signatory |
| 7.26 https://www.fda.gov/ab out-fda/reports- manuals-forms/forms | US FDA Forms |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_RSU0021 | Essential Documents Pack | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Updated Quintiles and QuintilesIMS to IQVIA | Throughout document | Company name change |
| Updated RSUL to SAM | Throughout document | Change in role title |
| Updated roles of RSUL LM and RSU AM | 3.0 and throughout document | Due to title changes, have corrected “RSU AM” to “Account Manager Site Activation” (AM SA) and RSU LM to “Line Manager Site Activation” (LM SA) |
| Updated SOP numbers and titles as needed | Throughout document and in 7.0 | Ensuring current SOPs and Work Instructions are appropriately referenced. |
| Removed references to obsolete SOPs | Throughout document | Obsolete SOPs are no longer relevant |
| Changed text of note regarding cRSU involvement in tasks in this work instruction | 3.0 | To make information clear and to reference new cRSU SOP |
| Added note regarding use of “ctms” versus “CTMS” | 4.0 | To ensure all IQVIA Tracking Systems are referenced in the work instruction |
| Removed reference to Site Activation from Section title and step | 6.1 and 6.1.2 | The SOP focuses on the Essential Documents Pack. Site Activation is addressed in a separate work instruction |
| Moved reference to the submission documents for the RA into the Note, and added cross reference to appropriate work instruction | 6.3.1 | This SOP is focused on the Essential Documents Pack, another work instruction is used for submissions to RA. |
| Changed Site & Patient Networks to Global Patient and Site Solutions | 6.3.2 | Change in department name |
| Removed reference to the PL and CL roles from the “Who” column | 6.3 and 6.6 | More appropriate to include the consultation with the PL and CL in the “Step” column |
| Added reference to new form | 6.3.3 | CS_FM_RSU0059, Statement of Investigator is newly released form |
| Added instruction to upload EDP-RF, EDP-RC and SAAF to eTraining | 6.4.1 | To ensure that the documents are available to the team members that need them, and updates are acknowledged |
| Corrected errors in cross references to step numbers | 6.4.2, 6.4.3, and 6.5.2 | Steps were incorrectly cross-referenced in past. |
| Modified text to remove requirement for a training session for every project | 6.4.4 | Training sessions are not needed for most studies. |

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Added Note to refer to Patient Recruitment Material Translation Process | 6.5.3 | New SOP that is specific to Patient Recruitment material |
| Updated QA Status references to include Account QA Status as well as Investigator QA Status | 6.6.4 and 6.6.5 | Change to process to add check of Account QA Status. |
| Added text to make clear that it is a requirement to provide earlier versions of the EDP- RC with each review | 6.6.12 Notes | All previous versions of the EDP-RC must be provided to the reviewer for the final review/approval step. |
| Clarified that the EDP-RC can be marked as “approved with action” or “approved without action” but in both cases the outcome of EDP review is “Approved” | 6.6.18 | Internal review found that this was not clearly stated previously |
| Removed requirement to provide SAAF to CL | 6.6.19 | SAAF is now signed by the SAM |
| Added reminder of who is accountable for TMF filing | 6.6.21 | clarification |

- APPENDICES

  - Appendix A: Example List of Essential Documents Collected for the EDP

Appendix A: Example List of Essential Documents Collected for the EDP

Note: A complete Essential Document Pack varies among countries. Country- specific requirements can be found in the Regulatory Intelligence Database and in each country’s Local Monitoring Work Instructions.

    - Country Regulatory Approval letter (if applicable)

    - IEC/IRB Approval letter

    - IEC/IRB Composition

    - IEC/IRB Statement of GCP Compliance

    - Signed Clinical Trial Agreement

    - Signed Protocol Signature page

    - Signed Investigator Brochure Receipt form (if applicable)

    - Form FDA 1572 (or equivalent Investigator statement)

    - Financial Disclosure information from Principal Investigator (PI) and Sub- Investigators

    - Curriculum Vitae (CV) of PI and Sub-Investigators

    - Medical License of PI and Sub-Investigators

    - Good Clinical Practice (GCP) Training documentation for PI and Sub- Investigators

    - Informed Consent Form (ICF) and Assent Form (if applicable)

    - Advertisements and subject materials

    - Laboratory information

Page 13 of 13

Copyright © 2017, 2019 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Trieschmann, Twila (q405536) Title:

Date: Tuesday, 30 July 2019, 02:30 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================