|  | IQVIATM Work Instruction Project Lifecycle Clinical Trial Applications |
| --- | --- |
|  | Document Number and Revision: CS_WI_RSU0067 Revision 2 |
| Document Owner: Mary Beatty | Author(s): Chris Bamford, Mary Beatty, Andrius Leonavicius Zubin Thacker, Trevor Walker, |

# PURPOSE

  - To describe the process for preparing and submitting Clinical Trial Applications.

# SCOPE

  - This Work Instruction (WI) applies to functional groups involved in Clinical Trial Application (CT Application) activities through the project lifecycle.

# ROLES AND RESPONSIBILITIES

The following roles perform tasks described within this WI:

| Role | Sections |
| --- | --- |
| Site Activation Manager (SAM) | 6.1, 6.2, 6.3, 6.4, 6.6 |
| Regulatory Advisor (RAd) | 6.1, 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 |
| Local Regulatory and Start-up Representative (LRSU Rep) | 6.1, 6.3, 6.4, 6.5, 6.6, 6.7 |
| Clinical Lead (CL) | 6.2, 6.3, 6.4, 6.5, 6.6, 6.7 |
| Centralized Regulatory and Start Up Representative (cRSU Rep) | 6.3 |
| Maintenance Lead (ML) | 6.2, 6.3, 6.4, 6.6, 6.7 |
| Project Leader (PL) | 6.5 |
| Centralized Monitoring Lead (CML) | 6.6, 6.7 |

Notes:

    - In some countries, the Regulatory and Start-up (RSU) activities may be performed by staff in the Regulatory Affairs (RA) group, the Site Start-Up (SSU) group, or by different roles within RSU. In addition, some RSU responsibilities may be performed by Monitors. All these groups will have the same responsibilities as described in this WI.

    - Where a single country project is in place, the LRSU Rep performs tasks that are assigned to the SAM or RAd in this WI. The Country Quality Control (QC) Checklist should be completed and reviewed by the CL to ensure all required documents are enclosed.

    - For clinical studies conducted under the European Union (EU) Clinical Trial Regulation (CTR) the RAd will take responsibility for submission-related tasks in countries where EU CTR is applicable. The RAd will retain such responsibilities throughout the lifecycle of the study (Lifecycle Maintenance) in these cases. Where listed in Section 6.0, the “RAd (EU CTR)” role indicates that the RAd will be responsible for the described process steps in all countries where EU CTR is applicable, and the other roles described will be responsible for the stated tasks in countries where EU CTR is not applicable.

    - For projects occurring only in Asia Pacific, the SAM performs tasks by coordinating directly with LRSU due to the absence of the RAd role.

    - Where no SAM is assigned (small project), the CL performs the tasks assigned to SAM.

    - Where SAM/ML/CL is indicated, the SAM is primarily assigned during study Start-up and ML is assigned during Lifecycle Maintenance. If neither a SAM nor ML is assigned, the CL performs the tasks assigned to these roles.

# DEFINITIONS

Refer to QG_OD_SMT0018, Glossary of Terms – Clinical Services

Electronic Signatures: All signatures applied must be in accordance with IQVIA validated signature procedures. Signatures can be either electronic or wet signature. Electronic signatures are preferable, when possible and should be applied using the appropriate Trial Master File (TMF) platform or validated eSignature solution.

QC Checklists: Where Core QC Checklist is referenced, refer to CS_TP_RSU0024, Global QC Checklist for Clinical Trial Submission Documents. Where Country QC Checklist is referenced, refer to CS_TP_RSU0025, Country QC Checklist for Clinical Trial Submission Documents.

Trial Management System: When referencing “Trial Management System” throughout this work instruction, this infers tracking directly into CTMS or other IQVIA trial management systems.

CTIS (Clinical Trials Information System): A dedicated EU Portal and Database for submitting information and management of clinical study business processes throughout lifecycle for studies conducted under EU CTR.

Redaction: The irreversible obscuring of text within a document with the aim of rendering the document appropriate for future publication within an online clinical study registry. Such redaction must utilize a software application that is either validated by IQVIA or industry- standard for the purpose (eg. Adobe Acrobat Professional).

# MATERIAL AND EQUIPMENT

Not Applicable

# PROCEDURE

  - Regulatory and Ethics Committee Submission

Decisions regarding submission strategy, such as those relating to use of country level or EU CTR processes will be documented in CS_TP_RSU0013, Site Activation Management Plan (SAMP).

This section of the WI describes initial Regulatory Authority, Independent Ethics Committee, Independent Review Board (RA/IEC/IRB) submissions and/or relevant Competent Authority (e.g., radiation committees, biobanks, etc.) relevant for Site

Activation requirements, if IQVIA is contracted on behalf of a Sponsor. Refer to Section

6.3 for management of amendments and maintenance submissions.

Note: Each role mentioned in this work instruction is responsible to:

- Ensure tracking, status reporting, risk/issue identification and mitigation of activities to support site activation in applicable systems as per CS_OP_RSU0060, Site Activation.

- File individual documents or pertinent correspondence in the Trial Master File as they are finalized as per CS_OP_RSU0060.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.1 | SAM/RAd (EU CTR) | Gathers Regulatory Intelligence on Submission Document Requirements (SDR) for the Project and on Submission Strategy Collates, with the RAd and LRSU Rep (as required), the core and country-specific submission document requirements from the Regulatory Intelligence Database (RID) taking into consideration the indication, subject population, Protocol design, Investigational Product (IP) involved, and the type of submission if different options are available either by region or by country. Notes: - SAM performs for non-EU CTR countries, RAd for EU CTR countries. - The SAMP and list of countries are finalized at or soon after the project kick-off meeting. The documents provided by the Sponsor may vary per project based on which core documents the Sponsor has taken direct responsibility for as defined by the Scope of Work (SoW), Table of Regulatory Responsibilities (TRR) and listed in the SDR. These documents may include, but are not limited to: Protocol, Investigator’s Brochure, Investigational Medicinal Product Dossier (IMPD), recruitment materials, etc. | Following SAMP and country list finalization |
| 6.1.2 | SAM | Prepares the TRR Completes CS_TP_RSU0023, Table of Regulatory Responsibilities (or a sponsor template, if applicable) with input from the RAd. The first version of the TRR must be approved before the first submission that IQVIA performs outside the United States (US). Notes: - Each approved version of the TRR is made available to the LRSU Rep through project eTraining. - The TRR identifies the regulatory responsibilities of IQVIA and the Sponsor for a clinical project for all countries EXCEPT the US. - For projects conducted under a US Investigational New Drug application (IND), a Transfer of Regulatory Obligations (TORO) will be prepared as part of the finalization of the project work order. | IQVIA is contracted to perform RA/IEC/IRB and/or relevant Competent Authority (e.g., radiation committees, biobanks, etc.) submissions on behalf of a Sponsor |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Refer to CS_WI_RSU0009, Transfer of Regulatory Obligations. There is no requirement for the TORO to be in place before project work can begin. - For Japan-only projects, the TRR is not used – the SoW provides sufficient detail to define the regulatory responsibilities of IQVIA and the Sponsor. |  |
| 6.1.3 | SAM | - Defines the Essential Documents required for the study in accordance with CS_WI_RSU0021, Essential Documents Pack,(EDP), using CS_FM_RSU0047, Essential Documents Pack – Requirements Form, (EDP-RF). Liaises with LRSU Rep to verify that country-specific requirements are included in the EDP-RF. - Verifies that all identified EDP and submission requirements are accounted for and included in the project-specific SAMP. | Startup |
| 6.1.4 |  | Shares EDP-RF and SAMP versions as they are developed with relevant LRSU Rep(s). | Following EDP- RF finalization |
| 6.1.5 |  | Defines and summarizes the study-specific criteria required for Site Activation and Site Ready to Enroll (SrtE), refer to CS_WI_RSU0068, Site Ready to Enroll Execution and Oversight, in consultation with the CL, PL, Project Vendor Manager (PVM – if assigned) and Sponsor. |  |
| 6.1.6 | SAM/LRSU Rep/ML | Coordinates Submission to Sponsor of United States (US) Food and Drug Administration (FDA) Investigational New Drug (IND) Investigator Information Package - Provides initial US IND Investigator Information Package to the Sponsor or Sponsor’s delegate for sites in all countries that are subject to IND regulations. - The US FDA IND Investigator Information Package at minimum consists of the Principal Investigator’s (PI) Curriculum Vitae (CV) and the signed Form FDA 1572. Other documents may be included per Sponsor requirements. Notes: - If a representative from IQVIA’s Global Regulatory Affairs (GRA) department is the US Agent for the Sponsor, the SAM must work with the GRA Representative to establish a process for submission and document that process in the SAMP. - ML manages the submission of revised US FDA IND Investigator Information Packages, including PI change at a site, during Lifecycle Maintenance | Startup and Conduct, when study is under a US FDA IND |
| 6.1.7 | SAM | Obtains CT Application Dossier Documents - Obtains the required documents for the Core CT Application Dossier that are being provided directly from the Sponsor or Sponsor’s delegate. Refer to Appendix A for a sample list of Core Dossier requirements. | Startup or upon amendment |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Tracks receipt of the Core Submission documents in the applicable Trial Management System and files the documents or ensures first IQVIA recipient files in the appropriate location in the TMF upon receipt to avoid duplication of filing. |  |
| 6.1.8 | RAd | Prepares and Finalizes Country/Region-Specific Delegation Letters - Prepares Delegation Letters for all countries as applicable in collaboration with SAM, PL, and LRSU Rep using the SoW. - Prepares instructions for finalization (number of copies, originals, notarization, apostilles) per country/region and sends to Sponsor. - Ensures finalized delegation letters are forwarded to appropriate LRSU Rep for submission and TMF filing. | Startup after country list finalization |
| 6.1.9 | RAd (EU CTR) | - Requests the number required for initiation of an EU CT Application (or works with Sponsor, per agreed scope). - Establishes appropriate access to the EU CTIS, where required, for studies being conducted under the EU CTR. - Oversees provision of study specific access to other IQVIA users who require access, per clinical study submission scope. | While draft Core CT application is being prepared |
| 6.1.10 | RAd | Compiles and Finalizes Core CT Application Dossier - Reviews IP Labels in accordance with CS_WI_RSU0019, Investigational Product Label Review. - Reviews the master Informed Consent Form (ICF) in accordance with CS_WI_RSU0033, Creation and Review of the Informed Consent Form. - Reviews subject recruitment documents if not developed by IQVIA, as applicable, according to CS_TP_RSU0034, Regulatory Review Checklist for Subject Recruitment Material. - Performs a review of the Core CT Application Dossier documents as discussed in the expectation meeting and/or as noted in SoW/SAMP (i.e., technical review of Protocol, Investigator’s Brochure (IB) and IMPD or content review to support the study and Investigational Product)). - Completes appropriate checklists to document the reviews of Protocol, IB and IMPD. Documents the review on the Core QC Checklist. | Startup |
| 6.1.11 |  | - Prepares (or reviews if prepared by the Sponsor) the Core EudraCT CT Application Form, and validates the prepared or updated Core EudraCT CT Application Form using the validation function on the EudraCT website. - Obtains Sponsor review and approval. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | Note: This applies only for studies involving countries in the European Economic Area (EEA) but where the EU CTR is not yet applicable (i.e. during the EU CTR transition period), |  |
| 6.1.12 | RAd | Redaction of Core Documents - Identifies any personal or commercially confidential information within the Core documents that is considered acceptable to Redact, per applicable regulatory requirements and/or guidelines (eg. European Medicines Agency guidance on transparency relating to clinical studies) and considering any Sponsor-specific agreement described in the SAMP. An example of standard expectations for redaction of personal information in the European Union (EU) is included in Redaction Guidance and Tools (refer to 7.19 in this WI). - Prepares the draft redacted Core clinical document(s) in an appropriate version of applicable software (eg. Adobe Acrobat Professional) using a ‘Mark for Redaction’ tool ensuring that all information to be redacted is still visible. Unless expectations are already clearly documented in the SAMP, a Sponsor review should be completed for each redaction performed on a Core clinical study document. - Applies full redaction, following Sponsor confirmation of acceptability of the planned redaction. Note: The redacted and non-redacted versions of all documents must be retained and filed in the TMF. | Startup |
| 6.1.13 |  | - Compiles the Core CT Application Dossier and obtains a completed QC review of the Core Dossier with the assigned SAM reviewer to verify the accuracy and completeness of the dossier (refer to the Core QC Checklist) before the first RA/IEC/IRB submission IQVIA performs. - Obtains Sponsor-level approval of the Core Dossier in consultation with SAM, if required per Sponsor specifications. - Finalizes the Core CT Application Dossier. |  |
| 6.1.14 |  | For studies performed under EU CTR - submits Part I CT Application Dossier - Prepares Part I CT Application in the CTIS, by upload of Core documents and finalization of information included within the EU CT Application Form on the CTIS. - Validates the completed Part I CT Application dossier, including all previously reviewed Core documents and the EU CT Application form, using the validation function within the CTIS system. - Where translations of documentation (or information from within documents) is necessary, coordinates with LRSU Rep to obtain such translations, per step 6.1.18. | EU CTR applies and Following Final Core CT Application Dossier |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Conducts or facilitates any additional Sponsor review activities as described in the SAMP. - Utilizes the information within the Core QC Checklist to prepare a Part I-specific QC checklist, describing all final documents uploaded and planned for submission (equivalent to a Country-level submission QC review). - Submits the Part I CT Application dossier upon completion of required QC review. Notes: - In parallel to the Part I CT Application dossier preparation the RAd is also required to coordinate Part II, country-level submission planning and conduct, to ensure steps performed per steps 6.1.18- 6.1.21 are performed efficiently, and submissions can proceed in parallel or sequentially, as planned. - Proceed to step 6.1.21 for monitoring of submissions in countries where EU CTR is not applicable. |  |
| 6.1.15 | RAd | For studies performed under EU CTR - Monitors the Part 1 assessment status routinely - Facilitates and coordinates, in consultation with the SAM, PL and Sponsor, the resolution and submission of responses to questions or corrections requested by the Reporting Member State (rMS). - Documents verbal discussions and decision points with the rMS using CS_FM_RSU0015, Regulatory Authority, Institutional Review Board and Ethics Committee Contact Form, if applicable. - If conditional approval is provided by the rMS, verifies that all conditions are addressed and resubmits documentation, as requested. - If approved, notifies relevant stakeholders of the approval status and updates the applicable Trial Management System. - If rejected, notifies relevant stakeholders of the rejection status and liaises with the SAM, PL and Sponsor on follow up actions. | Throughout Activation Process |
| 6.1.16 | LRSU Rep / SAM | Prepares the Country/Site CT Application Dossier - Creates and where appropriate, obtains the required documents for the Country/Site CT Application Dossier, EDP and any other supporting documents, that are being provided directly from the Investigator site(s). - Tracks receipt of the Country/Site Submission documents in relevant systems and files the documents in the appropriate location in the TMF upon receipt. - Compiles the Country/Site CT Application Dossier for submission to RA/IEC/IRB in accordance with Core CT Application Dossier, local | Following final Core CT Application Dossier |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | regulatory requirements, local Clinical Monitoring WIs, and the project-specific SAMP. - Uploads documents to the CTIS to compile the Part II dossier on CTIS prior to review of dossier quality and submission, if the project involves countries where the EU CTR is applicable. - For studies involving countries in the EEA but where the EU CTR is not yet applicable (i.e. during the EU CTR transition period), adds country-specific information to the Core EudraCT CT Application Form, and validates the updated EudraCT CT Application Form using the validation function on the EudraCT website. Note: The SAM will be the principle lead role supporting and coordinating LRSU with respect to CT Applications in countries where EU CTR is not applicable, and the RAd will be the principle lead role supporting and coordinating LRSU with respect to CT Applications in countries where EU CTR is applicable. |  |
| 6.1.17 | LRSU Rep | This step is applicable for EU/EEA countries in studies conducted under EU CTR. Redaction of Country/Site documents. - Identifies any personal or commercially confidential information within country specific documents that is considered acceptable to Redact, per applicable regulatory requirements and/or guidelines (e.g. European Medicines Agency guidance on transparency relating to clinical studies) and considering any Sponsor-specific agreement described in the SAMP. An example of standard expectations for redaction of personal information in the European Union (EU) is included in Redaction Guidance and Tools (refer to 7.19 in this WI). - Prepares the draft redacted clinical document(s) in an appropriate version of applicable software (eg. Adobe Acrobat Professional) using a ‘Mark for Redaction’ tool, ensuring that all information to be redacted is still visible. Unless expectations are already clearly documented in the SAMP, a Sponsor review should be completed for the first example of each type of redaction performed on a country or site-level submission document for each project (e.g. the first instance of redaction of an Investigator signature from within a CV). - Applies full redaction following Sponsor confirmation of acceptability of the planned redaction. Note: The redacted and non-redacted versions of all documents must be retained and filed in the TMF. | During compilation of Country CT Application Dossier |
| 6.1.18 | LRSU Rep | Translates documents, as required, in accordance with CS_WI_RSU0032, Translation of Documents. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.1.19 |  | Verifies Country/Site CT Application Dossier Quality - Ensures a QC review of the Country/Site CT Application Dossier is completed (when IQVIA is responsible for the submission to the RA/IEC/IRB) by an independent LRSU Rep reviewer to verify - the accuracy and completeness of the dossier - the completeness of redaction of personal information in countries/regions where documents will be published in future (refer to step 6.1.17) - Any deviation should be recorded in accordance with country specific WI. - Obtains Sponsor-level approval of the dossier in consultation with the SAM/RAd (EU CTR), if required per Sponsor specifications. Note: QC of submission dossier is required for all applications including those that are completed under EU CTR as a Part II application of national level documentation. | Prior to the submission of the Country/Site CT Application Dossier, at the final stage of preparation of the dossier (e.g. after upload of final documents to CTIS for submissions under EU CTR) |
| 6.1.20 | LRSU Rep / SAM | Submits Country/Site CT Application Dossier - Verifies that all local submission fees are paid and submits Country/Site CT Application Dossier to the relevant RA/IEC/IRB for approval. Provides the relevant documents to site representatives for submission, if sites are required to submit documents to the EC directly. - Completes the submission of Part II dossier in CTIS, if the study involves countries where the EU CTR is applicable. | After QC of Country/Site CT Application Dossier |
| 6.1.21 | LRSU Rep | - Monitors the Country/Site assessment status routinely. - Monitors the “Request for Information” (RFI) receipt for Part II dossier (e.g. questions from RA/EC), if the study involves countries where the EU CTR is applicable, - Facilitates, in consultation with the SAM, RAd, PL and Sponsor, the resolution and submission of responses to questions or corrections requested by the RA/IEC/IRB - Uploads response documents to CTIS, and completes the submission of responses in CTIS, If the study involves countries where EU CTR is applicable. - Documents verbal discussions and decision points with RA/IEC/IRB using CS_FM_RSU0015, Regulatory Authority, Institutional Review Board and Ethics Committee Contact Form, if applicable. - If conditional approval is provided by the RA/IEC/IRB, verifies that all conditions are addressed and resubmits documentation, as requested, within one working day of receipt of conditional approval. | Throughout Site Activation Process |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - If approved, notifies relevant stakeholders of the approval status and updates the Trial Management System with approval date(s) within one working day of receipt of approval. - If rejected, notifies relevant stakeholders of the rejection status and liaises with the SAM, RAd and Sponsor on follow up actions. - When required, translates approval documentation and RA/IEC/IRB correspondence per CS_WI_RSU0032, Translation of Documents. - Completes any post-approval activities (e.g., notifications, registrations to national clinical study registries), notifies the SAM/CL/PL, and tracks in the applicable Trial Management System. - Ensures all documents are filed in the TMF upon receipt (files directly or via Trial Management System workflow process when applicable). |  |

  - Addition of New Countries during Conduct/Maintenance Phase

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.2.1 | SAM/ML/CL | Updates the SAMP and TRR by adding the new countries as needed. Note: If no SAM or ML is assigned, the CL must update the project- specific Clinical Operations Plan (COP) with the appropriate information (instead of the SAMP) and ensure changes are summarized within the document as part of history of changes. The RAd and LRSU Rep(s) must be provided with a copy of the COP in place of the SAMP. | Conduct |
| 6.2.2 | SAM/ML/CL/ RAd (EU CTR) | Collects core and country-specific requirements and works with the Sponsor to obtain documents and establish timelines. Note: SAM/ML/CL performs for non-EU CTR countries, RAd for EU CTR countries. |  |
| 6.2.3 | SAM/ML/ CL/RAd (EU CTR) | Ensures the Regulatory and Ethics submissions are completed as defined in Section 6.1. |  |

  - Preparation of Amendments to the Core or Country/Site CT Application Dossier

Note: Refer to CS_WI_SM0020, Management of Revised Clinical Study Documents, for information about managing changes to Clinical Study Documents.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.1 | SAM/ML/CL | Refers to the project-specific TRR for the agreed scope for post-filing commitments. | Startup and Conduct / Lifecycle Maintenance |
| 6.3.2 |  | Upon receipt of information from the Sponsor or project team of any upcoming global amendments to the study documents: - Informs the RAd about the changes - Determines the submission requirements with the help of the RAd |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | and the LRSU Rep, as appropriate - Asks for the Sponsor’s determination of substantial or non- substantial classification and liaises with the RAd to complete CS_FM_RSU0054, Assessment of Substantiality. Notes: - RA/IEC/IRB notifications are not required for non-substantial amendments unless specified by local regulations (e.g. for studies being conducted under EU CTR it may be necessary for certain changes considered as non-substantial updates to be reflected in the CTIS). Consult the RID and/or RAd and LRSU Rep to determine country or region-specific requirements. - The Assessment of Substantiality is not required for non- interventional studies (i.e., studies without a EudraCT or EU Clinical Trial number, that do not fall under the Clinical Trial Directive or EU CTR). - The RAd will be the main contact for discussion with the Sponsor relating to submission for the transition of clinical studies between the EU regulatory frameworks described by the EU CT Directive and the EU CTR. |  |
| 6.3.3 | RAd | - Prepares CS_FM_RSU0054, Assessment of Substantiality and sends to the Sponsor for review and approval. - In parallel, starts the compilation of the Core CTA submission dossier, including (when in the SoW) the preparation of cover letters and the Substantial Amendment Application Form (for substantial amendments involving EU Member State or EEA countries). Note: these activities, and subsequent steps of Section 6.3 will involve the upload and submission of clinical study documents via the EU CTIS, for amendment submissions performed under the EU CTR. | Startup and Conduct / Lifecycle Maintenance |
| 6.3.4 |  | Performs a QC of all component parts of the Core CT Application dossier (including consideration for any redaction that may be necessary, per step 6.1.12). |  |
| 6.3.5 |  | Completes the Core QC Checklist, files any core documents not already filed and sends the checklist to the SAM/ML/CL for second review. |  |
| 6.3.6 | SAM/ML/CL | Performs a second review and acknowledges the QC by e-signature in the appropriate Trial Management System, ensuring that all documents listed are: - all the documents that are required - the correct version(s) |  |
| 6.3.7 | RAd | - Sends the completed and signed Core QC package for each amendment to the SAM/ML/CL/ - Submits request in the IQVIA Support Portal for cRSU Rep to track the Core documents in the Trial Management System. Note: This does not apply to submission dossiers that do not contain |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | any Core documents as they will be tracked at the country level (e.g., country-specific documents required for a country submission). |  |
| 6.3.8 | RAd | For amendments impacting Part I core documents in studies performed under EU CTR - Prepares Part I amendment information in the CTIS, by upload of core documents and finalization of information included within the EU CT Application Form on the CTIS. - Finalizes documentation required for submission within Part I substantial modification dossier. - Conducts or facilitates any additional Sponsor review activities as described in the SAMP. - Utilizes the information within the Core QC Checklist to prepare a Part I-specific QC checklist, describing all final documents uploaded and planned for submission. - Submits the Part I dossier upon completion of required review. - Follows the process described in step 6.1.14, and monitors and follows-up on the submission to ensure effective completion of Part I submission and authorization process. Note: In parallel to the Part I dossier preparation the RAd is also required to coordinate Part II, country-level submission planning, to ensure steps performed per steps 6.3.10 - 6.3.14 are performed efficiently, and submissions can proceed in parallel or sequentially, as planned. | EU CTR applies and Following Final Core QC of amendment dossier |
| 6.3.9 | RAd/cRSU Rep | Checks the applicable Trial Management System to ensure that all Core documents are tracked and enters any missing information. | Startup and Conduct / Lifecycle Maintenance |
| 6.3.10 |  | Confirms that all documents are tracked into the applicable Trial Management System and filed into TMF. |  |
| 6.3.11 | SAM/ML/CL | Informs the LRSU Rep of the amendment, using the country maintenance mailboxes: - Type of amendment (e.g., Protocol, IB, IMPD, ICF, Delegation Letters, labels, subject-facing documents, EU CT Application Form, any country-specific documents,). - Proposed RA/IEC/IRB submission requirements (ensure this is agreed at country level). - Document availability. - Target timelines for submission. |  |
| 6.3.12 | LRSU Rep/CL | - Uses the Core QC Checklist to prepare a Country QC Checklist to ensure all required documents are included in the submission. - Prepares all necessary documentation required for RA/IEC/IRB submission (including consideration for any redaction that may be necessary, per step 6.1.17) and completes the submission. Note: A Country QC Checklist must be completed for all country submissions prior to submission. |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.3.13 |  | - Prepares all necessary documentation required for RA/IEC/IRB submission if site amendments are required during the project (e.g., addition or removal of an Investigator, addition of a new site or change of address at an existing site with contract changes). - Prepares a Country QC Checklist to ensure all required documents are included in the submission. - Completes the submission and QC of the submission file. | Startup and Conduct / Lifecycle Maintenance When site amendments are required |
|  |  | Note: The CL/ML will be the principle lead role supporting and coordinating LRSU with respect to CT Applications in countries where EU CTR is not applicable, and the RAd will be the principle lead role supporting and coordinating LRSU with respect to CT Applications in countries where EU CTR is applicable. |  |
| 6.3.14 | LRSU Rep | - Monitors the Country/Site assessment status routinely. - Monitors RFI receipt for Part II dossier if the study involves countries where the EU CTR is applicable. - Facilitates, in consultation with the SAM, ML, RAd, PL and Sponsor, the resolution and submission of responses to questions or corrections requested by the RA/IEC/IRB. - Uploads response documents to CTIS, and completes the submission of responses in CTIS, if the study involves countries where EU CTR is applicable. - Verbal discussions and decision points with RA/IEC/IRB should be documented using CS_FM_RSU0015, Regulatory Authority, Institutional Review Board and Ethics Committee Contact Form, if applicable. | Startup and Conduct / Lifecycle Maintenance |
|  |  | - If conditional approval is provided by the RA/IEC/IRB, verifies that all conditions are addressed and resubmits documentation, as requested, within one working day of receipt of conditional approval. |  |
|  |  | - If approved, notifies relevant stakeholders of the approval status and updates the Trial Management System with approval date(s) within one working day of receipt of approval. |  |
|  |  | - If rejected, notifies relevant stakeholders of the rejection status and liaises with the SAM, ML, RAd, PL and Sponsor on follow up actions. |  |
|  |  | - When required, translates approval documentation and /IEC/IRB correspondence per CS_WI_RSU0032, Translation of Documents, - Completes any post-approval activities (e.g., notifications, registrations to national clinical study registries), notifies the SAM/ML/CL/PL and tracks in applicable Trial Management System. - Ensures all documents are filed in the TMF upon receipt (files directly or via Trial Management System workflow process when applicable). |  |

  - Progress Reports and Other Periodic Updates on Study Status

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.4.1 | SAM/ML/CL/R Ad (EU CTR) | Monitors progression of key clinical study Lifecycle Maintenance milestones and provides overall oversight of the submission during the progress reporting process, assisting stakeholders with removal of barriers and resolution of potential issues or delays throughout the clinical study lifecycle maintenance process. | Startup and Conduct / Lifecycle Maintenance |
|  |  | Notes: - Refer to local Wis and/or RID for information on specific country/regional requirements, frequency and content of progress reports. - SAM/ML/CL performs for non-EU CTR countries, RAd for EU CTR countries. |  |
| 6.4.2 | LRSU Rep | - Collects and compiles needed information for the Progress Report from Monitors, Lifecycle Safety/Sponsor’s safety department and other relevant sources (as appropriate). - Completes a Country QC Checklist to ensure all required documents are included in the submission. A QC checklist is not necessary in cases where only a date is being added to a Regulatory Agency system, to indicate a particular step has been reached within the conduct of the clinical study (eg. Notification of date of start of the study or end of enrollment). - Submits Progress report to RA/IEC/IRB as needed. - Tracks in Trial Management System and files checklist and submission package in the TMF. |  |

  - Urgent Safety Measures and Temporary Halt to Clinical Projects

Note: Any Temporary Halt not related to Urgent Safety Measures should be notified to the RA/EC as per country requirements found in RID. In the event that no submission to the RA is required for restarting the study, communication may still be required to inform Regulators of restart to ensure that study status is correctly reflected on Regulatory owned databases.

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.5.1 | PL | Oversees the coordination of submission to the RA/IEC/IRB by the LRSU Rep if the Sponsor or Data Safety Monitoring Board (DSMB) decides that the study requires an Urgent Safety Measure (USM) with or without a Temporary Halt or Premature End of Trial. Notes: - Teams should remain vigilant for any safety issues, particularly those communicated directly through site communications like Dear Investigator Letters (DILs). Additional team activities and responsibilities are also defined in CS_WI_PL0029 Project Management, Communications, and Reporting. | Startup and Conduct / Lifecycle Maintenance |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | - Urgent Safety Measures and Temporary Halt notifications must be made immediately and within timelines mandated per country specific Regulations: - For EU and EEA countries, the submissions to RA/IEC/IRB must follow within 15 days from when the study is temporarily halted. - For all other regions/countries, the LRSU Rep must be consulted regarding the locally-legislated timeframe for the submission. This information is also available in RID. - After the Urgent Safety Measure is confirmed, informs Lifecycle safety that the submission was made so that there is no duplication of submission. |  |
| 6.5.2 | LRSU Rep /RAd (EU CTR) | - Submits USM Notifications to RA/IEC/IRB for full-service studies as applicable per country regulations unless country level processes require another business function (e.g., Lifecycle Safety) to manage notifications to Regulatory and/or other applicable Authorities. - Uses Core QC Checklist to prepare a Country QC Checklist to ensure all required documents are included in the submission. - Prepares all necessary documentation required for RA/IEC/IRB submission (including consideration for any redaction that may be necessary, per step 6.1.17). - Completes the submission. Note: Lifecycle Safety Regulatory Reporting (LS RR) may on occasion be requested to be involved in the submissions of urgent safety measures however coordination and oversight of such submissions remains an RSU responsibility. RAd will be responsible for submission of USM via CTIS for countries where EU CTR is applicable. | Startup and Conduct / Lifecycle Maintenance |
| 6.5.3 | LRSU Rep /RAd (EU CTR) | Ensures all documents are filed in the TMF. |  |

  - End of Trial (EoT)/Early Termination Notifications

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.6.1 | CML/ML/ SAM | Determines the EoT/Early Termination submission requirements for the countries involved using RID and input from the RAd and LRSU Rep. | End of Trial |
| 6.6.2 |  | Gathers any additional Core documents/data that regions/countries require to prepare submission, then enters the global EoT/Early Termination date into the Trial Management System. |  |
| 6.6.3 | RAd | - Prepares Core QC Checklist and Global EoT Notification documentation (including consideration for any redaction that |  |

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
|  |  | may be necessary, per step 6.1.12). - Prepares information relating to Early End of Trial Notification, in cases where additional explanation or justification of the reasons for the Early End of Trial are necessary. |  |
| 6.6.4 | LRSU Rep CML/ML/SAM | - Performs local EoT/Early Termination Notifications, as applicable. - Enters the local submission dates into the Trial Management System. - Notifies SAM/ML/CML when EoT submission is completed. - Ensures all documents are filed in the TMF. | End of Trial |
| 6.6.5 |  | Follows up with LRSU Rep until completion of the EoT submission and filing has occurred. Escalates to the LRSU Rep’s Line Manager, if needed. |  |

  - Clinical Study Report (CSR) Submissions

| No: | Who: | Step: | When: |
| --- | --- | --- | --- |
| 6.7.1 | ML/CL/CML / RAd (EU CTR | - Collects country requirements and legislated timelines for submission of the Clinical Study Report (CSR) using RID. - Determines whether countries require the full report or only a synopsis or if the results will be posted in the EudraCT any country-specific or regional (e.g. EU) database by the Sponsor. Note: ML/CL performs for non-EU CTR countries, RAd for EU CTR Countries. | Project Close, End of study |
| 6.7.2 |  | Follows up with the Sponsor to ensure that the CSR is ready in time to meet all country requirements and sends the documents to the RAd after it is received. |  |
| 6.7.3 | RAd | Completes the Core QC Checklist and all the actions (including consideration for any redaction that may be necessary, per step 6.1.12). |  |
| 6.7.4 | LRSU Rep/ RAd (EU CTR) | Prepares the country submission and Country QC Checklist using the Core QC Checklist to ensure all required documents are included in the submission and performs the submission as per local Regulatory requirements. |  |
| 6.7.5 |  | Ensures all documents are filed in the TMF. Note: LRSU Rep performs for non-EU CTR countries, RAd for EU CTR countries. |  |

- SUPPORTING DOCUMENTATION

| DOCUMENT NUMBER | TITLE |
| --- | --- |
| ESOP References |  |
| 7.1 QG_OD_SMT0018 | Glossary of Terms – Clinical Services |

| DOCUMENT NUMBER | TITLE |  |
| --- | --- | --- |
| ESOP References |  |  |
| 7.2 CS_TP_RSU0024 | Global QC Checklist for Clinical Trial Submission Documents |  |
| 7.3 CS_TP_RSU0025 | Country QC Checklist for Clinical Trial Submission Documents |  |
| 7.4 CS_TP_RSU0013 | Site Activation Management Plan |  |
| 7.5 CS_OP_RSU0060 | Site Activation |  |
| 7.6 CS_TP_RSU0023 | Table of Regulatory Responsibilities |  |
| 7.7 CS_TP_RSU0009 | Transfer of Regulatory Obligations |  |
| 7.8 CS_WI_RSU0021 | Essential Documents Pack |  |
| 7.9 CS_FM_RSU0047 | Essential Documents Pack - Requirements Form |  |
| 7.10 CS_WI_RSU0068 | Site Ready to Enroll Execution and Oversight |  |
| 7.11 CS_WI_RSU0019 | Investigational Product Label Review |  |
| 7.12 CS_WI_RSU0033 | Creation and Review of the Informed Consent Form |  |
| 7.13 CS_FM_RSU0034 | Regulatory Review Checklist for Subject Recruitment Material |  |
| 7.14 CS_FM_RSU0015 | Regulatory Authority, Institutional Review Board and Ethics Committee Contact Form |  |
| 7.15 CS_WI_RSU0032 | Translation of Documents |  |
| 7.16 CS_WI_SM0020 | Management of Revised Clinical Study Documents |  |
| 7.17 CS_FM_RSU0054 | Assessment of Substantiality |  |
| 7.18 CS_WI_PL0029 | Project Management, Communications, and Reporting |  |
| EXTERNAL REFERENCES |  |  |
| 7.19 Redaction Guidance and Tools | EU Clinical Trial Regulation for IQVIA Project Teams |  |

- SUPERSEDES

| DOCUMENT NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 8.1 CS_WI_RSU0067 | Project Lifecyle Clinical Trial Applications | 1 |

- MODIFICATION FROM PREVIOUS REVISION

| CHANGE | SECTION REFERENCE | JUSTIFICATION |
| --- | --- | --- |
| Updated section 3.0 to match current document | 3.0 | Corrections |
| Added note regarding EU Clinical Trial Regulation | 3.0 | New regulation |
| Update SOP titles as needed | Throughout | To match current SOP titles |
| Added definitions for CTSI and Redaction | 4.0 | New processes include new terminology |
| Removed reference to VHP submissions | Throughout | Will no longer be available option |
| Added note that the SAM will perform task for non-EU CTR Countries and RAd will perform for the EU CTR Countries. | 6.1.1 | Change in process |
| Added process for establishing access to EU CTIS | 6.1.9 | New process |
| Removed reference to CS_FM_RSU0058 | 6.1.10 | Form is obsolete |
| Added information about the EU CTR process. Including making the RAd responsible for oversight of Part II submissions in EU CTR Countries, and SAM responsible for Country submission oversight in non-EU CTR countries. | Throughout | New process |

- APPENDICES

  - Appendix A: Example List of Documents to be included in Core Clinical Trial Application

Appendix A: Example List of Documents to be included in Core Clinical Trial Application

    - Cover Letter template including a Table of Contents for the dossier

    - Scientific Advice

    - Delegation Letter

    - EU Legal Representative for non-EU Sponsor

    - EudraCT Application Form and number

    - List of Regulatory Authorities

    - Project Protocol

    - Protocol Synopsis

    - Investigator’s Brochure (IB)

    - Master Informed Consent Form (ICF) (refer to CS_WI_RSU0033, Creation and Review of the Informed Consent Form) for more detail on the ICF creation process)

    - Investigational Medicinal Product Dossier (IMPD) and related GMP documentation

    - List of ongoing projects with the Investigational Product

    - Non-Investigational Medicinal Product (nIMP) Dossier

    - Labeling (refer to CS_WI_RSU0019, Investigational Product Label Review)

    - Patient Recruitment material. Specific documents are determined by project scope that can include subject-facing recruitment, compliance, and retention materials (e.g., posters, brochures), advertisements, and/or site tools

    - Patient Questionnaires, Patient Cards, and other mandatory submission documents

Note: Refer to RID for any templates that can be used in preparing some of these documents.

Page 19 of 19

Copyright © 2020, 2021 IQVIA. All rights reserved. The contents of this document are confidential and proprietary to IQVIA Holdings, Inc. and its subsidiaries. Unauthorized use, disclosure or reproduction is strictly prohibited.

Standard Operating Procedure Approval Signature(s)

This is a representation of an electronic record that was signed electronically in Content Server.

This page is the manifestation of the electronic signature(s) used in compliance with the organization’s electronic signature policies and procedures

Refer to Signatories CV for Business Title.

UserName: Trieschmann, Twila (q405536) Title:

Date: Thursday, 14 October 2021, 08:51 PM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nikolova, Danny (q601511) Title:

Date: Friday, 15 October 2021, 03:24 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================

UserName: Nufer, Letha (q012496) Title:

Date: Friday, 15 October 2021, 09:07 AM Eastern Time Meaning: Signing this Document Indicates My Approval

================================================